NATIONAL LEPROSY ERADICATION PROGRAMME

Project Implementation Plan  2026-2027

Objectives:

The main objectives under NLEP may be reiterated here :

1. Elimination of Leprosy i.e. Prevalence of less than 1 case per 10,000 population in all the blocks / districts of the State.

2. Early case detection without deformity.

3. Strengthen Disability Prevention & Medical (DPMR) of Persons affected by Leprosy. 4. Reduction in the level of Stigma associated with Leprosy.

Case Detection and Management: Specific plan for high endemic district :

Given the limited budget for NLEP and the fact that it is now in the elimination phase, it is essential to perform re-surveys and conduct Active Case Detection Campaigns in districts that have had no reported leprosy cases for five consecutive years. In this context, five districts namely Aizawl West, Champhai, Saiha, Mamit and Serchhip districts  will be thoroughly surveyed to ensure they can be declared as leprosy-free. This Leprosy Case Detection Campaign will be comprehensive and will depend significantly on additional manpower from the districts, in addition to the team sent from the state headquarters, technicial and non-technical staff under each district will be utilized and incentivized .As desired by Central Leprosy Division, this LCDC is proposed under this head as there is no separate budget head for LCDC. Rs 1,20,000/- each is proposed  for these five districts which is Rs 6,00,000/-

Case Detection and Management Service in Urban Areas:

Although it is highly anticipated that the migrating population in and around Aizawl City and Lunglei may have many hidden leprosy cases, Active Case Surveillance conducted randomly at several places in and around Aizawl City didn’t have the anticipated result. It is still considered very important to screen as much as possible migrant populations and contacts of recent case of leprosy detection. Rs 2,40,000/- is considered sufficient for this purpose.

Welfare Allowance to patients for Reconstructive Surgery:

Not Proposed as the case never arise.

ASHA incentive for detection and treatment :

The following are proposed in anticipation of cases:

1) Case diagnosis (3.1.1.4.7.a) :  Rs 250 x 40 per case			-	Rs   10,000/-

2) Treatment completion of MB cases (3.1.1.4.7.b)- Rs 600 x 20 cases 	-	Rs   12,000/-

3) Treatment completion of PB cases (3.1.1.4.7.c) – Rs 400 x 20 cases  	-	Rs     8,000/-

Total		-	Rs    30,000/-

Procurement of bio-medical equipment:-

Not proposed.

Micro Cellular Rubber : MCR footwear are not current required and is not proposed.

Aids and Appliances : Not proposed during the current PIP.

Supportive drugs and Laboratory Reagents:

Rifampicin/chofazimine a prophylaxis drugs may be procured in small quantity as need basis. Considering the trend of detection during the recent years. Rs 10,000 is deemed sufficient. The same amount is proposed during 2026-27

Capacity Building ( Trainings under NLEP) :

As 3 Non-Medical Officers from our state has already completed their training at Gouripur, it is considered more effective to deploy them at Local Case Detection Campaign, separate training for other staff and ASHAs is considered not necessary for the moment.

NLEP review meetings:

Quarterly review meetings will be conducted if fund is available,  during 2026-2027 with the districts, Rs 2,58,000/- is proposed which is 5% increase from previous year’s proposal.

Travel Expenses - Contractual Staff at State Level :

Rs 1,15,000 is proposed for travel expenses of Contractual staff at state level to be utilized for monitoring visit of Districts Leprosy Cells with 5% increased from previous years approval .

Mobility Support –State Cell :

Rs 1,58,000/- is proposed to be utilized for maintenance of vehicle, purchase of POL etc. at the state headquarters with 5%  increased from previous year’s proposal.

NLEP Review Meetings:

Rs 2,42,000/- which is 5% hike from previous years approval is proposed for conducting Review Meetings under NLEP.

Office Operation & Maintenance -State Cell :

Ongoing activity, proposed with 5% increase from previous year’s approval.            Rs 1,08,000/- is proposed.

Office Operation & Maintenance - District  Cell :-

Ongoing activity, Rs 48,000/- each for 12 Districts i.e, Rs 5,76,,000/-  is proposed with 5%  increment from previous approval. It may be noted that, Mizoram has 3 new Districts namely; Hnahthial, Khawzawl and Saitual District which now have a separate Chief Medical Officers and separate Treasury Office.

Consumables - State Cell:

Rs 75,000/- is proposed with 5% increment from last proposal.

Consumables -District Cell:

Rs 4,32,000/- is proposed for 12 districts (explained above)   with 5% increase from previous proposal which is 36,000 for each district.

Others - Travel Expenses for Regular Staff :

It may be noted that all the staff in the Districts are regular employees and their travelling expenses cannot be paid from NLEP fund. The State Leprosy officer and Non-Medical Officer at the state were  constantly called for training and review meetings etc. outside the state and elsewhere in which the state is always given instruction to meet the expenditure from State Leprosy fund. It is very important that some funds should be set aside for meeting these expenditures and Rs 2,10,000/- is proposed again without increment .

IEC/BCC Activities under NLEP :

Rs 4,83,000/- is proposed for enhanced IEC/BCC activities with 5%  increment from previous  proposalto aid in the Local Case Detectection Campaigns to be conducted during this year. Under IEC activities the following activities will continued to be conducted during the current year :

- Displaying of NLEP posters at City Buses, Town Buses, Local Taxis during the Leprosy Forthnight.(This is among the best practices under NHM Mizoram).

- Leprosy messages will be broadcasted and telecasted at Local Radio Stations and Local Channels which have a huge coverage of the population.

- Franchisee will be sought with huge events in the state as far as possible to enable widespread communication for awareness and elimination of stigma.

Printing activities under NLEP:

As proposed earlier, extensive Leprosy Case Detection Campaign will be conducted, to aid this campaign, several IEC materials will be needed. Rs 4,00,000/- is proposed for this purpose.

BUDGET SUMMARY

Project Implementation Plan 2026-2027

| NATIONAL LEPROSY ERADICATION PROGRAMME (NLEP) 2025-2026 |  |  |  |  |
| --- | --- | --- | --- | --- |
|  | Budget Head |  | Particulars | Total Proposed |
| NDCP.3 | DCP | Surveillance, Research, Review, Evaluation (SRRE) | CD&M Specific Plan for High Endemic District | 6.00 |
| NDCP.4 | DCP | Others including operating costs(OOC) | Case Detection & Management services in Urban Areas | 2.40 |
| NDCP.4 | DCP |  | Welfare Allowance to patients for RCS | 0.00 |
| HSS.17 | Case detection and Management | ASHA incentives | ASHA involvement under NLEP | 0.30 |
| NDCP.3 | DCP |  | Procurement of bio-medical equipment | 0.00 |
| NDCP.4 |  |  | Supportive Drugs and Lab. Reagents | 0.10 |
| NDCP.3 | Case detection and Management | Equipment (Including Furniture, Excluding Computers) | Aids/Appliance | 0.00 |
| HSS.16 | Case detection and Management | Capacity building incl. training | Trainings under NLEP (Capacity Building) | 0.00 |
| HSS.11 | Case detection and Management | Others including operating costs(OOC) | Travel Expenses – Contractual Staff at State Level | 1.15 |
| HSS.11 | Case detection and Management | Others including operating costs(OOC) | Mobility support ( State cell) | 1.58 |
| HSS.11 | Case detection and Management | Surveillance, Research, Review, Evaluation (SRRE) | NLEP Review Meetings | 2.42 |
| HSS.11 | Other NLEP Components | Others including operating costs(OOC) | Office Operation & Maintenance – State Cell | 1.08 |
| HSS.11 | Other NLEP Components | Others including operating costs(OOC) | State Cell – Consumables | 0.75 |
| HSS.11 | Other NLEP Components | Others including operating costs(OOC) | Office Operation & Maintenance – District Cell | 5.76 |
| HSS.11 | Other NLEP Components | Others including operating costs(OOC) | Consumables - District Cell | 4.32 |
| HSS.11 | Other NLEP Components | Others including operating costs(OOC) | Others – Travel Expenses for Regular Staff | 2.10 |
| HSS.19 | Case detection and Management | IEC & Printing | IEC/BCC activities under NLEP | 4.83 |
| HSS.19 | Case detection and Management | IEC & Printing | Printing activities Under NLEP | 4.00 |
|  |  |  | G TOTAL | 36.79 |