COMPREHENSIVE PRIMARY HEALTH CENTRE

NATIONAL HEALTH MISSION

GOVERNMENT OF MIZORAM

PROGRAMME IMPLEMENTATION PLAN FOR 2026-2027

HSS.1 Comprehensive Primary Healthcare (CPHC) Health & Wellness Centers - Rural

Delivery of Comprehensive Primary Health Care (CPHC) through Health & Wellness Centres (AAMs) is a flagship programme of the current Central Government which has the potential to transform the health system in India including Mizoram in the years to come. AAMs is a health system strengthening project that aims to strengthen the core pillars of the health system that are:

- Human Resource - One additional manpower of Mid-level health providers (MLHPs) is to be posted in all Ayushman Arogya Mandirs. Mizoram designated CHOs as ‘Health & Wellness Officers’ (HWOs) as Community Health Officers (CHOs) is already a regular cadre of CHOs in the state.

- Health financing - Innovative health financing in the form of incentives and enhanced untied funds to sub-centres. The enhanced untied fund of Rs. 50,000 per Sub-Centre is adopted by the state.

- Governance - Performance linked payments (PLPs) after rigorous assessments through independent monitoring has the potential to improve upon governance and also staff performance.

- Essential drugs & technology - Provisions have been made through the programme to make available all essential drugs in Essential Medicines list (EML) and to provide a set list of diagnostics free of cost at all AAMs.

- Health services - promotive, preventive, curation, rehabilitative & palliative care are to be provided as appropriate to the level of facility and at community level. There are 12 packages of health services that are to be rolled out.

- Health information system - AAM portal has been developed that aid in programme management and monitoring. The portal is to be integrated with other applications such as NCD app.

Ministry of Health & Family Welfare (MoHFW) aims for conversion of all Sub-Centres (SCs) and Primary Health Centres (PHCs) into Health & Wellness Centres by December, 2022. Sharing this endeavor, Mizoram is able to achieve the December 2022 target. In the table below, we have highlighted the yearly target for conversion of SCs and PHCs into AAMs by 2026-2027.

| Year | Rural PHCs | Urban PHCs | SCs |
| --- | --- | --- | --- |
| 2018-19 | 4 | 8 | 20 |
| 2019-20 | 52 | 0 | 29 |
| 2020-21 | 1 | 0 | 79 |
| 2021-22 | 0 | 0 | 120 |
| 2022-23 | 3 | 0 | 27 |
| 2023-24 | 0 | 0 | 8 |
| 2024-25 | 0 | 1 | 15 |
| 2025-26 | 0 | 0 | 11 |
| 2026-27 | -2 | 1 | 23 |
| Total | 58 | 10 | 313 |

For upgradation and facilitate to provide Comprehensive Primary Care at existing Sub-Centers and Primary Health Center AAMs we propose for the following activities:

Sl No.150. Development and Operations

- Infrastructure Strengthening of SCs to AAM: The amount proposed is for

Infrastructure Strengthening of SCs to AAM @ Rs. 1 lakh per SHC for 23 new SHC-AAM.

| Total no. of SHCs proposed | Unit cost in Rs. | Total cost in Rs. |
| --- | --- | --- |
| 23 | 1,00,000 | 23,00,000 |

(Rupees Twenty-Three Lakhs only)

- Infrastructure Strengthening of PHCs to AAM: The amount proposed is for

Infrastructure Strengthening of PHCs to AAM @ Rs. 1 lakh per PHC for 10 new PHC-AAM.

| Total no. of PHCs proposed | Unit cost in Rs. | Total cost in Rs. |
| --- | --- | --- |
| 10 | 1,00,000 | 10,00,000 |

(Rupees Ten Lakhs only)

3.        Capacity Building including Training: This budget head has been split into the different components as below: -

- Bridge Course/Standard Treatment Protocols: We are proposing 23 CCH trainees under IGNOU – 6 months CCH training: The total estimated cost for each student for IGNOU BPCCHN & development/roll-out of Standard Treatment Protocols (STPs) is Rs.1,03,400 per student.

| Total no. of trainees | Unit cost in Rs. | Total cost in Rs. |
| --- | --- | --- |
| 23 | 1,03,400 | 23,78,200 |

(Rupees Twenty-Three Lakhs Seventy-Eight Thousand Two Hundred only)

- Refresher/ Multiskilling/ Training for ANM, MPW, ASHAs: The aim of this training is to build capacity of ANMs, ASHAs & MPWs in sub-centers to be able to manage all of minor ailments for delivery of Comprehensive Primary Health Care. Refresher training of ASHAs & ANMs on Expanded range of services will also be met form this head.

Refresher Multiskilling training for ANM, MPW, ASHAs @Rs.3000 per ASHAs for 995 rural ASHAs, @Rs.5000 per ANM/MPWs for 866 ANM/MPWs

| Sl. No | District | Amount Proposed |
| --- | --- | --- |
| 1 | Aizawl East | ₹ 9,52,000 |
| 2 | Aizawl West | ₹ 9,77,000 |
| 3 | Champhai | ₹ 5,09,000 |
| 4 | Hnahthial | ₹ 3,24,000 |
| 5 | Khawzawl | ₹ 3,37,000 |
| 6 | Kolasib | ₹ 5,28,000 |
| 7 | Mamit | ₹ 6,06,000 |
| 8 | Saitual | ₹ 4,08,000 |
| 9 | Serchhip | ₹ 5,83,000 |
| TOTAL |  | ₹ 52,24,000 |

(Rupees Fifty-Two Lakhs, Twenty-Four Thousand Only)

District wise budget break up for Refresher Multiskilling training for ANM, MPW, ASHAs:

- Aizawl East:

| Particulars | Rate | 1st batch | 2nd batch | 3rd batch | 4th batch | Total | No of days | Amount |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Hall Rent | 4,000 | 4,000 | 4,000 | 4,000 | 4,000 | 16,000 | 3 | 48,000 |
| Resource Fee | 1,000 | 4 | 4 | 4 | 4 | 16 | 3 | 48,000 |
| Refreshment | 200 | 56 | 56 | 56 | 58 | 226 | 3 | 1,35,600 |
| TADA & Accommodation | 3,000 | 56 | 56 | 56 | 58 | 226 |  | 6,78,000 |
| Training aid |  |  |  |  |  |  |  | 42,400 |
| G.Total |  |  |  |  |  |  |  | 9,52,000 |

- Aizawl West:

| Particulars | Rate | 1st batch | 2nd batch | 3rd batch | 4th batch | Total | No of days | Amount |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Hall Rent | 4,000 | 4,000 | 4,000 | 4,000 | 4,000 | 16,000 | 3 | 48,000 |
| Resource Fee | 1,000 | 4 | 4 | 4 | 4 | 16 | 3 | 48,000 |
| Refreshment | 200 | 56 | 56 | 57 | 58 | 227 | 3 | 1,36,200 |
| TADA & Accommodation | 3,000 | 56 | 56 | 57 | 58 | 227 |  | 6,81,000 |
| Training Aid |  |  |  |  |  |  |  | 63,800 |
| G.Total |  |  |  |  |  |  |  | 9,77,000 |

- Champhai:

| Particulars | Rate | 1st batch | 2nd batch | 3rd batch | Total | No of days | Amount |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Hall Rent | 4,000 | 4,000 | 4,000 | 4,000 | 12,000 | 3 | 36,000 |
| Resource Fee | 1,000 | 4 | 4 | 4 | 12 | 3 | 36,000 |
| Refreshment | 200 | 43 | 43 | 41 | 127 | 3 | 76,200 |
| TADA & Accommodation | 3,000 | 56 | 56 | 57 | 112 |  | 3,36,000 |
| Training Aid |  |  |  |  |  |  | 24,800 |
| G.Total |  |  |  |  |  |  | 5,09,000 |

- Hnahthial:

| Particulars | Rate | 1st batch | 2nd batch | Total | No of days | Total |
| --- | --- | --- | --- | --- | --- | --- |
| Hall Rent | 4,000 | 4,000 | 4,000 | 8,000 | 3 | 24,000 |
| Resource Fee | 1,000 | 4 | 4 | 8 | 3 | 24,000 |
| Refreshment | 200 | 40 | 42 | 82 | 3 | 49,200 |
| TADA & Accommodation | 3,000 | 40 | 42 | 68 |  | 2,04,000 |
| Training Aid |  |  |  |  |  | 22,800 |
| G.Total |  |  |  |  |  | 3,24,000 |

- Khawzawl:

| Particulars | Rate | 1st batch | 2nd batch | Total | No of days | Total |
| --- | --- | --- | --- | --- | --- | --- |
| Hall Rent | 4,000 | 4,000 | 4,000 | 8,000 | 3 | 24,000 |
| Resource Fee | 1,000 | 4 | 4 | 8 | 3 | 24,000 |
| Refreshment | 200 | 43 | 42 | 85 | 3 | 51,000 |
| TADA & Accommodation | 3,000 | 43 | 42 | 70 |  | 2,10,000 |
| Training Aid |  |  |  |  |  | 28,000 |
| G.Total |  |  |  |  |  | 3,37,000 |

- Kolasib:

| Particulars | Rate | 1st batch | 2nd batch | 3rd batch | Total | No of days | Total |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Hall Rent | 4,000 | 4,000 | 4,000 | 4,000 | 12,000 | 3 | 36,000 |
| Resource Fee | 1,000 | 4 | 4 | 4 | 12 | 3 | 36,000 |
| Refreshment | 200 | 46 | 46 | 46 | 138 | 3 | 82,800 |
| TADA & Accommodation | 3,000 | 46 | 46 | 46 | 111 |  | 3,33,000 |
| Training Aid |  |  |  |  |  |  | 40,200 |
| G.Total |  |  |  |  |  |  | 5,28,000 |

- Mamit:

| Particulars | Rate | 1st batch | 2nd batch | 3rd batch | Total | No of days | Total |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Hall Rent | 4,000 | 4,000 | 4,000 | 4,000 | 12,000 | 3 | 36,000 |
| Resource Fee | 1,000 | 4 | 4 | 4 | 12 | 3 | 36,000 |
| Refreshment | 200 | 50 | 50 | 54 | 154 | 3 | 92,400 |
| TADA & Accommodation | 3,000 | 50 | 50 | 54 | 131 |  | 3,93,000 |
| Training Aid |  |  |  |  |  |  | 48,600 |
| G.Total |  |  |  |  |  |  | 6,06,000 |

- Saitual:

| Particulars | Rate | 1st batch | 2nd batch | Total | No of days | Total |
| --- | --- | --- | --- | --- | --- | --- |
| Hall Rent | 4,000 | 4,000 | 4,000 | 8,000 | 3 | 24,000 |
| Resource Fee | 1,000 | 4 | 4 | 8 | 3 | 24,000 |
| Refreshment | 200 | 50 | 52 | 102 | 3 | 61,200 |
| TADA & Accommodation | 3,000 | 50 | 52 | 89 |  | 2,67,000 |
| Training Aid |  |  |  |  |  | 31,800 |
| G.Total |  |  |  |  |  | 4,08,000 |

- Serchhip:

| Particulars | Rate | 1st batch | 2nd batch | 3rd batch | Total | No of days | Total |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Hall Rent | 4,000 | 4,000 | 4,000 | 4,000 | 12,000 | 3 | 36,000 |
| Resource Fee | 1,000 | 4 | 4 | 4 | 12 | 3 | 36,000 |
| Refreshment | 200 | 50 | 50 | 45 | 145 | 3 | 87,000 |
| TADA & Accommodation | 3,000 | 50 | 50 | 45 | 131 |  | 3,93,000 |
| Training Aid |  |  |  |  |  |  | 31,000 |
| G.Total |  |  |  |  |  |  | 5,83,000 |

- Refresher training of 116 Staff Nurses at PHCs on Expanded Package Services @Rs. 3000 per person

| Particulars | Rate | 1st batch | 2nd batch | Total | No of days | Total |
| --- | --- | --- | --- | --- | --- | --- |
| Hall Rent | 4,000 | 4,000 | 4,000 | 8,000 | 3 | 24,000 |
| Resource Fee | 1,000 | 4 | 4 | 8 | 3 | 24,000 |
| Refreshment | 200 | 60 | 56 | 120 | 3 | 72,000 |
| TADA & Accommodation | 3,000 | 60 | 56 | 68 |  | 2,04,000 |
| Training Aid |  |  |  |  |  | 24,000 |
| G.Total |  |  |  |  |  | 3,48,000 |

(Rupees Three Lakhs Forty-Eight Thousand only)

D. Training of MO's on Expanded Package Service @10000 per person for 20 new MO's

| Particulars | No of days | Rate/unit | Unit | Total |
| --- | --- | --- | --- | --- |
| Hall Rent | 3 | 4000 |  | 12,000 |
| Resource Fee | 3 | 2000 | 5 | 30,000 |
| Refreshment | 3 | 250 | 20 | 15,000 |
| TADA & Accommodation |  | 7000 | 20 | 1,40,000 |
| Training Aid |  | 150 | 20 | 3,000 |
| G.Total |  |  |  | 2,00,000 |

(Rupees Two Lakhs Only)

- Training of new CHOs on CHO induction module @10,000 for 23 CHOs

| Particulars | No of days | Rate/unit | Unit | Total |
| --- | --- | --- | --- | --- |
| Hall Rent | 10 | 4000 |  | 40,000 |
| Resource Fee | 10 | 2000 | 3 | 60,000 |
| Refreshment | 10 | 200 | 23 | 46,000 |
| TADA & Accommodation | 10 | 300 | 23 | 69,000 |
| Training Aid |  | 100 | 23 | 2,300 |
| Contingency |  |  |  | 12,700 |
| G.Total |  |  |  | 2,30,000 |

(Rupees Two Lakh Thirty Thousand only)

- Refresher Training of CHOs on Expanded Package of Services @ Rs. 6000 per CHO for 80 missed CHOs in the previous training: -

| Particulars | Unit Cost | 1st Batch | 2nd Batch | No of participants | No. of Days | Amount |
| --- | --- | --- | --- | --- | --- | --- |
| Hall Rent | 4000 |  |  |  | 3 | 12,000 |
| Resource Fee | 1000 | 4 | 4 | 8 | 3 | 24,000 |
| Refreshment | 300 | 40 | 40 | 80 | 3 | 72,000 |
| TADA & Accommodation | 4000 | 40 | 40 | 80 |  | 3,20,000 |
| Training Aid | 350 | 40 | 40 | 80 |  | 28,000 |
| Contingencies |  |  |  |  |  | 24,000 |
| Grand Total |  |  |  |  |  | 4,80,000 |

(Rupees Four Lakhs Eighty Thousand only)

- CHO Mentoring: Remuneration of CHO mentors @ 150 for 12 months x 72 CHOs

| No. of CHO proposed | Unit cost in Rs. | Total cost in Rs. |
| --- | --- | --- |
| 72 | 150 x 12 months | 1,29,600 |

(Rupees One Lakh Twenty-Nine Thousand Six Hundred only)

- Procurement of Equipment (including furniture):

A.  Procurement of Supplies for Newly Proposed AAM: The amount proposed is for equipping new 23 AAM @ Rs. 50,000 per AAM under Aizawl East, Khawzawl, Kolasib, Lawngtlai,  Lunglei , Serchhip & Siaha districts in terms of furniture and basic equipment for functionalization of the AAM.

| Total no. of SHCs proposed | Unit cost in Rs. | Total cost in Rs. |
| --- | --- | --- |
| 23 | 50,000 | 11,50,000 |

(Rupees Eleven Lakhs Fifty Thousand only)

B. Procurement of Diagnostics (Consumables, PPP, Sample Transport): The amount is proposed for procuring essential diagnostics and consumables for 347 AAM Procurement of diagnostic for 347 AAM i.e. 289 SC and 58 PHCs @Rs. 30,000 per AAM to ensure availability of essential services as per operational guidelines at all AAM.

| S.No | District | Total no. of AAM | Unit cost in Rs. | Total cost in Rs. |
| --- | --- | --- | --- | --- |
| 1 | Aizawl East | 37 | 30,000 | 11,10,000 |
| 2 | Aizawl West | 36 | 30,000 | 10,80,000 |
| 3 | Champhai | 26 | 30,000 | 7,80,000 |
| 4 | Hnahthial | 15 | 30,000 | 4,50,000 |
| 5 | Khawzawl | 20 | 30,000 | 6,00,000 |
| 6 | Kolasib | 26 | 30,000 | 7,80,000 |
| 7 | Lawngtlai | 30 | 30,000 | 9,00,000 |
| 8 | Lunglei | 49 | 30,000 | 14,70,000 |
| 9 | Mamit | 39 | 30,000 | 11,70,000 |
| 10 | Saitual | 21 | 30,000 | 6,30,000 |
| 11 | Serchhip | 26 | 30,000 | 7,80,000 |
| 12 | Siaha | 22 | 30,000 | 6,60,000 |
|  | Grand Total | 347 |  | 104,10,000 |

(Rupees One Crore Four Lakhs and Ten Thousand only)

- Wellness activities at AAM-Rural: The amount proposed is for organizing wellness activities @ Wellness @ Rs. 1000/AAM for 347 AAM organizing wellness at AAMs

| S.No | District | Total no. of AAM | Unit cost | Total cost in Rs. |
| --- | --- | --- | --- | --- |
| 1 | Aizawl East | 37 | 1000 | 37,000 |
| 2 | Aizawl West | 36 | 1000 | 36,000 |
| 3 | Champhai | 26 | 1000 | 26,000 |
| 4 | Hnahthial | 15 | 1000 | 15,000 |
| 5 | Khawzawl | 20 | 1000 | 20,000 |
| 6 | Kolasib | 26 | 1000 | 26,000 |
| 7 | Lawngtlai | 30 | 1000 | 30,000 |
| 8 | Lunglei | 49 | 1000 | 49,000 |
| 9 | Mamit | 39 | 1000 | 39,000 |
| 10 | Saitual | 21 | 1000 | 21,000 |
| 11 | Serchhip | 26 | 1000 | 26,000 |
| 12 | Siaha | 22 | 1000 | 22,000 |
|  | Grand Total | 347 |  | 3,47,000 |

(Rupees Three Lakhs and Forty-Seven Thousand only)

- Printing of IECs: The amount proposed is for printing IEC materials @ 20,000/ AAM for 347 AAMs

| S.No | District | Total no. of AAM | Unit cost in Rs. | Total cost in Rs. |
| --- | --- | --- | --- | --- |
| 1 | Aizawl East | 37 | 20,000 | 7,40,000 |
| 1 | Aizawl West | 36 | 20,000 | 7,20,000 |
| 2 | Champhai | 26 | 20,000 | 5,20,000 |
| 3 | Hnahthial | 15 | 20,000 | 3,00,000 |
| 4 | Khawzawl | 20 | 20,000 | 4,00,000 |
| 5 | Kolasib | 26 | 20,000 | 5,20,000 |
| 6 | Lawngtlai | 30 | 20,000 | 6,00,000 |
| 7 | Lunglei | 49 | 20,000 | 9,80,000 |
| 8 | Mamit | 39 | 20,000 | 7,80,000 |
| 9 | Saitual | 21 | 20,000 | 4,20,000 |
| 10 | Serchhip | 26 | 20,000 | 5,20,000 |
| 11 | Siaha | 22 | 20,000 | 4,40,000 |
|  | Grand Total | 347 | 20,000 | 69,40,000 |

(Rupees Sixty-Nine Lakhs and Forty Thousand only)

- Ayushman Arogya Shivir: The amount proposed is for Organizing Specialist clinic @Rs. 5000/facility for 128 facilities once a month x 12 months (61 SCs, 58PHCs and 9 CHCs). We proposed for all SHCs, PHC and CHCs for Aizawl East and Aizawl West. For other districts, we proposed only for PHCs due to inadequate specialist doctors.

| S.N | District | Total no. of health facility proposed | Cost Per month | Month | Total |
| --- | --- | --- | --- | --- | --- |
| 1 | Aizawl East | 39 | 5000 | 12 | 2340000 |
| 2 | Aizawl West | 37 | 5000 | 12 | 2220000 |
| 3 | Champhai | 5 | 5000 | 12 | 300000 |
| 4 | Hnahthial | 5 | 5000 | 12 | 300000 |
| 5 | Khawzawl | 4 | 5000 | 12 | 240000 |
| 6 | Kolasib | 5 | 5000 | 12 | 300000 |
| 6 | Lawngtlai | 6 | 5000 | 12 | 360000 |
| 8 | Lunglei | 5 | 5000 | 12 | 300000 |
| 9 | Mamit | 8 | 5000 | 12 | 480000 |
| 10 | Saitual | 5 | 5000 | 12 | 300000 |
| 11 | Serchhip | 5 | 5000 | 12 | 300000 |
| 12 | Siaha | 4 | 5000 | 12 | 240000 |
| Grand Total |  | 128 | Rs. 76,80,000 |  |  |

(Rupees Seventy Six Lakhs, Eighty Thousand only)

- Teleconsultation: The amount proposed is for Specialist remuneration for 12 DHs -once a week for 12 months i.e. 52 weeks @Rs.1000

- e-Sanjeevani AAM is being implemented in almost all AAMs and efforts are being made to operationalize telemedicine services

- We have not proposed for HR component due to limited Resource Envelope and huge proportion of RE being spent on HR.

- District hospitals will predominantly receive teleconsultations from PHC-AAMs. As per need, they may also cater directly to SC-AAMs.

- PHC-AAMs will link to SC-AAMs for teleconsultation.

- Teleconsultation sessions will be held in District hospitals in space provided by them.

- Teleconsultation sessions will be conducted by in-house specialists who will be remunerated Rs. 1,000 per session irrespective of the number of consultations done per session.

- Sessions will be conducted once a week for 52 weeks per year.

- Each session will be conducted in the afternoons and should last for a minimum of 2 hours. Attempt should be made to connect with all PHC-AAMs within each district per session.

| Component | Unit Cost in Rs. | No(s) | Total Cost in Rs. |
| --- | --- | --- | --- |
| Remuneration for specialists conducting teleconsultation | 1000 | 12 district hospitals x 1 day/week for 52 weeks | 6,24,000 |
| G.Total |  |  | 6,24,000 |

(Rupees Six Lakhs Twenty-Four Thousand only)

- Planning & M & E: Under this budget head, Independent monitoring cost for Performance assessment of AAMs is proposed as below: - The entire cascade of monitoring of AAMs from the state, district and block (PHC) nodal officers and independent verification from Medical College is estimated to cost roughly Rs. 5,000 per AAM (average cost).

This cost will include mentoring of 10 AAMs by Medical College.

| Total no. of AAMs | Unit cost in Rs. | Total cost in Rs. |
| --- | --- | --- |
| 289 | 5000 | 14,45,000 |

(Rupees Fourteen Lakhs and Forty-Five Thousand only)

LIST OF AAM

| Sl.N | Name of SC-AAM | District | FY |
| --- | --- | --- | --- |
| 1 | Bawngkawn SC | Aizawl E | Existing |
| 2 | Bazar SC | Aizawl E | Existing |
| 3 | Bethlehem Vengthlang SC | Aizawl E | Existing |
| 4 | Central Jail Veng SC | Aizawl W | Existing |
| 5 | Chaltlang SC | Aizawl E | Existing |
| 6 | Chanmari SC | Aizawl E | Existing |
| 7 | Chanmari W SC | Aizawl E | Existing |
| 8 | Chawnpui SC | Aizawl W | Existing |
| 9 | Chhinga Veng SC | Aizawl E | Existing |
| 10 | Dawrpui Vengthar SC | Aizawl E | Existing |
| 11 | Dinthar SC | Aizawl W | Existing |
| 12 | Durtlang SC | Aizawl E | Existing |
| 13 | Edenthar SC | Aizawl W | Existing |
| 14 | Electric SC | Aizawl E | Existing |
| 15 | Hlimen SC | Aizawl W | Existing |
| 16 | Hmunpui SC | Aizawl W | Existing |
| 17 | Hualngohmun SC | Aizawl W | Existing |
| 18 | Hunthar SC | Aizawl W | Existing |
| 19 | ITI SC | Aizawl E | Existing |
| 20 | Kanan SC | Aizawl W | Existing |
| 21 | Kulikawn SC | Aizawl W | Existing |
| 22 | Lawipu SC | Aizawl W | Existing |
| 23 | Lengpui SC | Aizawl W | Existing |
| 24 | Luangmual SC | Aizawl W | Existing |
| 25 | Maubawk SC | Aizawl W | Existing |
| 26 | Melriat SC | Aizawl W | Existing |
| 27 | Melthum SC | Aizawl W | Existing |
| 28 | Mission Vengthlang SC | Aizawl W | Existing |
| 29 | N Lungleng SC | Aizawl W | Existing |
| 30 | PTC Lungverh SC | Aizawl W | Existing |
| 31 | Ramhlun S SC | Aizawl E | Existing |
| 32 | Ramthar SC | Aizawl E | Existing |
| 33 | Republic SC | Aizawl W | Existing |
| 34 | Salem SC | Aizawl W | Existing |
| 35 | Sihphir SC | Aizawl E | Existing |
| 36 | Tanhril SC | Aizawl W | Existing |
| 37 | Thuampui SC | Aizawl E | Existing |
| 38 | Tlangnuam SC | Aizawl W | Existing |
| 39 | Tuikual SC | Aizawl W | Existing |
| 40 | Tuirial SC | Aizawl E | Existing |
| 41 | Tuivamit SC | Aizawl W | Existing |
| 42 | Upper Republic SC | Aizawl E | Existing |
| 43 | Vaivakawn SC | Aizawl W | Existing |
| 44 | Venghlui SC | Aizawl W | Existing |
| 45 | Zemabawk SC | Aizawl E | Existing |

| Sl.N | Name of SC-AAM | District | FY |
| --- | --- | --- | --- |
| 46 | Zotlang SC | Aizawl W | Existing |
| 47 | Zuangtui SC | Aizawl W | Existing |
| 48 | Lamchhip SC | Aizawl W | Existing |
| 49 | Muallungthu SC | Aizawl W | Existing |
| 50 | Phulpui SC | Aizawl W | Existing |
| 51 | Samlukhai SC | Aizawl W | Existing |
| 52 | Sateek SC | Aizawl W | Existing |
| 53 | Sumsuih SC | Aizawl W | Existing |
| 54 | Tachhip SC | Aizawl W | Existing |
| 55 | E Phaileng SC | Aizawl E | Existing |
| 56 | Kepran SC | Aizawl E | Existing |
| 57 | Khanpui SC | Aizawl E | Existing |
| 58 | Mauchar SC | Aizawl E | Existing |
| 59 | N Serzawl SC | Aizawl E | Existing |
| 60 | New Vervek SC | Aizawl E | Existing |
| 61 | Palsang SC | Aizawl E | Existing |
| 62 | Thingsat SC | Aizawl E | Existing |
| 63 | Tinghmun SC | Aizawl E | Existing |
| 64 | Vaitin SC | Aizawl E | Existing |
| 65 | Zohmun SC | Aizawl E | Existing |
| 66 | Seling SC | Aizawl E | Existing |
| 67 | Thingsulthliah SC | Aizawl E | Existing |
| 68 | Tlungvel SC | Aizawl E | Existing |
| 69 | Bethel SC | Champhai | Existing |
| 70 | Bulfekzawl SC | Champhai | Existing |
| 71 | Champhai Vengthlang SC | Champhai | Existing |
| 72 | Hmunhmeltha SC | Champhai | Existing |
| 73 | Khawbung N | Champhai | Existing |
| 74 | Khuangphah SC | Champhai | Existing |
| 75 | Melbuk | Champhai | Existing |
| 76 | Ngur SC | Champhai | Existing |
| 77 | Tlangsam SC | Champhai | Existing |
| 78 | Vaikhawtlang SC | Champhai | Existing |
| 79 | Vapar | Champhai | Existing |
| 80 | Zokhawthar SC | Champhai | Existing |
| 81 | Zote SC | Champhai | Existing |
| 82 | Dungtlang SC | Champhai | Existing |
| 83 | Khankawn SC | Champhai | Existing |
| 84 | Khuangleng SC | Champhai | Existing |
| 85 | Lianpui SC | Champhai | Existing |
| 86 | Samthang SC | Champhai | Existing |
| 87 | Sazep SC | Champhai | Existing |
| 88 | Vanzau SC | Champhai | Existing |
| 89 | Selam SC | Champhai | Existing |
| 90 | Bualpui H SC | Hnahthial | Existing |

| Sl.N | Name of SC-AAM | District | FY |
| --- | --- | --- | --- |
| 91 | Bualpui V SC | Hnahthial | Existing |
| 92 | Hnahthial SC | Hnahthial | Existing |
| 93 | Leite SC | Hnahthial | Existing |
| 94 | Muallianpui SC | Hnahthial | Existing |
| 95 | Rawpui SC | Hnahthial | Existing |
| 96 | S Chawngtui SC | Hnahthial | Existing |
| 97 | Tarpho SC | Hnahthial | Existing |
| 98 | Thiltlang SC | Hnahthial | Existing |
| 99 | Tuipui D SC | Hnahthial | Existing |
| 100 | Biate SC | Khawzawl | Existing |
| 101 | Chawngtlai SC | Khawzawl | Existing |
| 102 | Chhawrtui SC | Khawzawl | Existing |
| 103 | Dulte SC | Khawzawl | Existing |
| 104 | Lungtan SC | Khawzawl | Existing |
| 105 | Neihdawn SC | Khawzawl | Existing |
| 106 | New Chalrang SC | Khawzawl | Existing |
| 107 | Ngaizawl SC | Khawzawl | Existing |
| 108 | Pawlrang SC | Khawzawl | Existing |
| 109 | Riangtlei SC | Khawzawl | Existing |
| 110 | Saichal SC | Khawzawl | Existing |
| 111 | Tlangpui SC | Khawzawl | Existing |
| 112 | Tualpui SC | Khawzawl | Existing |
| 113 | Tualte SC | Khawzawl | Existing |
| 114 | Vanchengpui SC | Khawzawl | Existing |
| 115 | Vangtlang SC | Khawzawl | Existing |
| 116 | Buhchangphai SC | Kolasib | Existing |
| 117 | Diakkawn SC | Kolasib | Existing |
| 118 | N Chawnpui SC | Kolasib | Existing |
| 119 | New Builum SC | Kolasib | Existing |
| 120 | Pangbalkawn SC | Kolasib | Existing |
| 121 | Phainuam SC | Kolasib | Existing |
| 122 | Phaisen SC | Kolasib | Existing |
| 123 | Saiphai SC | Kolasib | Existing |
| 124 | Saipum SC | Kolasib | Existing |
| 125 | Tuitha Veng SC | Kolasib | Existing |
| 126 | Tumpui SC | Kolasib | Existing |
| 127 | Vairengte SC | Kolasib | Existing |
| 128 | Venglai SC | Kolasib | Existing |
| 129 | Bualpui SC | Kolasib | Existing |
| 130 | Hortoki SC | Kolasib | Existing |
| 131 | N Chaltlang SC | Kolasib | Existing |
| 132 | N Hlimen SC | Kolasib | Existing |
| 133 | Lungmuat SC | Kolasib | Existing |
| 134 | Nisapui SC | Kolasib | Existing |
| 135 | Serkhan SC | Kolasib | Existing |

| Sl.N | Name of SC-AAM | District | FY |
| --- | --- | --- | --- |
| 136 | Zanlawn SC | Kolasib | Existing |
| 137 | Ajasora SC | Lawngtlai | Existing |
| 138 | Chawngte P SC | Lawngtlai | Existing |
| 139 | Devasora SC | Lawngtlai | Existing |
| 140 | Hmunlai SC | Lawngtlai | Existing |
| 141 | Jarulsury SC | Lawngtlai | Existing |
| 142 | Longpuighat SC | Lawngtlai | Existing |
| 143 | Saizawh SC | Lawngtlai | Existing |
| 144 | Sumsilui SC | Lawngtlai | Existing |
| 145 | College Veng SC | Lawngtlai | Existing |
| 146 | Kawlchaw SC | Lawngtlai | Existing |
| 147 | Mampui SC | Lawngtlai | Existing |
| 148 | Thingkah SC | Lawngtlai | Existing |
| 149 | Chamdur P SC | Lawngtlai | Existing |
| 150 | Diltlang SC | Lawngtlai | Existing |
| 151 | M Kawnpui SC | Lawngtlai | Existing |
| 152 | Mautlang SC | Lawngtlai | Existing |
| 153 | Vathuampui SC | Lawngtlai | Existing |
| 154 | Cheural SC | Lawngtlai | Existing |
| 155 | Lungtian SC | Lawngtlai | Existing |
| 156 | Lungzarhtum SC | Lawngtlai | Existing |
| 157 | Pangkhua SC | Lawngtlai | Existing |
| 158 | Rawlbuk | Lawngtlai | Existing |
| 159 | Siachangkawn SC | Lawngtlai | Existing |
| 160 | Vawmbuk SC | Lawngtlai | Existing |
| 161 | Lungrang SC | Lunglei | Existing |
| 162 | Rualalung SC | Lunglei | Existing |
| 163 | Bazar (Lunglei) SC | Lunglei | Existing |
| 164 | Central SC | Lunglei | Existing |
| 165 | Electric (Lunglei) SC | Lunglei | Existing |
| 166 | Farm Veng SC | Lunglei | Existing |
| 167 | Hauruang SC | Lunglei | Existing |
| 168 | Hnahchang SC | Lunglei | Existing |
| 169 | Hrangchalkawn SC | Lunglei | Existing |
| 170 | Lunglawn SC | Lunglei | Existing |
| 171 | Mamte SC | Lunglei | Existing |
| 172 | Mualcheng S SC | Lunglei | Existing |
| 173 | Mualthuam N SC | Lunglei | Existing |
| 174 | Rahsi Veng SC | Lunglei | Existing |
| 175 | Ralvawng SC | Lunglei | Existing |
| 176 | Ramlaitui SC | Lunglei | Existing |
| 177 | Ramthar (Lunglei) SC | Lunglei | Existing |
| 178 | Tawipui N SC | Lunglei | Existing |
| 179 | Thehlep (Belthei) SC | Lunglei | Existing |
| 180 | Thingfal SC | Lunglei | Existing |

| Sl.N | Name of SC-AAM | District | FY |
| --- | --- | --- | --- |
| 181 | Thualthu SC | Lunglei | Existing |
| 182 | Vaisam SC | Lunglei | Existing |
| 183 | Venghlun SC | Lunglei | Existing |
| 184 | Zobawk SC | Lunglei | Existing |
| 185 | Zohnuai SC | Lunglei | Existing |
| 186 | Zotlang (Lunglei) SC | Lunglei | Existing |
| 187 | Chawilung SC | Lunglei | Existing |
| 188 | Diblibagh SC | Lunglei | Existing |
| 189 | Nunsury SC | Lunglei | Existing |
| 190 | Phairuangkai SC | Lunglei | Existing |
| 191 | Puankhai SC | Lunglei | Existing |
| 192 | Putlungasih SC | Lunglei | Existing |
| 193 | Tuisenchhuah SC | Lunglei | Existing |
| 194 | Zawlpui SC | Lunglei | Existing |
| 195 | Zodin SC | Lunglei | Existing |
| 196 | Changpui SC | Lunglei | Existing |
| 197 | Kawlhawk SC | Lunglei | Existing |
| 198 | Khawlek SC | Lunglei | Existing |
| 199 | Laisawral SC | Lunglei | Existing |
| 200 | Lungchem SC | Lunglei | Existing |
| 201 | Old Sachan SC | Lunglei | Existing |
| 202 | Serte SC | Lunglei | Existing |
| 203 | Sertlangpui SC | Lunglei | Existing |
| 204 | Sesawm SC | Lunglei | Existing |
| 205 | Ailawng SC | Mamit | Existing |
| 206 | Darlung West SC | Mamit | Existing |
| 207 | Khawrihnim SC | Mamit | Existing |
| 208 | Rulpuihlim SC | Mamit | Existing |
| 209 | W Lungdar SC | Mamit | Existing |
| 210 | Damparengpui SC | Mamit | Existing |
| 211 | Lallen SC | Mamit | Existing |
| 212 | Parvatui SC | Mamit | Existing |
| 213 | Pukzing SC | Mamit | Existing |
| 214 | Silsuri SC | Mamit | Existing |
| 215 | Tuipuibari SC | Mamit | Existing |
| 216 | Bawrai SC | Mamit | Existing |
| 217 | Bungthuam SC | Mamit | Existing |
| 218 | Chuhvel SC | Mamit | Existing |
| 219 | Damdiai SC | Mamit | Existing |
| 220 | Dampui SC | Mamit | Existing |
| 221 | Darlak SC | Mamit | Existing |
| 222 | Hriphaw SC | Mamit | Existing |
| 223 | Kanhmun SC | Mamit | Existing |
| 224 | Kawrthah SC | Mamit | Existing |
| 225 | Mamit SC | Mamit | Existing |

| Sl.N | Name of SC-AAM | District | FY |
| --- | --- | --- | --- |
| 226 | N Sabual SC | Mamit | Existing |
| 227 | Nalzawl SC | Mamit | Existing |
| 228 | New Eden SC | Mamit | Existing |
| 229 | Rengdil SC | Mamit | Existing |
| 230 | Saikhawthlir SC | Mamit | Existing |
| 231 | Suarhliap SC | Mamit | Existing |
| 232 | Thinghlun SC | Mamit | Existing |
| 233 | Tuidam SC | Mamit | Existing |
| 234 | W Bunghmun SC | Mamit | Existing |
| 235 | Zamuang SC | Mamit | Existing |
| 236 | Maubawk (Saiha) SC | Saiha | Existing |
| 237 | Old Siaha SC | Saiha | Existing |
| 238 | Phalhrang SC | Saiha | Existing |
| 239 | Rawmibawk SC | Saiha | Existing |
| 240 | Saihatlangkawn SC | Saiha | Existing |
| 241 | Theiva SC | Saiha | Existing |
| 242 | Tuipuiferry SC | Saiha | Existing |
| 243 | Tuisumpui SC | Saiha | Existing |
| 244 | Laki SC | Saiha | Existing |
| 245 | Lawngban SC | Saiha | Existing |
| 246 | New Latawh SC | Saiha | Existing |
| 247 | Serkawr SC | Saiha | Existing |
| 248 | Siata SC | Saiha | Existing |
| 249 | Tawngkawlong SC | Saiha | Existing |
| 250 | Tuipang L SC | Saiha | Existing |
| 251 | Tuisih SC | Saiha | Existing |
| 252 | Vahai SC | Saiha | Existing |
| 253 | Zawngling SC | Saiha | Existing |
| 254 | Buhban SC | Saitual | Existing |
| 255 | Daido SC | Saitual | Existing |
| 256 | Kawlbem SC | Saitual | Existing |
| 257 | Khawkawn SC | Saitual | Existing |
| 258 | Khawlian SC | Saitual | Existing |
| 259 | Lamzawl SC | Saitual | Existing |
| 260 | Lenchim SC | Saitual | Existing |
| 261 | Maite SC | Saitual | Existing |
| 262 | N. Khawlek SC | Saitual | Existing |
| 263 | Rulchawm SC | Saitual | Existing |
| 264 | Saitual SC | Saitual | Existing |
| 265 | Sihfa SC | Saitual | Existing |
| 266 | Teikhang SC | Saitual | Existing |
| 267 | Thanglailung SC | Saitual | Existing |
| 268 | Tualbung SC | Saitual | Existing |
| 269 | Vanbawng SC | Saitual | Existing |
| 270 | Buangpui SC | Serchhip | Existing |

| Sl.N | Name of SC-AAM | District | FY |
| --- | --- | --- | --- |
| 271 | Bungtlang SC | Serchhip | Existing |
| 272 | Chhiahtlang SC | Serchhip | Existing |
| 273 | Hmuntha SC | Serchhip | Existing |
| 274 | Hriangtlang SC | Serchhip | Existing |
| 275 | Hualtu SC | Serchhip | Existing |
| 276 | Kanghmun S SC | Serchhip | Existing |
| 277 | Khawbel SC | Serchhip | Existing |
| 278 | Leng SC | Serchhip | Existing |
| 279 | Lungchhuan SC | Serchhip | Existing |
| 280 | Lungkawlh SC | Serchhip | Existing |
| 281 | Lungpho SC | Serchhip | Existing |
| 282 | Mualcheng SC | Serchhip | Existing |
| 283 | Rullam SC | Serchhip | Existing |
| 284 | Sailulak SC | Serchhip | Existing |
| 285 | Serchhip SC | Serchhip | Existing |
| 286 | Sialhau SC | Serchhip | Existing |
| 287 | Thentlang SC | Serchhip | Existing |
| 288 | Thenzawl SC | Serchhip | Existing |
| 289 | Thinglian SC | Serchhip | Existing |
| 290 | Zote S SC | Serchhip | Existing |
| 291 | Dinthar SC | Khawzawl | Proposed for 26-27 |
| 292 | Hermon SC | Khawzawl | Proposed for 26-27 |
| 293 | Kawnzar SC | Khawzawl | Proposed for 26-27 |
| 294 | Vengthar SC | Khawzawl | Proposed for 26-27 |
| 295 | Zuchhip SC | Khawzawl | Proposed for 26-27 |
| 296 | Zaingen SC | Khawzawl | Proposed for 26-27 |
| 297 | Arro SC | Khawzawl | Proposed for 26-27 |
| 298 | Lungvar SC | Khawzawl | Proposed for 26-27 |
| 299 | Vengchung Khawhai SC | Khawzawl | Proposed for 26-27 |
| 300 | Parkkawn SC | Kolasib | Proposed for 26-27 |
| 301 | Hmar Veng | Kolasib | Proposed for 26-27 |
| 302 | Gulsil | Lawngtlai | Proposed for 26-27 |
| 303 | Sethlun | Lunglei | Proposed for 26-27 |
| 304 | Thangpui | Lunglei | Proposed for 26-27 |
| 305 | Upper Lungrang | Lunglei | Proposed for 26-27 |
| 306 | Lalnutui | Lunglei | Proposed for 26-27 |
| 307 | Buknuam | Lunglei | Proposed for 26-27 |
| 308 | Mautlang | Lunglei | Proposed for 26-27 |
| 309 | Sailen | Lunglei | Proposed for 26-27 |
| 310 | Vairawkai | Lunglei | Proposed for 26-27 |
| 311 | Hmunthar | Lunglei | Proposed for 26-27 |
| 312 | Tawipui North II | Lunglei | Proposed for 26-27 |
| 313 | South Mualcheng | Lunglei | Proposed for 26-27 |

LISTS OF PHC-AAM

| Sl.N | Name of PHC-AAM | Type | District_Name |
| --- | --- | --- | --- |
| 1 | Darlawn PHC | AAM-PHC | Aizawl E |
| 2 | Khawruhlian PHC | AAM-PHC | Aizawl E |
| 3 | Ratu PHC | AAM-PHC | Aizawl E |
| 4 | Sairang PHC | AAM-PHC | Aizawl W |
| 5 | Aibawk PHC | AAM-PHC | Aizawl W |
| 6 | Sialsuk PHC | AAM-PHC | Aizawl W |
| 7 | Hnahlan PHC | AAM-PHC | Champhai |
| 8 | Bungzung PHC | AAM-PHC | Champhai |
| 9 | Farkawn PHC | AAM-PHC | Champhai |
| 10 | Khawbung PHC | AAM-PHC | Champhai |
| 11 | Sesih PHC | AAM-PHC | Champhai |
| 12 | Cherhlun PHC | AAM-PHC | Hnahthial |
| 13 | Chhipphir PHC | AAM-PHC | Hnahthial |
| 14 | Pangzawl PHC | AAM-PHC | Hnahthial |
| 15 | S Vanlaiphai PHC | AAM-PHC | Hnahthial |
| 16 | Thingsai PHC | AAM-PHC | Hnahthial |
| 17 | Kawlkulh PHC | AAM-PHC | Khawzawl |
| 18 | Khawhai PHC | AAM-PHC | Khawzawl |
| 19 | Rabung PHC | AAM-PHC | Khawzawl |
| 20 | Sialhawk PHC | AAM-PHC | Khawzawl |
| 21 | Bairabi PHC | AAM-PHC | Kolasib |
| 22 | Bilkhawthlir PHC | AAM-PHC | Kolasib |
| 23 | Bukpui PHC | AAM-PHC | Kolasib |
| 24 | Kawnpui PHC | AAM-PHC | Kolasib |
| 25 | Lungdai PHC | AAM-PHC | Kolasib |
| 26 | Borapansury PHC | AAM-PHC | Lawngtlai |
| 27 | Longpuighat PHC | AAM-PHC | Lawngtlai |
| 28 | Bungtlang S PHC | AAM-PHC | Lawngtlai |
| 29 | Bualpui NG PHC | AAM-PHC | Lawngtlai |
| 30 | S Lungpher PHC | AAM-PHC | Lawngtlai |
| 31 | Sangau PHC | AAM-PHC | Lawngtlai |
| 32 | Haulawng PHC | AAM-PHC | Lunglei |
| 33 | Tawipui S PHC | AAM-PHC | Lunglei |
| 34 | Lungsen PHC | AAM-PHC | Lunglei |
| 35 | Buarpui PHC | AAM-PHC | Lunglei |
| 36 | Bunghmun S PHC | AAM-PHC | Lunglei |
| 37 | Kanghmun PHC | AAM-PHC | Mamit |
| 38 | Rawpuichhip PHC | AAM-PHC | Mamit |
| 39 | Reiek PHC | AAM-PHC | Mamit |
| 40 | Marpara PHC | AAM-PHC | Mamit |
| 41 | Phuldungsei PHC | AAM-PHC | Mamit |
| 42 | West Phaileng PHC | AAM-PHC | Mamit |
| 43 | Kawrtethawveng PHC | AAM-PHC | Mamit |
| 44 | Zawlnuam PHC | AAM-PHC | Mamit |
| 45 | Chakhang PHC | AAM-PHC | Saiha |

| Sl.N | Name of PHC-AAM | Type | District_Name |
| --- | --- | --- | --- |
| 46 | Chhuarlung PHC | AAM-PHC | Saiha |
| 47 | Phura PHC | AAM-PHC | Saiha |
| 48 | Tuipang PHC | AAM-PHC | Saiha |
| 49 | Mimbung PHC | AAM-PHC | Saitual |
| 50 | NE Khawdungsei PHC | AAM-PHC | Saitual |
| 51 | Phuaibuang PHC | AAM-PHC | Saitual |
| 52 | Phullen PHC | AAM-PHC | Saitual |
| 53 | Suangpuilawn PHC | AAM-PHC | Saitual |
| 54 | Chhingchhip PHC | AAM-PHC | Serchhip |
| 55 | East Lungdar PHC | AAM-PHC | Serchhip |
| 56 | Khawlailung PHC | AAM-PHC | Serchhip |
| 57 | N Vanlaiphai PHC | AAM-PHC | Serchhip |
| 58 | Ngentiang PHC | AAM-PHC | Serchhip |

| HSS 1 : LIST OF DIAGNOSTICS FOR AAM 289 SC & 58 PHC |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| FMR | Component |  | No. of Units | Unit Cost (in lakhs) | Budget Proposed (in lakhs) |
| 150 | Procurement of Diagnostics |  | 347 | 0.3 | 104.1 |
|  | ITEMS | UNIT RATE/ per test kit (Rs) | QUANTITY | AMOUNT (Rs) | REMARKS |
| 1 | Hb Test strips | 31.86 | 80,000 | 25,48,800 |  |
| 2 | Multiparameter urine strip | 4.5 | 29,000 | 1,30,500 |  |
| 3 | Glucostrips | 14.6 | 1,10,000 | 16,06,000 |  |
| 4 | Glucostrips | 10.1 | 1,10,000 | 11,11,000 |  |
| 5 | Lancets | 0.45 | 1,00,000 | 45,000 |  |
| 6 | Dual test kit for HIV & Syphillis | 21 | 29000 | 6,09,000 |  |
| 7 | RDK for Dengue | 30 | 29000 | 8,70,000 |  |
| 8 | Hepatitis B rapid test kit | 7.95 | 29000 | 2,30,550 |  |
| 9 | Hepatitis C rapid test kit | 7.95 | 5800 | 46,110 |  |
| 10 | Scrub typhus test kit | 49 | 29000 | 14,21,000 |  |
| 11 | Water testing kit for H2S (bacteria) | 22.8 | 7250 | 1,65,300 |  |
| 12 | Water testing kit for chlorination | 170 | 290 | 49,300 |  |
| 13 | Reagent- Billirubin (Total &Direct) | 655 | 58 | 37,990 |  |
| 14 | Reagent- Albumin | 375 | 58 | 21,750 |  |
| 15 | Reagent- Alkaline Phosphatase | 310 | 58 | 17,980 |  |
| 16 | Reagent- SGOT | 845 | 58 | 49,010 |  |
| 17 | Reagent- SGPT | 925 | 58 | 53,650 |  |
| 18 | Reagent- Total Protein | 330 | 58 | 19,140 |  |
| 19 | Reagent- Triglycerides | 1610 | 58 | 93,380 |  |
| 20 | Reagent- Blood Sugar | 380 | 58 | 22,040 |  |
| 21 | Reagent- Cholesterol | 835 | 58 | 48,430 |  |
| 22 | Reagent- HDL | 560 | 58 | 32,480 |  |
| 23 | Reagent- Urea | 820 | 58 | 47,560 |  |
| 24 | Reagent- Creatinine | 745 | 58 | 43,210 |  |
| 25 | Reagent- Uric Acid | 1060 | 58 | 61,480 |  |
| 26 | Reagent- ASO with Calibrator | 2595 | 58 | 1,50,510 |  |
| 27 | Reagent- Biochemistry Control Normal | 695 | 58 | 40,310 |  |
| 28 | Reagent- Biochemistry Control | 550 | 58 | 31,900 |  |
| 29 | Reagent- CRP with calibrator | 2395 | 58 | 1,38,910 |  |
| 30 | Reagent- RF with Calibrator | 1520 | 58 | 88,160 |  |
| 31 | Reagent- Flow Cell Washing Soln | 255 | 58 | 14,790 |  |
| 32 | 3 Part haematology Analyzer Liquid | 10480 | 58 | 6,07,840 |  |
|  | GRAND TOTAL |  |  | 1,04,53,080 |  |

| HSS 1: LIST OF EQUIPMENT FOR 23 NEW AAM SC |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| FMR | Component |  | No. of Units | Unit Cost (in lakhs) | Budget Proposed (in lakhs) |
| 150 | Procurement of Equipment |  | 23 | 0.5 | 11.5 |
|  | ITEMS | UNIT RATE/ per test kit (Rs) | QUANTITY | AMOUNT (Rs) | REMARKS |
| 1 | Office Table | 10000 | 23 | 2,30,000 |  |
| 2 | Revolving Chair | 5000 | 23 | 1,15,000 |  |
| 3 | Almirah | 15000 | 23 | 3,45,000 |  |
| 4 | Partition Screen | 3000 | 23 | 69,000 |  |
| 5 | 3 Plastic Chairs | 1500 | 23 | 34,500 |  |
| 6 | Refrigerator | 15000 | 23 | 3,45,000 |  |
|  | GRAND TOTAL | 49500 |  | 11,38,500 |  |

FMR CODE: HSS(U).1 Comprehensive Primary Healthcare (CPHC)

Sl.No . 127. Development and Operations of AAMs-Urban

- Community based service delivery by AAMs.

We aim to increase our delivery of service to the communities through Health & Wellness Centres (AAMs). Towards this we are proposing for the following activities.

- Others including operating costs (OOC): - The amount proposed is for recurring component only. Rs. 5,000 per facility for operating costs like internet connectivity, monthly internet bills, training of staff on IT software etc.

| Component | Total no. of UPHCs | Unit cost in Rs. | Total cost in Rs. |
| --- | --- | --- | --- |
| Recurring - software, training, etc. | 10 | 5,000 | 50,000 |
| G.Total |  |  | 50,000 |

(Rupees Fifty Thousand only)

- Procurement of Drugs: - Provision of drugs is an important component of health services delivered at UPHC-AAMs. The following amount is proposed for procurement and for making drugs available at 9 UPHCs.

| S.N | Name of District | Total no. of AAMs | Unit cost in Rs. | Total cost in Rs. |
| --- | --- | --- | --- | --- |
| 1 | Aizawl East | 3 | 7,00,000 | 21,00,000 |
| 2 | Aizawl West | 3 | 7,00,000 | 21,00,000 |
| 3 | Lunglei | 2 | 7,00,000 | 14,00,000 |
| 4 | Champhai | 1 | 7,00,000 | 7,00,000 |
| 5 | Kolasib | 1 | 7,00,000 | 7,00,000 |
| Total |  | 10 |  | 70,00,000 |

(Rupees Seventy Lakhs only)

- Equipment (Including Furniture, Excluding Computers): The amount proposed is for equipping 3 UPHCs @ Rs. 50,000 per AAMs to carry out tests and activities as per packages rolled-out.

| Total no. of AAMs | Unit cost in Rs. | Total cost in Rs. |
| --- | --- | --- |
| 7 | 50,000 | 3,50,000 |

(Rupees Three Lakhs Fifty Thousand only)

- Capacity Building including Training: This budget head has been split into the different components as below: -

- Refresher Training of MO/SN for UPHC-AAMs on Expanded Packages Services: Refresher Training of MO and SN on expanded range of services is crucial to enhance their capacity and skills to carry out the different services as desired. We proposed Rs.2,50,000 as below details:

| Particulars | No of days | Rate/unit | Unit | Total |
| --- | --- | --- | --- | --- |
| Hall Rent | 5 | 4000 |  | 20,000 |
| Resource Fee | 5 | 2000 | 4 | 40,000 |
| Refreshment | 5 | 200 | 30 | 30,000 |
| TADA & Accommodation | 5 | 1000 | 30 | 1,50,000 |
| Training Aid |  | 300 | 30 | 9,000 |
| Contingency |  |  |  | 1,000 |
| G.Total |  |  |  | 2,50,000 |

(Rupees Two Lakhs, Fifty Thousand only)

- Planning & M & E: Under this budget head, Independent monitoring cost for Performance assessment of AAMs is proposed. Monitoring of performance of UPHC-AAMs along the various conditions of operationalization through State programme management team for CPHC and other external agencies is critical.

In the table below, we have proposed for the following components:

| Total no. of UPHCs | Unit cost in Rs. | Total cost in Rs. |
| --- | --- | --- |
| 10 | 5,000 | 50,000 |

(Rupees Fifty Thousand only)

- IEC & Printing: Printing fund is to be utilized for printing of multiple forms, registers as required by AAMs for their smooth functioning. Printing of patient health cards/booklets, registers, forms is estimated to cost Rs. 80,000 per UPHC.

| Total no. of UPHCs | Unit cost in Rs. | Total cost in Rs. |
| --- | --- | --- |
| 10 | 10,000 | 1,00,000 |

(Rupees One Lakh only)

Sl.No . 128. Wellness Activities at AAMs-Urban

- Wellness Sessions: Under Wellness sessions, we have proposed for the following activities under UPHCs. To achieve monthly target of wellness sessions for AAM and to promote healthy lifestyle for prevention and promotion of health, we have proposed budget for organizing wellness session as below:

| Total no. of UPHCs | Total number of sessions held | Unit cost | Total cost |
| --- | --- | --- | --- |
| 10 | 10 sessions per month for 12 months | 250 | 3,00,000 |

(Rupees Three Lakhs only)

Sl.No 129: Teleconsultation at AAM- Urban  eSanjeevani AAM is being implemented in almost all the AAMs. Efforts are being made to operationalize telemedicine services. Teleconsultation sessions will be conducted by in-house specialists at DH/MCH with MO’s at UPHCs. Sessions will be conducted 1 day a week for 52 weeks per year. We have proposed a remuneration of Rs.1000 for 1 day a week for 52 weeks and Rs. 100 per call for a ceiling of 12 consultations for MO when SC-AAM consults Medical Officer at UPHC.

| Component | Unit Cost in Rs. | Frequency | Total Cost in Rs. |
| --- | --- | --- | --- |
| Remuneration for specialists conducting teleconsultation | 1000 | 12 DHs x 52 weeks x 1 day/week) days a week | 6,24,000 |

(Rupees Four Lakhs Twenty-Four thousand only)

LISTS OF UPHC-AAM

| Sl.N | Name of UPHC-AAM | Type | District |
| --- | --- | --- | --- |
| 1 | Chawlhhmun UPHC | AAM-UPHC | Aizawl W |
| 2 | Hlimen UPHC | AAM-UPHC | Aizawl W |
| 3 | Lawipu UPHC | AAM-UPHC | Aizawl W |
| 4 | ITI UPHC | AAM-UPHC | Aizawl E |
| 5 | Sihphir UPHC | AAM-UPHC | Aizawl E |
| 6 | Zemabawk UPHC | AAM-UPHC | Aizawl E |
| 7 | Champhai UPHC | AAM-UPHC | Champhai |
| 8 | Hrangchalkawn UPHC | AAM-UPHC | Lunglei |
| 9 | Sazaikawn UPHC | AAM-UPHC | Lunglei |
| 10 | Kolasib UPHC | Proposed for 26-27 | Kolasib |

| LIST OF MEDICINE UNDER NATIONAL URBAN HEALTH MISSION |  |  |  |
| --- | --- | --- | --- |
| Sl no | Generic name | Strength | Amount |
| TABLETS |  |  |  |
| 1 | Tab. Calcium & Vitamin D3 | 500 mg | 100000 |
| 2 | Tab.Metformin | 500mg | 100000 |
| 3 | Tab.Telmisartan | 40 | 100000 |
| 4 | Tab. Levoceterizine & Montelukast | 5mg+10mg | 100000 |
| 5 | Tab. Ceterizine | 10mg | 100000 |
| 6 | Tab.Paracetamol | 500 | 100000 |
| 7 | Tab. Paracetamol, Acceclofenac & Serratiopeptidase | 325mg+100mg+250mg | 100000 |
| 8 | Diclofenec + Paracetamol | 50mg +325mg | 100000 |
| 9 | Tab. Pantoprazole | 40 mg | 100000 |
| 10 | Tab. Rabeprazole | 20 mg | 100000 |
| 11 | Tab.Amlodipine | 5 | 100000 |
| 12 | Tab. Ascorbic Acid | 500mg | 100000 |
| 13 | Tab.Cefixime | 200 | 80000 |
| 14 | Tab.Cefixime | 100 | 80000 |
| 15 | Tab.Nitrofurantoin | 100mg | 80000 |
| 16 | Tab.Amox plus Clavulanate | 625 | 80000 |
| 17 | Tab.Amox plus Clavulanate | 375 | 80000 |
| 18 | Tab Ferrous Ascorbate & Folic Acid Tablets | 5mg | 80000 |
| 19 | Tab. Glimepiride | 2mg | 80000 |
| 20 | Tab. Fluconazole | 150mg | 80000 |
| 21 | Tab. Ondansetron | 4mg | 80000 |
| 22 | Tab.Azithromycin | 250 | 80000 |
| 23 | Tab.Azithromycin | 500 | 80000 |
| 24 | Tab.Metronidazole | 400 | 80000 |
| 25 | Tab. Ciprofloxacin | 500mg | 80000 |
| 26 | Tab. Acyclovir | 400mg | 80000 |
| 27 | Tab Zinc | 20mg | 80000 |
| 28 | Tab. Clotrimazole Pessary | 100 | 80000 |
| 29 | Tab.Glimepiride plus metformin | 2 + 500 | 80000 |
| 30 | Tab.Glimepiride plus metformin | 1 + 500 | 80000 |
| 31 | Tab. Albendazole | 400 mg | 80000 |
| 32 | Tab. Cotrimoxazole + Sulphamethoxazol + Trimethoprim | 800mg + 160mg | 60000 |
| 33 | Tab.Ofloxacin plus Ornidazole |  | 60000 |
| 34 | Tab. Acyclovir | 800mg | 60000 |
| 35 | Tab. Vertin |  | 60000 |
| CAPSULES |  |  |  |
| 1 | Cap.B Complex |  | 100000 |
| 2 | Cap.Pre & Pro biotic |  | 100000 |
| 3 | Cap Pantoprazole & Domperidone | 40mg & 30mg | 100000 |
| 4 | Cap.Omeprazole plus domperidone | 20mg &10mg | 100000 |
| 5 | Cap Rabeprazole & Domperidone | 20mg & 30mg | 100000 |
| 6 | Cap Amoxicillin | 500mg | 100000 |
| 7 | Cap. Doxycycline + Lactic Acid Bacillus | 100mg | 100000 |
| 8 | Cap Methycobalamine & Pregabaline | 750mg & 75mg | 75000 |
| 9 | Cap Rabeprazole & Domperidone | 40mg & 30mg | 75000 |
| 10 | Cap Multivitamin |  | 750000 |
| SYRUP/ SUSPENSION |  |  |  |
| 1 | Susp.Antacid | 200ml | 10000 |
| 2 | Syrup .B.Complex | 200ml | 10000 |
| 3 | Susp.Calcium | 250 | 10000 |
| 4 | Susp. Paracetamol | 250 mg /5 ml | 10000 |
| 5 | Syrup.Levoceterizine plus Pot Montelucast | 2.5mg &4mg | 10000 |
| 6 | Syrup.Multivitamins |  | 10000 |
| 7 | Susp.Ceterizine | 5mg | 8000 |
| 8 | Syrup . B complex & cyproheptadine | 200 ml | 8000 |
| 9 | Oral Sol.Cefixime | 100mg /5ml | 8000 |
| 10 | Syrup . Ambroxol , ceterizine, Guaphenesine & phenylephrine | 100 ml | 8000 |
| 11 | Oral Sol.Ondansetron | 2 | 8000 |
| 12 | Syrup. Dextrometorphan HCl & Chlorpheniramine Maleate, Phenylephrine |  | 8000 |
| 13 | Syrup .Disodium Citrate |  | 8000 |
| 14 | Syrup. Digestive Enzyme |  | 8000 |
| 15 | Oral Susp. Azithromycin | 200 | 8000 |
| 16 | Oral Sol.Ondansetron | 4mg/ml | 8000 |
| 17 | Oral Sol. Amoxycillin plus Pot Clavulanate | 400 | 8000 |
| 18 | Oral. Sol.Oflox plus Ornidzole | 50 + 125 | 8000 |
| 19 | Oral Sol.Albendazole | 200 | 8000 |
| 20 | Susp. Sucralfate |  | 8000 |
| 21 | SyrupMetronidazole | 100 mg/5ml | 8000 |
| 22 | Susp, Pre probiotics | 30ml | 8000 |
| OINTMENT / CREAM |  |  |  |
| 1 | Diclofenac ointment |  | 8000 |
| 2 | Mupirocin ointment | 2% | 8000 |
| 3 | Povidone iodine ointments | 10% | 8000 |
| 4 | Lignocaine jelly |  | 8000 |
| 5 | Permethrin | 5% | 8000 |
| 6 | Clotrimazole |  | 8000 |
| 7 | Silver Sulphadiazine | 1% | 8000 |
| 8 | Diclofenac gel | 30mg | 8000 |
| 9 | Permethrine cream | 5% | 8000 |
| 10 | Lygnocaine gel | 2% | 8000 |
| 11 | Povidone Iodine | 10% | 8000 |
| 12 | Silver Sulphadiazine Oint. |  | 8000 |
| 13 | Clotrimazole+Beclomethasone | 1%+0.025% | 8000 |
| 14 | Ciprofloxacin Eye drop |  | 8000 |
| 15 | Methyl Cellulose Eye Drop |  | 8000 |
| 16 | Calamine Lotion |  | 8000 |
| 17 | Mometasone & Fusidic acid | 0.1% + 2% | 8000 |
| 18 | Neomycin& Polymyxin B Sulfates&Bacitracin Zinc |  | 8000 |
|  | INJECTABLES |  |  |
| 1 | Frusemide | 10mg | 8000 |
| 2 | Pantoprazole | 40mg | 8000 |
| 3 | Diclofenac | 25mg | 8000 |
| 4 | Ondansetron | 4mg | 8000 |
| 5 | Ondansetron | 8mg/4ml | 8000 |
| 6 | DNS | 500ml | 8000 |
| 7 | RL | 500ml | 8000 |
| 8 | Ceftriazone | 500mg | 8000 |
| 9 | Ceftriazone | 1000mg | 8000 |
| 10 | Ondansetron | 2mg/2ml | 8000 |
| 11 | Tetanus toxoid | NA | 8000 |
| 12 | NS | 500ml | 8000 |
| 13 | Pheniramine maleate | 22.75mg/ml | 8000 |
| 14 | Normal Saline | 0.9% w/v | 8000 |
| 15 | Dextrose | 500ml(5%) | 8000 |
| 16 | D5 | NA | 8000 |
| 17 | Lignocaine | 2% | 5000 |
| 18 | Hydrocortisone | 100mg | 5000 |
| 19 | Ceftriaxone + Salbactum | 1000 mg + 500 mg | 5000 |
|  | CONSUMABLES |  |  |
| 1 | Syringe | 5ml | 8000 |
| 2 | Syringe | 10ml | 8000 |
| 3 | Syringe | 2ml | 8000 |
| 4 | Unsterile gloves | Medium | 8000 |
| 5 | Unsterile gloves | large | 8000 |
| 6 | Sterile Gloves | 7 | 8000 |
| 7 | Sterile Gloves | 6.5 | 8000 |
| 8 | IV Set |  | 8000 |
| 9 | Bandage | 5cm | 8000 |
| 10 | Cannulla(Intracath) | 22G | 8000 |
| 11 | Cannulla(Intracath) | 24G | 8000 |
| 12 | Cotton wool | 500 gm | 8000 |
| 13 | Rolled bandage | 5 cm | 8000 |
| 14 | Bandage | 7.5cm | 8000 |
| 15 | Plaster | 7.5cm | 5000 |
| 16 | Plaster | 5 cm | 5000 |
| 17 | Sodium Hypochloride | 10% | 5000 |
| 18 | Gluteraldehyde Solution | 2% | 5000 |
| 19 | Gauze than |  | 5000 |
| 20 | Insulin syringes | 1 ml | 5000 |
| 21 | Accucheck instant strip | Instant strip | 100000 |
| 22 | Surgical suture (mersilk) Ethicon cutting (Non-absorbable) | 3-0 | 5000 |
| 23 | Surgical suture (mersilk) Ethicon cutting (Non-absorbable) | 4-0 | 5000 |
| 24 | Surgical Suture ( mersilk) Ethicon cutting (Non-absorbable) | 2-0 | 5000 |
| 25 | Crepe Bandage |  | 5000 |
| 26 | Catgut (Ethicon Absorbable) | 2-0 | 5000 |
| 27 | Catgut (Ethicon Absorbable) | 0 | 5000 |
| 28 | Parafin gauze |  | 5000 |

Estimate for procurement of equipment @Rs.35,000/UPHCs for 10 UPHCs

| Particulars | Total Number of AAMs | Unit Cost in Rs. | Total |
| --- | --- | --- | --- |
| Reagents and consumables for diagnostic | 10 | 35,000 | 3,50,000 |
| G Total |  |  | 3,50,000 |