PROGRAMME IMPLEMENTATION PLAN FOR DRUGS AND VACCINE DISTRIBUTION MANAGEMENT SYSTEM (DVDMS) UNDER NHM, MIZORAM 26-27

The Drugs and Vaccine Distribution Management System (DVDMS) was implemented in Mizoram in 2020, initially covering facilities up to the Primary Health Centre (PHC) level. Over the years, the State has made commendable progress in expanding the scope of implementation, which now extends up to the Ayushman Arogya Mandir–Sub Health Centre (AAM–SHC) level, achieving 100% facility coverage across the State.

While the coverage of DVDMS is comprehensive, there remains scope for improvement in the effective utilization of certain modules within the software. To ensure optimal use and strengthen system functionality, the State has been coordinating closely with C-DAC Silchar for ongoing technical support and system maintenance.

The initial phase of DVDMS implementation began in 2020 with training programmes for Medical Officers, Pharmacists, and other supporting staff. However, with the recent expansion of the system to the Sub-Centre level, the application is now being managed primarily by Health and Wellness Officers (HWOs/CHOs) who have not yet received formal training in its use. This has posed challenges in maintaining uniformity and efficiency in data entry and reporting across facilities.

Additionally, healthcare personnel who were trained during the initial implementation phase now require refresher training, as several updates and modifications have been introduced in the software since then.

In view of the above, the State proposes the following:

- Provision of funds for continuation of the technical support services currently being rendered by C-DAC Silchar; and

- Allocation of funds for conducting comprehensive training and refresher training for all stakeholders at various facility levels to ensure consistent and effective utilization of DVDMS. The total amount proposed is ₹. 66,21,755.10.

1.PROPOSAL FOR SERVICE EXTENSION OF DVDMS, MIZORAM 2026-27

| Components | Proposed for 2026-27 (in lakhs with 10% increment) |
| --- | --- |
| B.1 Application Software Support | ₹ 11,80000.95 |
| D.2 Project Management Support (CDAC IT Cell charges) | ₹ 301124.45 |
| E.1 Data Centre Hosting | ₹ 13,58365.25 |
| E.2 Application Administrator | ₹ 612184.45 |
| Total Amount | ₹ 3451675.10 |
| GST@18% | ₹ 621301.52 |
| Sub Total | ₹ 4072976.62 |
| Salary for state IT Cell (with 5% increment) | ₹ 995513.40 |
| Grand Total | ₹ 5068490 |

2. PROPOSAL FOR TRAINING

A. Resource fee/DA for trainers

| DA @ Rs.500/day for 2 persons for 32 days | DA SNO @ Rs. 1000/day for 32 days | Honorarium for resource person @ Rs. 1000/day for 3 persons for 12 days | Lodging @ Rs.2000/night for 20 nights for 3 persons | TOTAL in Rs |
| --- | --- | --- | --- | --- |
| 32000 | 32000 | 36000 | 120000 | 220000 |

B. Vehicle Hiring for Trainers

| District | Distance from Capital in km | Rate/km @ Rs.35 (To & Fro) | Night halt @ Rs 1200/night for 2 nights | TOTAL |
| --- | --- | --- | --- | --- |
| Aizawl East |  |  |  | 4000 |
| Aizawl West |  |  |  | 4000 |
| Champhai | 154 | 10780 | 2400 | 13180 |
| Hnahthial | 153 | 10710 | 2400 | 13110 |
| Khawzawl | 128 | 8960 | 2400 | 11360 |
| Kolasib | 83 | 5810 | 2400 | 8210 |
| Lawngtlai | 242 | 16940 | 2400 | 19340 |
| Lunglei | 165 | 11550 | 2400 | 13950 |
| Mamit | 90 | 6300 | 2400 | 8700 |
| Saitual | 80 | 5600 | 2400 | 8000 |
| Siaha | 320 | 22400 | 2400 | 24800 |
| Serchhip | 105 | 7350 | 2400 | 9750 |
| TOTAL |  |  |  | Rs. 138400 |

C. TA/DA for trainees

| Districts | No of facilities (upto PHC+SC) | No. of trainees |  |  | DA @ Rs.500 for Pharmacist/HWO and Rs. 1000 for MO |  |  | TA as per public transport fare for pharmacist &HWO and actual distance from facility to district HQ) | Refreshment @ Rs.200/head | TOTAL |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | DVDMS point person+MO | HWO | Total trainees | Pharmacist and HWO | MO | Sub total | MO+Pharmacist +HWO |  |  |  |
| Aizawl East | 10+41 | 20 | 41 | 61 | 25500 | 10000 | 35500 | 96000 | 12200 | 143700 |  |
| Aizawl West | 10+38 | 20 | 38 | 58 | 24000 | 10000 | 34000 | 41000 | 11600 | 86600 |  |
| Champhai | 9+27 | 18 | 27 | 45 | 18000 | 9000 | 27000 | 54000 | 9000 | 90000 |  |
| Hnahthial | 6+10 | 12 | 10 | 22 | 8000 | 6000 | 14000 | 24000 | 4400 | 42400 |  |
| Khawzawl | 6+17 | 12 | 17 | 29 | 11500 | 6000 | 17500 | 28500 | 5800 | 51800 |  |
| Kolasib | 9+22 | 18 | 22 | 40 | 15500 | 9000 | 24500 | 37000 | 8000 | 69500 |  |
| Lawngtlai | 7+31 | 14 | 31 | 45 | 19000 | 7000 | 26000 | 95000 | 9000 | 130000 |  |
| Lunglei | 10+52 | 20 | 52 | 72 | 31000 | 10000 | 41000 | 131000 | 14400 | 186400 |  |
| Mamit | 11+31 | 22 | 31 | 53 | 21000 | 11000 | 32000 | 81000 | 10600 | 123600 |  |
| Saitual | 6+18 | 12 | 18 | 30 | 12000 | 6000 | 18000 | 72000 | 6000 | 96000 |  |
| Siaha | 6+20 | 12 | 20 | 32 | 13000 | 6000 | 19000 | 46000 | 6400 | 71400 |  |
| Serchhip | 8+23 | 16 | 23 | 39 | 15500 | 8000 | 23500 | 39000 | 7800 | 70300 |  |
| TOTAL | 428 | 196 | 330 | 526 | 214000 | 98000 | 312000 | 613500 | 105200 | 1167700 |  |

Summarized proposal for Training

| S/No. | PROPOSAL | AMOUNT in Rs |
| --- | --- | --- |
| 1 | TA/DA for trainees | 1167700 |
| 2 | Resource fee/DA for Trainers | 220000 |
| 3 | Vehicle Hiring for Trainers | 138400 |
| 4 | Contingency-stationeries etc | 52600 |
| TOTAL |  | ₹. 1441700 |

SUMMARY

| S/No | PARTICULARS | AMOUNT in lakhs |
| --- | --- | --- |
| 1 | Service extension of DVDMS, Mizoram 2026-27 | ₹. 5068490 |
| 2 | Refresher training of stakeholders | ₹. 1441700 |
|  | TOTAL | ₹. 6510190 |

District wise fund break up

| District | Amount in Rs |
| --- | --- |
| Aizawl East | 272433 |
| Aizawl West | 224755 |
| Champhai | 97742 |
| Kolasib | 104949 |
| Lawngtlai | 166525 |
| Lunglei | 160380 |
| Mamit | 115364 |
| Saiha | 74382 |
| Serchhip | 79139 |
| Saitual | 57950 |
| Hnahthial | 36009 |
| Khawzawl | 52072 |
| TOTAL | Rs.1441700 |