INTEGRATED TRAINING OF PRIMARY HEALTHCARE TEAM AT

AYUSHMAN AAROGYA MANDIR (AAM)

UNDER NATIONAL HEALTH MISSION, MIZORAM

PROPOSAL UNDER PROGRAMME IMPLEMENTATION PLAN (PIP) – 2026-27

- The training plan for integrated training of primary healthcare team at Ayushman Aarogya Mandir (AAM) under National Health Mission (NHM), Mizoram is prepared as per the Guidance Document and Roll Out Strategy conveyed vide D.O.No.NHSRC/24-25/CP-CPHC/TrainingInstitutes/0520, Dt. 02.04.2026 (email from healthmission@nic.in, Dt. 07.04.2026)

- Level of trainers:

Only state level trainers are proposed for Mizoram at present. A total of 25 trainers is proposed from the 3 (three) state level training institutions identified. This is because there are no district level skills laboratories and relatively less number of trainees.

- Training Strategy for FY2026-27

  - National Orientation of Master Trainers by MoHFW/NHSRC – Q1

  - Training of state trainers at Regional Training Institutes – Q2

  - Training of AAM team – Medical Officer (MO), Staff Nurse (SN), Community Health Officer (CHO), Multipurpose workers (MPW M&F) & ASHAs at Skills lab at state level – Q3 & Q4

- Target number of trainees under Integrated Training for AAMs:

  - We propose for training of 25 state level trainers – 5 trainers for each of the 5 cadres.

  - The target for AAM Primary HealthCare team is as given below:

| S.No | Target trainees | No. of days | Number | Target for FY 2026-27 |
| --- | --- | --- | --- | --- |
| 1 | Medical Officer | 6 | 85 | 17 |
| 2 | Staff Nurse | 5+5 | 219 | 44 |
| 3 | CHO (HWO) | 5+5 | 326 | 64 |
| 4 | ANMs (HWs/MPWs) | 5+5 | 919 | 180 |
| 5 | ASHAs | 5+5+4 | 1091 | 217 |
|  | Total no. of trainees targeted |  | 2640 | 528 |

- Budget proposed:

  - Training of state trainers at regional level

As per the aforementioned guidelines, all costs of regional level training except TADA is to be provided by MoHFW. The cost of travel and daily allowance is calculated as below:

| S.No | Particulars | Total No. | Unit cost (in Rs) | Total cost (in Rs) |
| --- | --- | --- | --- | --- |
| 1. | Training of state level trainers at regional level for integrated training | 25 | 20,000 | 5,00,000 |

  - State level training of various cadres under AAM:

| Training of Medical Officers from PHC-AAMs |  |  |  |  |
| --- | --- | --- | --- | --- |
| Activity | Per day per person cost | No. of persons | No. of Days | Total Cost in Rs. |
| DA | 700.00 | 17 | 6 | 71,400.00 |
| Honorarium to guest faculty | 1,000.00 | 5 | 6 | 30,000.00 |
| Honararium for monitoring | - | 2 | 6 | - |
| Food | 250.00 | 30 | 6 | 45,000.00 |
| Accomodation for trainers | - | 0 | 6 | - |
| Accomodation for participants | 1,000.00 | 17 | 6 | 1,02,000.00 |
| Incidental expenses | 250.00 | 17 | 6 | 25,500.00 |
| Venue Hiring | 5,000.00 | 1 | 6 | 30,000.00 |
| Sub Total |  |  |  | 3,03,900.00 |
| Institutional overhead (15%) |  |  |  | 45,585.00 |
| Total |  |  |  | 3,49,485.00 |
| No. of batches |  |  |  | 1.00 |
| Total |  |  |  | 3,49,485.00 |

| Training of Staff Nurses & CHOs from AAMS |  |  |  |  |
| --- | --- | --- | --- | --- |
| Activity | Per day per person cost | No. of persons | No. of Days | Total Cost in INR |  |
| DA | 400 | 36 | 10 | 1,44,000.00 |  |
| Honorarium to guest faculty | 1000 | 5 | 10 | 50,000.00 |  |
| Honararium for monitoring | 0 | 2 | 10 | - |  |
| Food | 250 | 50 | 10 | 1,25,000.00 |  |
| Accomodation for trainers | 0 | 0 | 10 | - |  |
| Accomodation for participants | 1000 | 36 | 10 | 3,60,000.00 |  |
| Incidental expenses | 250 | 36 | 10 | 90,000.00 |  |
| Venue Hiring | 5000 | 1 | 10 | 50,000.00 |  |
| Sub Total |  |  |  | 8,19,000.00 |  |
| Institutional overhead |  |  |  | 1,22,850.00 |  |
| Total |  |  |  | 9,41,850.00 |  |
| No. of batches |  |  |  | 3.00 |  |
| Total |  |  |  | 28,25,550.00 |  |

| Training- ANMs & MPW (Male) (6 batches) |  |  |  |  |
| --- | --- | --- | --- | --- |
| Activity | Per day per person cost | No. of persons | No. of Days | Total Cost in INR |  |
| DA | 400 | 30 | 10 | 1,20,000.00 |  |
| Honorarium to guest faculty | 1000 | 5 | 10 | 50,000.00 |  |
| Honararium for monitoring | 0 | 2 | 10 | - |  |
| Food | 250 | 50 | 10 | 1,25,000.00 |  |
| Accomodation for trainers | 0 | 0 | 10 | - |  |
| Accomodation for participants | 500 | 30 | 10 | 1,50,000.00 |  |
| Incidental expenses | 250 | 30 | 10 | 75,000.00 |  |
| Venue Hiring | 5000 | 1 | 10 | 50,000.00 |  |
| Sub Total |  |  |  | 5,70,000.00 |  |
| Institutional overhead |  |  |  | 85,500.00 |  |
| Total |  |  |  | 6,55,500.00 |  |
| No. of batches |  |  |  | 6.00 |  |
| Total |  |  |  | 39,33,000.00 |  |

| Training- ASHA (7 batches) |  |  |  |  |
| --- | --- | --- | --- | --- |
| Activity | Per day per person cost | No. of persons | No. of Days | Total Cost in INR |  |
| DA | 400.00 | 31 | 14 | 1,73,600.00 |  |
| Honorarium to guest faculty | 1,000.00 | 5 | 14 | 70,000.00 |  |
| Honararium for monitoring | - | 2 | 14 | - |  |
| Food | 250.00 | 50 | 14 | 1,75,000.00 |  |
| Accomodation for trainers | 3,000.00 | 5 | 14 | 2,10,000.00 |  |
| Accomodation for participants | 500.00 | 31 | 14 | 2,17,000.00 |  |
| Incidental expenses | 200.00 | 31 | 14 | 86,800.00 |  |
| Venue Hiring | 5,000.00 | 1 | 14 | 70,000.00 |  |
| Sub Total |  |  |  | 10,02,400.00 |  |
| Institutional overhead |  |  |  | 1,50,360.00 |  |
| Sub Total |  |  |  | 11,52,760.00 |  |
| No. of batches |  |  |  | 7.00 |  |
| Total |  |  |  | 80,69,320.00 |  |

Abstract of proposed cost for Integrated Training of Primary Health Care Team (AAM team):

| Cadre | Total Cost |
| --- | --- |
| Medical Officer | 3,49,485.00 |
| Staff nurses & CHO (HWO) | 28,25,550.00 |
| ANMs (HWs/MPWs) | 39,33,000.00 |
| ASHAs | 80,69,320.00 |
| Sub-Total | 1,51,77,355.00 |
| Travel allowance (35%) | 53,12,074.25 |
| Total | 2,04,89,429.25 |