### MATERNAL HEALTH

RCH 1 – Sl No 1: Scheme – Village Health Sanitation & Nutrition Days (VHSNDs): Rs. 10,48,800/-

Components - Others including operating costs (OOC)

Particulars : Village Health Sanitation & Nutrition Days (VHSNDs)

Village Health Sanitation & Nutrition Days (VHSNDs) were successfully carried out across various villages in Mizoram as part of the ongoing efforts to strengthen community-level health and nutrition services. The event served as an important platform to deliver integrated maternal, child health and nutrition services directly to the community.

During the VHND sessions, a wide range of services such as antenatal and postnatal check-ups, immunization, growth monitoring, counselling on nutrition and family planning, as well as health awareness activities were conducted. Special emphasis was placed on improving health-seeking behaviour among women and children. The programme witnessed active participation and involvement of Non-Governmental Organisations (NGOs), who supported mobilization, awareness generation and facilitation of services. Their contribution helped ensure greater community participation and outreach to remote areas. Furthermore, the event was marked by strong inter-sectoral convergence between the Health Department and other line departments, particularly the Women and Child Development (WCD) Department. The convergence ensured coordinated service delivery through the joint efforts of HWOs, ANMs, ASHAs, Anganwadi Workers and other field-level functionaries.

Overall, the VHND in Mizoram demonstrated effective collaboration between departments and community-based organisations, contributing to the overall goal of improving maternal and child health outcomes in the State.The State is having 874 VHSNC and for this, the State is proposing Rs. 100 / month to be utilized for conducting VHND.

| Sno | District | No of VHSNC | Incentive @1200 |
| --- | --- | --- | --- |
| 1 | Aizawl East | 93 | 111600 |
| 2 | Aizawl west | 65 | 78000 |
| 3 | Champhai | 60 | 72000 |
| 4 | Hnahthial | 28 | 33600 |
| 5 | Khawzawl | 38 | 45600 |
| 6 | Kolasib | 60 | 72000 |
| 7 | Lawngtlai | 166 | 199200 |
| 8 | Lunglei | 111 | 133200 |
| 9 | Mamit | 83 | 99600 |
| 10 | Saitual | 43 | 51600 |
| 11 | Serchhip | 50 | 60000 |
| 12 | Siaha | 77 | 92400 |
| TOTAL |  | 874 | 1048800 |

Rs. 100 X 874VHSND X 12 Months = Rs. 10,48,800/-

RCH 1 – Sl No 2:Scheme – Pregnancy Registration and Ante-Natal Checkups

Components - Equipment (Including Furniture, Excluding Computers)

Particulars : Equipments for Screening of Gestational Diabetes Mellitus

As a part of MH intervention to control the high prevalence of GDM in Indian Women during pregnancy and it is expected increasing incidence, universal screening of GDM and treatment for GDM is planned to avoid the wide range of maternal (and neonatal) morbidity and mortality.

Total requirement for estimated pregnancy 21866  is Rs 9,00,000/-

| Sl.no | instrument for screening of GDM | Cost | Required amount | Total Amount |
| --- | --- | --- | --- | --- |
| 1 | Glucometer Strips | 15 | 15000 | 225000 |
| 2 | 75g Glucose pouch | 30 | 20000 | 600000 |
| 3 | Lancet for glucometer | 5 | 15000 | 75000 |
| total amount |  |  |  | 900000 |

RCH 1 – Sl No 2:Scheme – Pregnancy Registration and Ante-Natal Checkups

Components - Equipment (Including Furniture, Excluding Computers)

Particulars: Equipments for Syphilis/Syphilis & HIV Dual Kit in Pregnancy

As a part of Maternal Health intervention, Syphilis and HIV are a sexually transmitted infection and it’s primary route of transmission is through sexual contact. Screening and management of syphilis and HIV will result in reduced incidence of low birth weight (LBW), perinatal deaths and congenital syphilis, thus will improve pregnancy outcomes and reduced maternal morbidity. Screening of syphilis and HIV by point of care dual test kit at Sub- centre twice during pregnancy and spouse testing as part of ANC package planned for 21866 PW is Rs. 8, 40,000/- only and is tabulated as given below: -

| Sl.no | Budget Head | Cost in Rs | Quantity | Total Amount in Rs |
| --- | --- | --- | --- | --- |
| 1 | POC test kits / Syphilis & HIV Dual Kit | 28 | 30000 | Rs. 8,40,000 |

RCH 1 – Sl No 2:Scheme – Pregnancy Registration and Ante-Natal Checkups

Components –Equipment (Including Furniture, Excluding Computers)

Particulars: Procurement of different equipment for conducting Delivery

Instruments & Equipment required for delivery planned for 78 public PHC/UPHC/CHC/SDH and 144 HWC/SC/SC clinics conducting delivery (List attached below) is Rs 15,27,500/-

| Sl No | Item | Amount | Price | Total Price |
| --- | --- | --- | --- | --- |
| 1 | Weighing Machine (adult) | 10 | 1300 | 13000 |
| 2 | Newborn weighing machine | 15 | 1800 | 27000 |
| 3 | Episiotomy scissor | 30 | 400 | 12000 |
| 4 | Plain forcep | 30 | 300 | 9000 |
| 5 | Artery forcep (straight) | 30 | 350 | 10500 |
| 6 | Artery forcep (curved) | 30 | 350 | 10500 |
| 7 | Surgical scissor | 30 | 400 | 12000 |
| 8 | Needle holder | 30 | 400 | 12000 |
| 9 | Sponge holding forcep | 30 | 350 | 10500 |
| 10 | Sims Speculum | 20 | 550 | 11000 |
| 11 | Allis forcep | 20 | 350 | 7000 |
| 12 | Tooth forcep | 30 | 350 | 10500 |
| 13 | Cheatle Forcep | 20 | 400 | 8000 |
| 14 | kidney tray | 30 | 350 | 10500 |
| 15 | Steel tray with lid | 20 | 1000 | 20000 |
| 16 | Kelly's pad | 30 | 500 | 15000 |
| 17 | Mackintosh sheet | 30 | 300 | 9000 |
| 18 | Delivery Trolley | 10 | 10000 | 100000 |
| 19 | Radiant Warmer | 15 | 48000 | 720000 |
| 20 | Labor bed | 10 | 50000 | 500000 |
| TOTAL |  |  |  | Rs 15,27,500 |

RCH 1 – Sl No 2:Scheme – Pregnancy Registration and Ante-Natal Checkups

Components –Drugs

Particulars : Procurement of Calcium tablets &Vit D3 for pregnant women

Proposed for 21866 PW to be given twice daily (2 tabs) during pregnancy ( 6 months) & post partum (3 months) + 5% buffers @Rs 0.5/tab is Rs 61,98,444/-

| Sl.no | Name of District | Expected pregnancy | requirement during pregnancy i.e 360 tab/PW | requirement during post partum i.e 180 tab/pw | 5% buffer stock | Total stock required | total price @ Rs 0.5/tab |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Aizawl East | 4274 | 1538640 | 769320 | 115398 | 2423358 | 1211679 |
| 2 | Aizawl west | 3166 | 1139760 | 569880 | 85482 | 1795122 | 897561 |
| 3 | Champhai | 1469 | 528840 | 264420 | 39663 | 832923 | 416461.5 |
| 4 | Hnahthial | 527 | 189720 | 94860 | 14229 | 298809 | 149404.5 |
| 5 | Khawzawl | 677 | 243720 | 121860 | 18279 | 383859 | 191929.5 |
| 6 | Kolasib | 1590 | 572400 | 286200 | 42930 | 901530 | 450765 |
| 7 | Lawngtlai | 2464 | 887040 | 443520 | 66528 | 1397088 | 698544 |
| 8 | Lunglei | 2425 | 873000 | 436500 | 65475 | 1374975 | 687487.5 |
| 9 | Mamit | 1805 | 649800 | 324900 | 48735 | 1023435 | 511717.5 |
| 10 | Saitual | 984 | 354240 | 177120 | 26568 | 557928 | 278964 |
| 11 | Serchhip | 1337 | 481320 | 240660 | 36099 | 758079 | 379039.5 |
| 12 | Siaha | 1146 | 412560 | 206280 | 30942 | 649782 | 324891 |
| Total |  | 21866 | 7871040 | 3935520 | 590328 | 12396888 | 61,98,444 |

RCH 1 – Sl No 3: Scheme – Janani Suraksha Yojana (JSY)

Components - DBT

Particulars: Beneficiary Compensation under Janani Suraksha Yojana (JSY) - Rural

Proposal for 7351 JSY beneficiaries on rural areas @Rs. 700 is Rs. 51,45,700/- i.e. Rs. 51.45 Lakhs

| S.No | District | Expected Delivery at Rural area | Budget for Rural @Rs. 700/- |
| --- | --- | --- | --- |
| 1 | Aizawl East | 786 | 550200 |
| 2 | Aizawl west | 582 | 407400 |
| 3 | Champhai | 676 | 473200 |
| 4 | Hnahthial | 243 | 170100 |
| 5 | Khawzawl | 312 | 218400 |
| 6 | Kolasib | 585 | 409500 |
| 7 | Lawngtlai | 1134 | 793800 |
| 8 | Lunglei | 607 | 424900 |
| 9 | Mamit | 831 | 581700 |
| 10 | Saitual | 453 | 317100 |
| 11 | Serchhip | 615 | 430500 |
| 12 | Siaha | 527 | 368900 |
| Total |  | 7351 | 5145700 |

Particulars: Beneficiary Compensation under Janani Suraksha Yojana (JSY) - Urban Proposed for 2743 expected deliveries at urban areas @Rs. 600 =Rs. 16,45,800/- i.e. Rs. 16.46 Lakhs

| S.No | District | Expected Delivery at Urban areas | Budget for Urban @Rs. 600/- |
| --- | --- | --- | --- |
| 1 | Aizawl East | 1180 | 708000 |
| 2 | Aizawl West | 875 | 525000 |
| 3 | Champhai | 136 | 81600 |
| 4 | Kolasib | 147 | 88200 |
| 5 | Lunglei | 405 | 243000 |
| Total |  | 2743 | 1645800 |

HSS 17– 202: Scheme: ASHA Incentives (Incl. RCH, NDCP, NCD, HSS-Urban, HSS-Rural)

Incentives to ASHA

Scheme – Janani Suraksha Yojana (JSY)

Components – DBT

ASHA Rural:

Incentive for 7351 ASHA Rural delivery is proposed for deliveries @Rs.600/beneficiaries at Rural = Rs.44,10,600/- i.e. Rs. 44.11 Lakhs

| Sl.no | Name of District | No. of ASHA beneficiaries in RURAL | Budget for rural ASHAs (In rs) |
| --- | --- | --- | --- |
| 1 | Aizawl East | 786 | 471600 |
| 2 | Aizawl west | 582 | 349200 |
| 3 | Champhai | 676 | 405600 |
| 4 | Hnahthial | 243 | 145800 |
| 5 | Khawzawl | 312 | 187200 |
| 6 | Kolasib | 585 | 351000 |
| 7 | Lawngtlai | 1134 | 680400 |
| 8 | Lunglei | 607 | 364200 |
| 9 | Mamit | 831 | 498600 |
| 10 | Saitual | 453 | 271800 |
| 11 | Serchhip | 615 | 369000 |
| 12 | Siaha | 527 | 316200 |
| TOTAL |  | 7351 | 4410600 |

HSS 17– 202: Scheme: ASHA Incentives (Incl. RCH, NDCP, NCD, HSS-Urban, HSS-Rural)

ASHA URBAN:

Incentive for 2743 ASHA Urban delivery is proposed for ASHAs @Rs.400 = Rs. 10,97,200/- i.e. Rs. 10.97 Lakhs

| S.No | District | Expected Delivery at Urban areas | Budget for Urban @Rs. 600/- |
| --- | --- | --- | --- |
| 1 | Aizawl East | 1180 | 472000 |
| 2 | Aizawl West | 875 | 350000 |
| 3 | Champhai | 136 | 54400 |
| 4 | Kolasib | 147 | 58800 |
| 5 | Lunglei | 405 | 162000 |
| Total |  | 2743 | 1097200 |

HSS 11 – 194: Scheme: Planning and Program Management

JSY Administrative Expenses –

Total proposal = Rs. 6,14,965/-

| Sl.no | Name of District | JSY budget PW + ASHA (In Rs) | (.04 x Total JSY budget) (In Rs) | STATE | TOTAL JSY Administrative Expense |
| --- | --- | --- | --- | --- | --- |
| 1 | Aizawl East | 2201800 | 88072 | 122993 | 614965 |
| 2 | Aizawl west | 1631600 | 65264 |  |  |
| 3 | Champhai | 1014800 | 40592 |  |  |
| 4 | Hnahthial | 315900 | 12636 |  |  |
| 5 | Khawzawl | 405600 | 16224 |  |  |
| 6 | Kolasib | 907500 | 36300 |  |  |
| 7 | Lawngtlai | 1474200 | 58968 |  |  |
| 8 | Lunglei | 1194100 | 47764 |  |  |
| 9 | Mamit | 1080300 | 43212 |  |  |
| 10 | Saitual | 588900 | 23556 |  |  |
| 11 | Serchhip | 799500 | 31980 |  |  |
| 12 | Siaha | 685100 | 27404 |  |  |
| TOTAL |  | 12299300 | 491972 |  |  |

RCH 1 – Sl No 4:Scheme – Janani Shishu Suraksha Karyakram (JSSK) (excluding transport)

Components - Others including operating costs (OOC)

Particulars : Blood Transfusion for JSSK Beneficiaries

Blood transfusion is proposed for Pregnant women expected to require blood transfusion for all districts @Rs.300 which comes to a total of Rs.300 x 620= Rs. i.e.Rs.1,86,000 lakhs

District wise break up of Blood transfusion for PW in all districts are given below:

| Sl.no | Name of District | No. of Expected Blood transfusion | (Unit Cost Rs.300) x (Expected Blood transfusion) |
| --- | --- | --- | --- |
| 1 | Aizawl East | 100 | 30000 |
| 2 | Aizawl west | 50 | 15000 |
| 3 | Champhai | 40 | 12000 |
| 4 | Hnahthial | 30 | 9000 |
| 5 | Khawzawl | 30 | 9000 |
| 6 | Kolasib | 100 | 30000 |
| 7 | Lawngtlai | 50 | 15000 |
| 8 | Lunglei | 100 | 30000 |
| 9 | Mamit | 30 | 9000 |
| 10 | Saitual | 30 | 9000 |
| 11 | Serchhip | 30 | 9000 |
| 12 | Siaha | 30 | 9000 |
| TOTAL |  | 620 | 186000 |

RCH 1 – Sl No 4 : Scheme – Janani Shishu Suraksha Karyakram (JSSK) (excluding transport)

Components – Drugs

Particulars - Drugs and Consumables under JSSK (Normal Delivery)

### Drugs and consumables proposed for expected 7822 normal deliveries i.e. @Rs.350 = Rs. 27, 37,560/-

RCH 1 – Sl No 4: Scheme – Janani Shishu Suraksha Karyakram (JSSK) (excluding transport)

Components – Drugs

Particulars - Drugs and Consumables under JSSK (C-section)

| Sl.no | Name of District | Expected Normal Delivery | expected ND x 350 (InRs.) |
| --- | --- | --- | --- |
| 1 | Aizawl East | 1529 | 535080 |
| 2 | Aizawl west | 1133 | 396480 |
| 3 | Champhai | 526 | 183960 |
| 4 | Hnahthial | 188 | 65940 |
| 5 | Khawzawl | 242 | 84840 |
| 6 | Kolasib | 569 | 199080 |
| 7 | Lawngtlai | 881 | 308490 |
| 8 | Lunglei | 868 | 303660 |
| 9 | Mamit | 646 | 225960 |
| 10 | Saitual | 352 | 123270 |
| 11 | Serchhip | 478 | 167370 |
| 12 | Siaha | 410 | 143430 |
| TOTAL |  | 7822 | 2737560 |

### Drugs and consumables proposed for 457 CS is Rs. 7,31,200/-

| Sl.no | Name of District | expected C-section | expected CS x1600 (In Rs) |
| --- | --- | --- | --- |
| 1 | Aizawl East | 89 | 142400 |
| 2 | Aizawl west | 66 | 105600 |
| 3 | Champhai | 31 | 49600 |
| 4 | Hnahthial | 11 | 17600 |
| 5 | Khawzawl | 14 | 22400 |
| 6 | Kolasib | 33 | 52800 |
| 7 | Lawngtlai | 51 | 81600 |
| 8 | Lunglei | 51 | 81600 |
| 9 | Mamit | 38 | 60800 |
| 10 | Saitual | 21 | 33600 |
| 11 | Serchhip | 28 | 44800 |
| 12 | Siaha | 24 | 38400 |
| TOTAL |  | 457 | 731200 |

RCH 1 – Sl No 4: Scheme – Janani Shishu Suraksha Karyakram (JSSK) (excluding transport)

Components - Diagnostics (Consumables, PPP, Sample Transport)

Particulars - Free Diagnostics for Pregnant Women (JSSK)

Free Diagnostics is proposed for expected 7822 PW i.e. for all districts @ Rs.300= Rs. 23,46,480/-

District wise breakup for Diagnostics of PW and budget is given below:

| Sl.no | Name of District | No. of expected PW (Inst. Delivery) | Rs.300 x No. of expected PW (in Rs.) |
| --- | --- | --- | --- |
| 1 | Aizawl East | 1529 | 458640 |
| 2 | Aizawl west | 1133 | 339840 |
| 3 | Champhai | 526 | 157680 |
| 4 | Hnahthial | 188 | 56520 |
| 5 | Khawzawl | 242 | 72720 |
| 6 | Kolasib | 569 | 170640 |
| 7 | Lawngtlai | 881 | 264420 |
| 8 | Lunglei | 868 | 260280 |
| 9 | Mamit | 646 | 193680 |
| 10 | Saitual | 352 | 105660 |
| 11 | Serchhip | 478 | 143460 |
| 12 | Siaha | 410 | 122940 |
| TOTAL |  | 7822 | 2346480 |

RCH 1 – Sl No 5: Scheme – Janani Shishu Suraksha Karyakram (JSSK) - transport

Components - Others including operating costs (OOC)

Particulars -Free Referral Transport for Pregnant women (JSSK)

Ongoing. Proposed for 7822 Pregnant women for transport from Home to institution and from Institution to home, and in case of Referral to higher institution @Rs.1000/PW = Rs. 78,21,600/-

District wise breakup for Transport of PW and budget is given below:

| Sl.no | Name of District | No. of expected PW | Rs. 1000 x No. of expected PW |
| --- | --- | --- | --- |
| 1 | Aizawl East | 1529 | 1528800 |
| 2 | Aizawl west | 1133 | 1132800 |
| 3 | Champhai | 526 | 525600 |
| 4 | Hnahthial | 188 | 188400 |
| 5 | Khawzawl | 242 | 242400 |
| 6 | Kolasib | 569 | 568800 |
| 7 | Lawngtlai | 881 | 881400 |
| 8 | Lunglei | 868 | 867600 |
| 9 | Mamit | 646 | 645600 |
| 10 | Saitual | 352 | 352200 |
| 11 | Serchhip | 478 | 478200 |
| 12 | Siaha | 410 | 409800 |
| TOTAL |  | 7822 | 7821600 |

RCH 1 – Sl No 6:Scheme – Pradhan Mantri Surakshit Matritva Abhiyan (PMSMA):

Components –OOC, DBT & ASHA Incentives

Particulars : PMSMA activities at State / District Level, Case-based incentives to beneficiaries, Incentive of ASHAs for mobilizing pregnant women to PMSMA

Total Budget under PMSMA – Rs 21,24,450/-

The Pradhan Mantri SurakshitMatritva Abhiyan (PMSMA) has been launched by the Ministry of Health & Family Welfare (MoHFW), Government of India and it was launched in Mizoram on 9th June’2016 and it has been functioning ever since. The program provides quality antenatal care to many beneficiaries free of cost on 9th and 24th of every month at public hospitals. More than 73000 pregnant women were seen at PMSMA & E-PMSMA service. More than 4700 high risks pregnancy were detected, given treatment and referral based on their requirement.

ACTIVITY 1 : Case-based incentives to beneficiaries: Rs 3,35,100/-

Under Extended PMSMA, once a pregnant woman is diagnosed as High-Risk Pregnancy, Rs. 100/- per visit may be provided to meet transportation costs for attending a maximum of three PMSMA sessions/nearest facility for follow up ANC checkups by a doctor/Obstetrician. 5% of Expected Pregnancy are expected to be detected as High-risk pregnancy in PMSMA clinic according to PMSMA report.

For 5% of PW, incentive is proposed for 3 visits @Rs.100/visit for mothers i.e Rs.300 x = Rs.3,35,100/-

| Sl.No | District | Expected pregnancy | Expected High Risk Pregnancy (5% of Expected PW) | Incentive to HRP PW (Rs 300/PW) |
| --- | --- | --- | --- | --- |
| 1 | AizawlEast | 4274 | 214 | 64200 |
| 2 | Aizawl west | 3166 | 160 | 48000 |
| 3 | Champhai | 1469 | 75 | 22500 |
| 4 | Hnahthial | 527 | 30 | 9000 |
| 5 | Khawzawl | 677 | 35 | 10500 |
| 6 | Kolasib | 1590 | 80 | 24000 |
| 7 | Lawngtlai | 2464 | 125 | 37500 |
| 8 | Lunglei | 2425 | 125 | 37500 |
| 9 | Mamit | 1805 | 95 | 28500 |
| 10 | Saitual | 984 | 50 | 15000 |
| 11 | Serchhip | 1337 | 68 | 20400 |
| 12 | Siaha | 1146 | 60 | 18000 |
| TOTAL |  | 21866 | 1117 | 335100 |

ACTIVITY 2 :	Outreach activity – district level : Rs 2,40,000/-

Proposed for mobility support of outreach session (under E-PMSMA)  for Gynaecologist and medical officers to facilities where gynaecologists and medical officers are not available in the vacant facilities.

| Sl.no | Name of District | Amount |
| --- | --- | --- |
| 1 | Aizawl East | 20000 |
| 2 | Aizawl West | 20000 |
| 3 | Champhai | 20000 |
| 4 | Hnahthial | 20000 |
| 5 | Khawzawl | 20000 |
| 6 | Kolasib | 20000 |
| 7 | Lawngtlai | 20000 |
| 8 | Lunglei | 20000 |
| 9 | Mamit | 20000 |
| 10 | Saitual | 20000 |
| 11 | Serchhip | 20000 |
| 12 | Siaha | 20000 |
| TOTAL |  | 240000 |

ACTIVITY 3 : District Level PMSMA budget: Rs 5,99,000/-

For undertaking activities such as sensitization of stakeholders & meetings of committees calculated based on the number of public hospitals in each district.

| Sno | District | District Hospital | SDH+CHC | PHC+UPHC | Total amount for facility level |
| --- | --- | --- | --- | --- | --- |
| 1 | Aizawl East | 1 x 20000 | 2 x 8000 | 6 x 5000 | 66000 |
| 2 | Aizawl west | 1 x 15000 | 2 x 8000 | 6 x 5000 | 61000 |
| 3 | Champhai | 1 x 20000 | 0 | 6 x 5000 | 50000 |
| 4 | Hnahthial | 1 x 8000 | 0 | 5 x 5000 | 33000 |
| 5 | Khawzawl | 1 x 8000 | 1 x 8000 | 4 x 5000 | 36000 |
| 6 | Kolasib | 1 x 15000 | 1 x 8000 | 6 x 5000 | 53000 |
| 7 | Lawngtlai | 1 x 15000 | 1 x 10000 | 5 x 5000 | 50000 |
| 8 | Lunglei | 1 x 20000 | 1 x 8000 | 7 x 5000 | 63000 |
| 9 | Mamit | 1 x 15000 | 1 x 8000 | 8 x 5000 | 63000 |
| 10 | Saitual | 1 x 8000 | 1 x 8000 | 5 x 5000 | 41000 |
| 11 | Serchhip | 1 x 15000 | 1 x 8000 | 5 x 5000 | 48000 |
| 12 | Siaha | 1 x 15000 | 0 | 4 x 5000 | 35000 |
|  | Total |  |  |  | Rs 5,99,000 |

HSS 17– 202: Scheme: ASHA Incentives (Incl. RCH, NDCP, NCD, HSS-Urban, HSS-Rural)

Incentive of ASHAs for mobilizing pregnant women to PMSMA

Incentives of ASHAs for mobilizing pregnant women to PMSMA clinics/ facility with doctor/obstetrician.

- Rs. 100/- per HRP may be provided to ASHA for mobilization of HRPs for a maximum of three follow up ANC visits to PMSMA clinics/nearest facility for check up by a doctor/Obstetrician. (of PW are expected to be identified as HRP)

- Rs. 500/- per HRP may be provided to ASHA on achieving a healthy outcome for both mother and baby at 45th day after delivery after due verification by concerned ANM and MO. (90% of HRP are expected to achieve healthy outcome.)

- Rs 250/- per HRP identified in post-partum period and send to PMSMA session. (2% of expected pregnancy are estimated to be HRP in this period).

Total estimated for ASHA = Rs 9,50,350/-

| Sl.No | District | Expected pregnancy | Expected HRP (5% of Expected PW) | A. ASHA- Mobilization of HRPs (3 visit/Rs 100 per visit) | 90% of HRP | B. ASHA - Achieving Healthy outcome (Rs 500 for 90% of HRP) | 2% of expected PW | C. ASHA - Post Partum HRP identification (Rs 250/2% of expected PW) | Total (A + B + C) |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Aizawl East | 4274 | 214 | 64200 | 193 | 96500 | 86 | 21500 | 182200 |
| 2 | Aizawl west | 3166 | 160 | 48000 | 144 | 72000 | 64 | 16000 | 136000 |
| 3 | Champhai | 1469 | 75 | 22500 | 68 | 34000 | 30 | 7500 | 64000 |
| 4 | Hnahthial | 527 | 30 | 9000 | 27 | 13500 | 11 | 2750 | 25250 |
| 5 | Khawzawl | 677 | 35 | 10500 | 32 | 16000 | 14 | 3500 | 30000 |
| 6 | Kolasib | 1590 | 80 | 24000 | 72 | 36000 | 32 | 8000 | 68000 |
| 7 | Lawngtlai | 2464 | 125 | 37500 | 113 | 56500 | 50 | 12500 | 106500 |
| 8 | Lunglei | 2425 | 125 | 37500 | 113 | 56500 | 49 | 12250 | 106250 |
| 9 | Mamit | 1805 | 95 | 28500 | 86 | 43000 | 37 | 9250 | 80750 |
| 10 | Saitual | 984 | 50 | 15000 | 45 | 22500 | 20 | 5000 | 42500 |
| 11 | Serchhip | 1337 | 68 | 20400 | 62 | 31000 | 27 | 6750 | 58150 |
| 12 | Siaha | 1146 | 60 | 18000 | 54 | 27000 | 23 | 5750 | 50750 |
| State |  | 21866 | 1117 | 335100 | 1009 | 504500 | 443 | 110750 | Rs 950350 |

RCH 1 – Sl No 7: Scheme – Surakshit Matritva Aashwasan (SUMAN)& HSS 11 – 194: Scheme: Planning and Program Management

Components –DBT & Others including operating costs (OOC)

Particulars: SUMAN Committee / Meeting and 1st responder for Maternal Death Incentive

Surakshit Matritva Aashwasan (SUMAN) is an initiative under MH which aimed at eliminating preventable maternal and newborn deaths. A total of 356 facilities were notified during 2021-2024 and 109 more facilities will be notified during 2025-26. Total Proposal under SUMAN is Rs. 42,000/- and budget breakup is tabulated below:

- SUMAN Committee/meetings:Rs 20,000/-

- State level committee – 2000 x 4 times = Rs 8000

- District level meeting with stakeholder for community engagement – Rs 1000 x 12 times x district = Rs 12000

- 1st responder for Maternal Death Incentive: Rs 22,000/-

The total budget estimated for incentive for 1st responder of Maternal death under SUMAN is Rs 22,000/-.

Total case estimated – 22

Incentive per case – Rs 1000

| Sl.No | District | Expected Maternal Death | Incentives for 1st responder @Rs. 1000 |
| --- | --- | --- | --- |
| 1 | AizawlEast | 3 | 3000 |
| 2 | Aizawl west | 2 | 2000 |
| 3 | Champhai | 2 | 2000 |
| 4 | Hnahthial | 1 | 1000 |
| 5 | Khawzawl | 1 | 1000 |
| 6 | Kolasib | 2 | 2000 |
| 7 | Lawngtlai | 3 | 3000 |
| 8 | Lunglei | 3 | 3000 |
| 9 | Mamit | 2 | 2000 |
| 10 | Saitual | 1 | 1000 |
| 11 | Serchhip | 1 | 1000 |
| 12 | Siaha | 1 | 1000 |
| TOTAL |  | 22 | 22000 |

RCH 1 – Sl No 9: Scheme – Maternal Death Review

Components - Surveillance, Research, Review, Evaluation (SRRE)

Particulars: Maternal Death Review

- Community Audit:

Community based MDR using a verbal autopsy format is a method of finding out the medical causes of death and ascertaining the personal, family or community factors that may have contributed to the deaths.  The verbal autopsy consists of interviewing people who are knowledgeable about the events leading to the death such as family members, neighbors and traditional birth attendants.

Community based and facility-based audit must be taken up for all deaths that occurred in the specified geographical area, irrespective of the place of death, be it at home, facility or in transit. Budget estimated for 22 expected Maternal Death community audit is Rs.18700/- only and is tabulated below: -

| Community Audit |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| District | Expected MD | Honorarium for verbal Autopsy (VA) investigation team per district (Rs. 450/MD) | Travel Expenses for Verbal Autopsy Team (Rs. 200/team) | Reimbursement of travel expenses (Rs. 200/MD) | Amount |
| Aizawl East | 3 | 1350 | 600 | 600 | 2550 |
| Aizawl West | 2 | 900 | 400 | 400 | 1700 |
| Champhai | 2 | 900 | 400 | 400 | 1700 |
| Hnahthial | 1 | 450 | 200 | 200 | 850 |
| Khawzawl | 1 | 450 | 200 | 200 | 850 |
| Kolasib | 2 | 900 | 400 | 400 | 1700 |
| Lawngtlai | 3 | 1350 | 600 | 600 | 2550 |
| Lunglei | 3 | 1350 | 600 | 600 | 2550 |
| Mamit | 2 | 900 | 400 | 400 | 1700 |
| Saitual | 1 | 450 | 200 | 200 | 850 |
| Serchhip | 1 | 450 | 200 | 200 | 850 |
| Siaha | 1 | 450 | 200 | 200 | 850 |
| TOTAL |  | 9900 | 4400 | 4400 | 18700 |

Meeting Expense for the Maternal Death and Child death Review = Rs 3,12,000/-

- At District CMO Level @ Rs. 1000 X 12 Districts X 12 months = Rs. 144000/-

- At District DC Level @Rs. 1000 X 12 District X 4 = Rs. 48000/-

- Facility level comt (for 9 DH except new district) Rs. 1000 X 9 Districts X 12 months = Rs 108000/-

- At State Level @ Rs. 5000 X 2 =Rs. 10000/-

- State Level Task Force Meeting once a year = Rs. 2000/-

| District | State Level Meeting | State Level Task Force Meeting | CMO Level Meeting | DC Level Meeting | Facility Level Committee | Amount |
| --- | --- | --- | --- | --- | --- | --- |
| Aizawl East |  |  | 12000 | 4000 | 12000 | 28000 |
| Aizawl West |  |  | 12000 | 4000 | 12000 | 28000 |
| Champhai |  |  | 12000 | 4000 | 12000 | 28000 |
| Hnahthial |  |  | 12000 | 4000 |  | 16000 |
| Khawzawl |  |  | 12000 | 4000 |  | 16000 |
| Kolasib |  |  | 12000 | 4000 | 12000 | 28000 |
| Lawngtlai |  |  | 12000 | 4000 | 12000 | 28000 |
| Lunglei |  |  | 12000 | 4000 | 12000 | 28000 |
| Mamit |  |  | 12000 | 4000 | 12000 | 28000 |
| Saitual |  |  | 12000 | 4000 |  | 16000 |
| Serchhip |  |  | 12000 | 4000 | 12000 | 28000 |
| Siaha |  |  | 12000 | 4000 | 12000 | 28000 |
| State | 10000 | 2000 |  |  |  | 12000 |
| Total | 10000 | 2000 | 144000 | 48000 | 108000 | 312000 |

Total Budget under Maternal Death Review = Rs. 312000 + Rs 18700 = Rs 3,30,700/-

RCH 1 – Sl No 10: Scheme – Comprehensive Abortion Care

Components - Equipment (Including Furniture, Excluding Computers)

Particulars:	MVA/EVA for Safe Abortion services

Budget estimated for Procurement of required equipment for strengthening Safe Abortion services under Comprehensive Abortion Care (CAC) in designated CAC facilities for estimated cases of in facilities is Rs.1,00,000/- only and is tabulated below:

| Sl No | CAC equipment | Required amount | Price per unit | Final required amount |
| --- | --- | --- | --- | --- |
| 1 | Volsellum forcep | 20 | 500 | 10000 |
| 2 | Double valve MVA Kit | 30 | 3000 | 90000 |
| Total |  |  |  | Rs 1,00,000 |

HSS 16– 201: Scheme: Capacity building incl. training (Incl. RCH, NDCP, NCD, HSS-Urban, HSS-Rural)

Components - Capacity building incl. training

Particulars:	CAC Training of Medical Officers in safe abortion (CAC)

Planned for 2 batches @Rs. 3,22,000/batch

- Target Load                       = 12

- No of Batches                   = 2

- Participants per batch     = 6

- Duration of Training         = 12 days

| Components | Rate/day (Rs) | No of days | Participants/batch | Amount |
| --- | --- | --- | --- | --- |
| Honorarium of Resource Person | 1000 | 12 | 1 | 12000 |
| Contingencies | 300 | 1 | 6 | 1800 |
| Training Manuals | 2500 | 1 | 6 | 15000 |
| TA for trainees | 8000 | 1 | 6 | 48000 |
| DA for trainees | 1000 | 12 | 6 | 72000 |
| Hiring of vehicles by trainer | 800 | 12 | 1 | 9600 |
| DA for support staffs | 400 | 12 | 2 | 9600 |
| Accommodation (includes fooding) | 1500 | 13 | 6 | 117000 |
| Working lunch, Tea & Snacks | 250 | 12 | 9 | 27000 |
| Incidental expenditure |  |  |  | 10000 |
| Total |  |  |  | 322000 |

For 2 batches = Rs 322000 x 2 = Rs 6,44,000/-

HSS 19– 204: Scheme: IEC & Printing (Incl. RCH, NDCP, NCD, HSS-Urban, HSS-Rural)

Components 	-	IEC & Printing

Particulars	:	Printing of CAC register

Printing of CAC Registers & Reporting Formats - For 93 facilities (12 DH, 2 SDH, 9 CHC, 61 PHC & 9 UPHC) = Rs 1,76,700/-

i)	Admission Register (Form III) for 93 facilities @Rs.500 x 1 copies = Rs. 46500/-

ii)	Evacuation Register for 93 facilities @ Rs.500 x 1 copies = Rs. 46500/-

iii)	Form II for 93 facilities @ Rs.300 x 1 copies = Rs. 27900/-

iv)	Form I (RMP OPINION FORM) for 93 facilities @ Rs.300 x 1 copies = Rs. 27900/-

v)	Consent Form for 93 facilities @Rs. 300/facilities - Rs. 27900/-

HSS 16– 201: Scheme: Capacity building incl. training (Incl. RCH, NDCP, NCD, HSS-Urban, HSS-Rural)

Components - Capacity building incl. training

Particulars: SBA training for SN & ANM

TRAINING OF STAFF NURSES IN SBA – For Nurses in Public Hospital

SBA Training for SN is proposed for 1batch of SN @Rs. 3,12,000/batch

1. Target Load			= 6

2. No of Batches		= 1

3. Participants per batch	= 6

4. Duration of Training	= 21days

| Components | Rate/day (Rs) | No of days | Participants/batch | Amount (Rs) |
| --- | --- | --- | --- | --- |
| DA for trainees | 400 | 21 | 6 | 50400 |
| Honorarium of Resource Person | 1000 | 21 | 1 | 21000 |
| Honorarium of Co Trainer | 700 | 21 | 2 | 29400 |
| Contingencies | 150 |  | 8 | 1200 |
| Training Modules | 500 |  | 6 | 3000 |
| TA for trainees | 2000 |  | 6 | 12000 |
| Working Lunch, Tea & Snacks | 200 | 21 | 10 | 42000 |
| DA for Support Staffs | 400 | 21 | 1 | 8400 |
| Accommodation for trainees | 1000 | 22 | 6 | 132000 |
| Institutional overhead |  |  |  | 12600 |
| TOTAL |  |  |  | 312000 |

Budget for 1batches of SN = Rs. 3,12,000

TRAINING OF ANM IN SBA - for ANM posted at 154 HWC/SC/SC clinics conducting delivery

SBA Training for ANM is proposed for 1batches of ANM @Rs.3,12,000/batch

1. Target Load			= 6

2. No of Batches		= 1

3. Participants per batch	= 6

4. Duration of Training	= 21days

| Components | Rate/day (Rs) | No of days | Participants/batch | Amount (Rs) |
| --- | --- | --- | --- | --- |
| DA for trainees | 400 | 21 | 6 | 50400 |
| Honorarium of Resource Person | 1000 | 21 | 1 | 21000 |
| Honorarium of Co Trainer | 700 | 21 | 2 | 29400 |
| Contingencies | 150 |  | 8 | 1200 |
| Training Modules | 500 |  | 6 | 3000 |
| TA for trainees | 2000 |  | 6 | 12000 |
| Working Lunch, Tea & Snacks | 200 | 21 | 10 | 42000 |
| DA for Support Staffs | 400 | 21 | 1 | 8400 |
| Accommodation for trainees | 1000 | 22 | 6 | 132000 |
| Institutional overhead |  |  |  | 12600 |
| TOTAL |  |  |  | 312000 |

Budget for 1 batch of ANM= Rs. 3,12,000

TOTAL PROPOSAL FOR SBA: SN & ANM =Rs.6,24,000

HSS 16– 201: Scheme: Capacity building incl. training (Incl. RCH, NDCP, NCD, HSS-Urban, HSS-Rural)

Components - Capacity building incl. training

Particulars : BeMOC Training for MO

Planned for 1 batch of MO consisting of 6 participants to be trained at Civil Hospital Aizawl @Rs.2,62,000/batch

- Target Load                        = 6

- No of Batches                    = 1

- Participants per batch      = 6

- Duration of Training         = 10 days

| Components | Rate/day (Rs) | No of days | Participants/batch | Amount |
| --- | --- | --- | --- | --- |
| Honorarium of Resource Person | 1000 | 10 | 2 | 20000 |
| Contingencies | 300 | 1 | 6 | 1800 |
| Training Manuals | 2000 | 1 | 6 | 12000 |
| TA for trainees | 10000 | 1 | 6 | 60000 |
| DA for trainees | 700 | 10 | 6 | 42000 |
| Hiring of vehicles by trainer | 500 | 10 | 2 | 10000 |
| DA for support staffs | 500 | 10 | 2 | 10000 |
| Accommodation | 1000 | 11 | 6 | 66000 |
| Working lunch, Tea & Snacks | 300 | 10 | 10 | 30000 |
| Incidental expenditure |  |  |  | 10200 |
| Total |  |  |  | 262000 |

Total Proposal for BEmOC for1 batch @Rs.262000

RCH 1 – Sl No 14: Scheme – Labor room

Components: Equipment (Including Furniture, Excluding Computers)

Particulars: Procurement for Labour room Consumables

Budget estimate for the procurement consumables for strengthening Labour room for conducting deliveries in the state is Rs 25,85,000/-

The total no of expected deliveries in public facilities is 13036.

| Sl No | Labour room consumables | Required amount | Price per unit | Final required amount |
| --- | --- | --- | --- | --- |
| 1 | Disposable sterile gloves (4 pairs /delivery) | 30000 | 25 | 750000 |
| 2 | Disposable syringe with needle (2 ml) (1/delivery) | 10000 | 2 | 20000 |
| 3 | Disposable syringe with needle (5 ml) (1/delivery) | 15000 | 5 | 75000 |
| 4 | Disposable syringe with needle (10 ml) (No of delivery/10) | 2000 | 8 | 16000 |
| 5 | Disposable cord clamp | 15000 | 12 | 180000 |
| 6 | Disposable mucus extractor | 6000 | 50 | 300000 |
| 7 | Sterile urinary catheter (Foley’s). (No of deliveries/10) | 2000 | 100 | 200000 |
| 8 | Chromic catgut 2-0. (No of deliveries/2) | 1000 | 500 | 500000 |
| 9 | Povidone iodine solution (500 ml). No of deliveries/10 | 1000 | 200 | 200000 |
| 10 | Cetrimide solution (1 L) . No of deliveries /20 | 300 | 180 | 54000 |
| 11 | Cotton rolls (Big) (No of deliveries/8) | 2000 | 70 | 140000 |
| 12 | Gauze than 10 metre. (No of deliveries/10) | 1000 | 150 | 150000 |
|  | TOTAL |  |  | 2585000 |

RCH 1 – Sl No 14: Scheme – Labor room

Components: Equipment (Including Furniture, Excluding Computers)

Particulars : Procurement for Strengthening Labour room

Instrument for Strengthening Labour room.

| Sl No | Item | Total item | Price per item | Total |
| --- | --- | --- | --- | --- |
| 1 | Drum 15”x22” | 10 | 1500 | 15000 |
| 2 | Drum 6”X 9” | 10 | 800 | 8000 |
| 3 | Ventous Cap | 5 | 1200 | 6000 |
| 4 | Radiant warmer | 5 | 48000 | 240000 |
| 5 | Suction machine | 5 | 40000 | 200000 |
| 6 | Hand held Foetal Doppler | 10 | 3000 | 30000 |
| 7 | BP Instruments (Digital) | 10 | 1200 | 12000 |
| TOTAL |  |  |  | 511000 |

HSS 19– 204: Scheme: IEC & Printing (Incl. RCH, NDCP, NCD, HSS-Urban, HSS-Rural)

Components: IEC & Printing

Particulars: Printing of RCH Register

| District | Estimated Total No of EC for 2026-27 | Nos. of register required for EC & PW (100 EC & PW per register) + 5% Buffer stock at State | Cost per Register for EC & PW @ Rs. 780/Register | Estimated Infants for 2026-27 | Nos. of register required for Infants (80 Infants per register) + 5% Buffer stock at State | Cost per Register for Infants @ Rs. 460/Register | Total Amount required |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Aizawl East | 24021 | 240 | 187364 | 3885 | 49 | 22340 | 209704 |
| Aizawl West | 16293 | 163 | 127085 | 2879 | 36 | 16552 | 143637 |
| Champhai | 8689 | 87 | 67774 | 1336 | 17 | 7681 | 75455 |
| Hnahthial | 2656 | 27 | 20717 | 479 | 6 | 2756 | 23473 |
| Khawzawl | 3656 | 37 | 28517 | 616 | 8 | 3540 | 32057 |
| Kolasib | 8578 | 86 | 66908 | 1445 | 18 | 8310 | 75218 |
| Lawngtlai | 15996 | 160 | 124769 | 2240 | 28 | 12882 | 137651 |
| Lunglei | 15099 | 151 | 117772 | 2204 | 28 | 12676 | 130448 |
| Mamit | 10123 | 101 | 78959 | 1641 | 21 | 9438 | 88397 |
| Saitual | 4962 | 50 | 38704 | 895 | 11 | 5146 | 43849 |
| Serchhip | 6734 | 67 | 52525 | 1216 | 15 | 6991 | 59516 |
| Siaha | 6705 | 67 | 52299 | 1042 | 13 | 5989 | 58288 |
| State |  | 60 | 46800 |  | 17 | 7820 | 54620 |
| Total | 123512 | 1295 | 1010194 | 19878 | 265 | 122121 | 1132314 |

HSS 19– 204: Scheme: IEC & Printing (Incl. RCH, NDCP, NCD, HSS-Urban, HSS-Rural)

Components: IEC & Printing

Particulars: Printing of Tracking form / Workplan

| Items | AE | AW | Cp | Hnt | Kzl | Kol | Lti | Lli | Mm | St | Sc | Sh |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| EC Both side (Estimated EC) | 24021 | 16293 | 8689 | 2656 | 3656 | 8578 | 15996 | 15099 | 10123 | 4962 | 6734 | 6705 |
| Estimated FP Users | 727 | 538 | 250 | 90 | 115 | 270 | 419 | 412 | 307 | 167 | 227 | 195 |
| Estimated Newly Preg Women | 4274 | 3166 | 1469 | 527 | 677 | 1590 | 2464 | 2425 | 1805 | 984 | 1337 | 1146 |
| ANC | 4274 | 3166 | 1469 | 527 | 677 | 1590 | 2464 | 2425 | 1805 | 984 | 1337 | 1146 |
| Delivery Outcome | 3889 | 2881 | 1337 | 480 | 616 | 1447 | 2243 | 2207 | 1643 | 896 | 1217 | 1043 |
| PNC | 1556 | 1153 | 535 | 192 | 246 | 579 | 897 | 883 | 657 | 358 | 487 | 417 |
| Infant Registration | 3885 | 2879 | 1336 | 479 | 616 | 1445 | 2240 | 2204 | 1641 | 895 | 1216 | 1042 |
| HBNC | 3069 | 2274 | 1055 | 379 | 486 | 1142 | 1770 | 1742 | 1297 | 707 | 960 | 823 |
| Total nos of tracking form / Workplan | 45694 | 32351 | 16141 | 5330 | 7090 | 16640 | 28494 | 27396 | 19279 | 9954 | 13516 | 12516 |
| Amount @Rs. 3.5/page | 159930 | 113228 | 56493 | 18656 | 24815 | 58240 | 99729 | 95887 | 67476 | 34839 | 47307 | 43805 |
| Total | 820405 |  |  |  |  |  |  |  |  |  |  |  |

HSS 16– 201: Scheme: Capacity building incl. training (Incl. RCH, NDCP, NCD, HSS-Urban, HSS-Rural)

Particulars: Orientation on RCH 2.0

| RCH 2.0 TRAINING |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Sl.no | Name of Facility | HW | HWO | TOTAL Participants | TA | DA 400/head | Lunch 150/head | TOTAL |
| 1 | Aizawl East | 139 | 31 | 170 | 61500 | 68000 | 25500 | 155000 |
| 2 | Aizawl west | 147 | 36 | 183 | 13350 | 73200 | 27450 | 114000 |
| 3 | Champhai | 63 | 21 | 84 | 55800 | 33600 | 12600 | 102000 |
| 4 | Hnahthial | 39 | 10 | 49 | 50050 | 19600 | 7350 | 77000 |
| 5 | Khawzawl | 38 | 14 | 52 | 34400 | 20800 | 7800 | 63000 |
| 6 | Kolasib | 57 | 21 | 78 | 30100 | 31200 | 11700 | 73000 |
| 7 | Lawngtlai | 47 | 20 | 67 | 145150 | 26800 | 10050 | 182000 |
| 8 | Lunglei | 105 | 42 | 147 | 126150 | 58800 | 22050 | 207000 |
| 9 | Mamit | 72 | 31 | 103 | 89350 | 41200 | 15450 | 146000 |
| 10 | Saitual | 53 | 14 | 67 | 65150 | 26800 | 10050 | 102000 |
| 11 | Serchhip | 74 | 21 | 95 | 63750 | 38000 | 14250 | 116000 |
| 12 | Siaha | 31 | 18 | 49 | 64050 | 19600 | 7350 | 91000 |
| 13 | State |  |  | 180 | 64000 | 72000 | 27000 | 163000 |
| TOTAL |  | 865 | 279 | 1144 |  |  |  | 1591000 |

HSS 19– 204: Scheme: IEC & Printing (Incl. RCH, NDCP, NCD, HSS-Urban, HSS-Rural)

Components – IEC & Printing

Particulars : Printing of MCP Card

| District | Estimated No of Pregnant Women | Total Amount required @Rs. 50/Card (Rs. In Lakhs) |
| --- | --- | --- |
| Aizawl East | 4274 | 213687 |
| Aizawl West | 3166 | 158321 |
| Champhai | 1469 | 73472 |
| Hnahthial | 527 | 26366 |
| Khawzawl | 677 | 33858 |
| Kolasib | 1590 | 79486 |
| Lawngtlai | 2464 | 123223 |
| Lunglei | 2425 | 121246 |
| Mamit | 1805 | 90272 |
| Saitual | 984 | 49220 |
| Serchhip | 1337 | 66869 |
| Siaha | 1146 | 57290 |
| Total | 21866 | 1093309 |

HSS 19– 204: Scheme: IEC & Printing (Incl. RCH, NDCP, NCD, HSS-Urban, HSS-Rural)

Components – IEC & Printing

Particulars: IEC under Maternal Health

ACTIVITY 1 :	Estimated budget for creating and broadcasting of maternal health activities at Local Cable Network - 30000

For Broadcasting - Rs 15000/month x 2 months = Rs 30000

TOTAL = Rs 60,000

ACTIVITY 2 : 	Awareness/outreach programme for each district – 12 district x 1 times = Rs 120000/-

| Item | Rate |
| --- | --- |
| Refreshment (100 people x 50 per head) | 5000 |
| Incentive for Resource person | 2000 |
| Banner | 1000 |
| Contingencies | 2000 |
| Total | 10000 |

HSS 19– 204: Scheme: IEC & Printing (Incl. RCH, NDCP, NCD, HSS-Urban, HSS-Rural)

Components – IEC & Printing

Particulars: Printing of MDR format

Total budget estimated for Printing of MDR formats is Rs40,480/-  tabulated below as:

| Form | Particulars | No. of Pages | No. of copies | Amount per page (in Rs.) | Total amount (in Rs.) |
| --- | --- | --- | --- | --- | --- |
| Form 1 | MDSR Notification form | 2 | 4476 (12 copies each for 373 Subcentres) | 2 | 17904 |
| Form 2 | Block Level MDR Register for All Women’s Death (15-49 years) | 1 | 93 (All facilities PHCs and above) | 100 | 9300 |
| Form 3 | MDR Line Listing Form for All Cases of Maternal Deaths | 1 | 4476 (12 copies each for 373Subcentres) | 2 | 8952 |
| Form 4 | Confidential Facility Based Maternal Death Review Form | 8 | 22 (22 expected MD) | 2 | 352 |
| Form 5 | Verbal Autopsy Questionnaire | 2 | 186 (2 copies each to be kept at 93 facilities) | 2 | 744 |
|  | FOR INVESTIGATION OF MATERNAL DEATHS |  |  |  |  |
|  | Verbal Consent Form | 2 | 93 | 2 | 372 |
|  | Module – I | 3 | 93 | 2 | 558 |
|  | Module – II | 4 | 93 | 2 | 744 |
|  | Module – III | 7 | 93 | 2 | 1302 |
| Form 6 | MDR Case Summary | 3 | 20 | 2 | 120 |
| Template -1 | Minutes of the Meeting of Facility Based Maternal Death | 1 | 22 (22 expected MD) | 2 | 44 |
| Review Committee |  |  |  |  |  |
| Template-2 | Minutes of the Meeting of District Maternal Death Review Committee | 1 | 22 (22 expected MD) | 2 | 44 |
| Template-3 | Minutes of the Maternal Death Review under District Collector/Magistrate | 1 | 22 (22 expected MD) | 2 | 44 |
| TOTAL |  |  |  |  | Rs 40480 |

HSS 19– 204: Scheme: IEC & Printing (Incl. RCH, NDCP, NCD, HSS-Urban, HSS-Rural)

Components – IEC & Printing

Particulars: Printing of Labour room registers

Total budget estimated for Printing of Labour room registers(for all facilities conducting delivery) is Rs.75,000/- (Rupees Seventy-five thousand) only and is tabulated below as:

- Rs. 500 per Register containing 200 pages, 150 nos

- Rs.500 X 150 copies =Rs. 75,000/-

HSS 19– 204: Scheme: IEC & Printing (Incl. RCH, NDCP, NCD, HSS-Urban, HSS-Rural)

Components – IEC & Printing

Particulars: Whiteboard for HWCs  & PMSMA register

Total = Rs 410000 + Rs 63000 = Rs 4,73,000/-

ACTIVITY 1 :	Whiteboard for HWCs/SCs

For important RCH indicator, 205 HWCs in high priority area @ Rs2000 per 1 whiteboard

205 x Rs 2000 = Rs 4,10,000/-

ACTIVITY 2 :	 PMSMA Register: Rs 63,000 /-

Estimated @ Rs. 350 per Register containing 100 pages

Total cost for 180 Registers: Rs. 300 X 180 copies =Rs. 63,000/-

RCH 7 –Sl No 52: Scheme – Anaemia Mukt Bharat

Components – Drugs

Particulars: IFA Tablets for Pregnant & Lactating Mothers

Expected PW - 21866

Total Proposed for PW to be given 1 tablet for 6 months during pregnancy and 3 months post partum (total 270 tab) and additional tablet a day for 30 days for anaemic PW (total 310 tab) with 5% buffer stock @ Rs 0.5/tab= Rs. 34,44,525/-

| sl no | district | expected pregnancy | Expected PW with Anaemia (50%) during pregnancy & post partum (330 tab) | Expected PW without Anaemia (50%) during pregnancy & post partum(270 tab) | 5% Buffer Stock | Total requirement in tab | Total Price @ rs 0.5/tab |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | AizawlEast | 4274 | 705210 | 576990 | 64110 | 1346310 | 673155 |
| 2 | Aizawl west | 3166 | 522390 | 427410 | 47490 | 997290 | 498645 |
| 3 | Champhai | 1469 | 242550 | 198450 | 22050 | 463050 | 231525 |
| 4 | Hnahthial | 527 | 87120 | 71280 | 7920 | 166320 | 83160 |
| 5 | Khawzawl | 677 | 111870 | 91530 | 10170 | 213570 | 106785 |
| 6 | Kolasib | 1590 | 262350 | 214650 | 23850 | 500850 | 250425 |
| 7 | Lawngtlai | 2464 | 406560 | 332640 | 36960 | 776160 | 388080 |
| 8 | Lunglei | 2425 | 400290 | 327510 | 36390 | 764190 | 382095 |
| 9 | Mamit | 1805 | 297990 | 243810 | 27090 | 568890 | 284445 |
| 10 | Saitual | 984 | 162360 | 132840 | 14760 | 309960 | 154980 |
| 11 | Serchhip | 1337 | 220770 | 180630 | 20070 | 421470 | 210735 |
| 12 | Siaha | 1146 | 189090 | 154710 | 17190 | 360990 | 180495 |
|  | State | 21866 | 3608550 | 2952450 | 328050 | 6889050 | 3444525 |

CHILD HEALTH

HSS 17– 202: Scheme: ASHA Incentives (Incl. RCH, NDCP, NCD, HSS-Urban, HSS-Rural)

Components: ASHA Incentive

Particulars: Facility- ASHA Incentives for Home Based New born care (HBNC)programme

Expected live birth for 2026-27 is 19878.  80% of expected live birth is to be visited under HBNC i.e 15902

Total amount for ASHA Incentives for HBNC is Rs.39,75,600 /-

| Sl.No | Districts | No of ASHA | Total amount for ASHA incentives for HBNC @Rs 250 |
| --- | --- | --- | --- |
| 1 | Aizawl East | 129 | 777000 |
| 2 | Aizawl west | 106 | 575800 |
| 3 | Champhai | 71 | 267200 |
| 4 | Hnahthial | 43 | 95800 |
| 5 | Khawzawl | 44 | 123200 |
| 6 | Kolasib | 87 | 289000 |
| 7 | Lawngtlai | 165 | 448000 |
| 8 | Lunglei | 165 | 440800 |
| 9 | Mamit | 82 | 328200 |
| 10 | Saitual | 51 | 179000 |
| 11 | Serchhip | 71 | 243200 |
| 12 | Siaha | 77 | 208400 |
|  | TOTAL | 1091 | 39,75,600 |

HSS 17– 202: Scheme: ASHA Incentives (Incl. RCH, NDCP, NCD, HSS-Urban, HSS-Rural)

Components: ASHA Incentive

Particulars: Facility- ASHA Incentives for Home Based Care for Young Child (HBYC) programme

Expected live birth for 2026-27 is 19878.  80% of expected live birth is to be visited under HBYC i.e 15902

Total amount for ASHA Incentives for HBYC is Rs.39, 75,600 /-

| Sl.No | Districts | No of ASHA | Total amount for ASHA incentives for HBYC @Rs 250 |
| --- | --- | --- | --- |
| 1 | Aizawl East | 129 | 777000 |
| 2 | Aizawl west | 106 | 575800 |
| 3 | Champhai | 71 | 267200 |
| 4 | Hnahthial | 43 | 95800 |
| 5 | Khawzawl | 44 | 123200 |
| 6 | Kolasib | 87 | 289000 |
| 7 | Lawngtlai | 165 | 448000 |
| 8 | Lunglei | 165 | 440800 |
| 9 | Mamit | 82 | 328200 |
| 10 | Saitual | 51 | 179000 |
| 11 | Serchhip | 71 | 243200 |
| 12 | Siaha | 77 | 208400 |
|  | TOTAL | 1091 | 39,75,600 |

RCH 3 - Sno. 24: Scheme – Facility Based Newborn Care

Components: Others including operating costs (OOC)

Particulars: SNCU Data Management

Proposal is for monthly Internet Bill @ Rs 2500 X 12 months X 7 SNCUs (Aizawl East, Aizawl West, Champhai, Lawngtlai, Lunglei, Siaha, Mamit) = Rs. 2,10,000/-

RCH 3 – Sno. 24: Scheme – Facility Based Newborn Care

Components: Drugs and supplies

Particulars: Procurement of Biomedical Equipment under Child Health

Proposal is for procurement of SNCU equipments for 7 SNCUs at Aizawl East, Aizawl West, Champhai, Lunglei, Lawngtlai, Siaha and Mamit districts. The following list of items is submitted for proposal which cannot be met from Recurring cost for SNCU.

| Sl.no | Particulars | Rate | Quantity | Total amount |
| --- | --- | --- | --- | --- |
|  | Radiant warmer | 50000 | 14 | 700000 |
|  | Double Surface LED Phototherapy | 60000 | 14 | 840000 |
|  | Syringe Pump | 40000 | 14 | 560000 |
|  | TOTAL |  |  | 21,00,000/- |

HSS 19– 204: Scheme: IEC & Printing (Incl. RCH, NDCP, NCD, HSS-Urban, HSS-Rural)

Components: IEC & Printing

Particulars: Printing (SNCU Reporting Format).

Proposal is for printing of 7 SNCU stationary items and formats.

| Sl.no | Districts | Amount proposed per year |
| --- | --- | --- |
| 1. | SNCU Aizawl East | 40000 |
| 2. | SNCU Aizawl West | 30000 |
| 3. | SNCU Champhai | 30000 |
| 4. | SNCU Lunglei | 30000 |
| 5. | SNCU Lawngtlai | 30000 |
| 6. | SNCU Siaha | 30000 |
| 7. | SNCU Mamit | 30000 |
|  | Grand total | 2,20,000/- |

RCH 3 – Sno. 24 Scheme – Facility Based Newborn Care

Components: Others including operating costs (OOC)

Particulars: Operating Costs for Special Newborn Care Unit (SNCU)

All 7 SNCUs at Aizawl East, Aizawl West, Champhai, Lunglei, Lawngtlai, Mamit and Siaha Districts are functioning and reporting. Recurring cost for the SNCUs has been proposed as follows: -

| Sno | District | Recurring Cost for 1year (Rs.) |
| --- | --- | --- |
| 1 | Aizawl East | 5,00,000 |
| 2 | Aizawl West | 4,00,000 |
| 3 | Champhai | 3,00,000 |
| 4 | Lawngtlai | 3,00,000 |
| 5 | Lunglei | 3,00,000 |
| 6 | Mamit | 3,00,000 |
| 7 | Saiha | 3,00,000 |
| Total |  | 24,00,000 |

HSS 19– 204: Scheme: IEC & Printing (Incl. RCH, NDCP, NCD, HSS-Urban, HSS-Rural)

Components: IEC & Printing

Particulars: Printing (NBSU Reporting format).

Proposal is for printing of 8 NBSU stationary items and formats.

| Sl.no | Districts | Amount proposed per year |
| --- | --- | --- |
| 1. | NBSU Serchhip | 20000 |
| 2. | NBSU Kolasib | 20000 |
| 3. | NBSU Hnahthial | 20000 |
| 4. | NBSU Khawzawl | 20000 |
| 5. | NBSU Saitual | 20000 |
| 6. | NBSU Vairengte (Kolasib) | 20000 |
| 7. | NBSU Thenzawl (Serchhip) | 20000 |
| 8. | NBSU Kawrthah (Mamit) | 20000 |
|  | Grand total | 1,60,000/- |

RCH 3 – Sno. 24 Scheme – Facility Based Newborn Care

Components: Others including operating costs (OOC)

Particulars: Operating Costs for Newborn Stabilization Unit (NBSU)

8 NBSU has been set up in Mizoram at Kolasib, Serchhip, Saitual, Hnahthial, Khawzawl, Thenzawl, Vairengte and Kawrthah districts. At present, NBSU at Serchhip, Kolasib, Saitual, Hnahthial and Khawzawl district are functional and reporting. Hence, Recurring cost for the 8 NBSU proposed are as follows: -

Rs. 80,000 X 8 NBSUs = Rs. 6, 40,000

| Sl. No | District | Recurring cost for 1 year |
| --- | --- | --- |
| 1. | Serchhip DH | 80,000 |
| 2. | Kolasib DH | 80,000 |
| 3. | Saitual DH | 80,000 |
| 4. | Hnahthial DH | 80,000 |
| 5. | Khawzawl DH | 80,000 |
| 6. | Thenzawl CHC, Serchhip District | 80,000 |
| 7. | Vairengte CHC, Kolasib District | 80,000 |
| 8. | Kawrthah CHC, Mamit District | 80,000 |
| Total |  | Rs. 6,40,000 |

RCH 3 – Sno. 24 Scheme – Facility Based Newborn Care

Components: Others including operating costs (OOC)

Particulars: Operating Costs for Newborn Care Corners (NBCC)

There are 124 NBCCs in the state and the recurring cost for these NBCCs is proposed as follows

Rs. 5,000/- X 124 NBCCs = Rs 6, 20,000/-

No of Newborn Care Corners  (NBCC)

| Sl.No | District | No of NBCC | Total Amount (Rs.5000/facility) |
| --- | --- | --- | --- |
| 1 | Aizawl East | 9 | 45000 |
| 2 | Aizawl west | 8 | 40000 |
| 3 | Champhai | 11 | 55000 |
| 4 | Hnahthial | 9 | 45000 |
| 5 | Khawzawl | 5 | 25000 |
| 6 | Kolasib | 7 | 35000 |
| 7 | Lawngtlai | 17 | 85000 |
| 8 | Lunglei | 19 | 95000 |
| 9 | Mamit | 15 | 75000 |
| 10 | Saitual | 5 | 25000 |
| 11 | Serchhip | 4 | 20000 |
| 12 | Siaha | 15 | 75000 |
| TOTAL |  | 124 | Rs. 6,20,000/- |

| List Of NBCC |  |  |  |  |
| --- | --- | --- | --- | --- |
| S.No | Name of Facility | District | Level of Facility | No of NBCC |
|  | Civil Hospital Aizawl | Aizawl East | L3 | 3 |
|  | Sakawrdai CHC | Aizawl East | L2 | 1 |
|  | Thingsulthliah CHC | Aizawl East | L2 | 1 |
|  | Khawruhlian PHC | Aizawl East | L2 | 1 |
|  | Darlawn PHC | Aizawl East | L2 | 1 |
|  | Zemabawk UPHC | Aizawl East | L1 | 1 |
|  | ITI UPHC | Aizawl East | L1 | 1 |
|  | Zoram Medical College & Hospital | Aizawl West | L3 | 3 |
|  | Kulikawn Sub Divisional Hospital | Aizawl West | L3 | 1 |
|  | Lengpui CHC | Aizawl West | L2 | 1 |
|  | Sairang PHC | Aizawl West | L2 | 1 |
|  | Sialsuk PHC | Aizawl West | L2 | 1 |
|  | Aibawk PHC | Aizawl West | L2 | 1 |
|  | District Hospital Champhai | Champhai | L3 | 2 |
|  | Khawbung PHC | Champhai | L2 | 1 |
|  | Hnahlan PHC | Champhai | L2 | 1 |
|  | Farkawn PHC | Champhai | L2 | 1 |
|  | Bungzung PHC | Champhai | L2 | 1 |
|  | Khuangthing AHWC | Champhai | SC | 1 |
|  | Zokhawthar HWC | Champhai | SC | 1 |
|  | Vaphai AHWC | Champhai | SC | 1 |
|  | Khankawn HWC | Champhai | SC | 1 |
|  | Hmunhmeltha HWC | Champhai | SC | 1 |
|  | Hnahthial DH | Hnahthial | L3 | 2 |
|  | Chhipphir PHC | Hnahthial | L2 | 1 |
|  | Cherhlun PHC | Hnahthial | L2 | 1 |
|  | S Vanlaiphai PHC | Hnahthial | L2 | 1 |
|  | Pangzawl PHC | Hnahthial | L2 | 1 |
|  | Thingsai SC | Hnahthial | SC | 1 |
|  | Muallianpui HWC | Hnahthial | SC | 1 |
|  | Leite HWC | Hnahthial | SC | 1 |
|  | Khawzawl DH | Khawzawl | L3 | 1 |
|  | Biate CHC | Khawzawl | L2 | 1 |
|  | Khawhai PHC | Khawzawl | L2 | 1 |
|  | Kawlkulh PHC | Khawzawl | L2 | 1 |
|  | Sialhawl PHC | Khawzawl | L2 | 1 |
|  | District Hospital Kolasib | Kolasib | L3 | 1 |
|  | Vairengte CHC | Kolasib | L3 | 1 |
|  | Bairabi PHC | Kolasib | L2 | 1 |
|  | Kawnpui PHC | Kolasib | L2 | 1 |
|  | Bilkhawthlir PHC | Kolasib | L2 | 1 |
|  | Saipum HWC | Kolasib | SC | 1 |
|  | Hortoki HWC | Kolasib | SC | 1 |
|  | District Hospital Lawngtlai | Lawngtlai | L3 | 2 |
|  | Chawngte CHC | Lawngtlai | L2 | 2 |
|  | Bungtlang S PHC | Lawngtlai | L2 | 1 |
|  | S Lungpher PHC | Lawngtlai | L2 | 1 |
|  | Sangau PHC | Lawngtlai | L2 | 1 |
|  | Bualpui NG PHC | Lawngtlai | L1 | 1 |
|  | Pangkhua HWC | Lawngtlai | SC | 1 |
|  | Lungtian HWC | Lawngtlai | SC | 1 |
|  | Siachangkawn HWC | Lawngtlai | SC | 1 |
|  | Lungzarhtum HWC | Lawngtlai | SC | 1 |
|  | Paithar AHWC | Lawngtlai | SC | 1 |
|  | Diltlang HWC | Lawngtlai | SC | 1 |
|  | Hmunlai HWC | Lawngtlai | SC | 1 |
|  | Saizawh W HWC | Lawngtlai | SC | 1 |
|  | Kawlchaw HWC | Lawngtlai | SC | 1 |
|  | Civil Hospital Lunglei | Lunglei | L3 | 2 |
|  | Tlabung Sub Divisional Hospital | Lunglei | L3 | 2 |
|  | Bunghmun PHC | Lunglei | L2 | 1 |
|  | Buarpui PHC | Lunglei | L2 | 1 |
|  | Haulawng PHC | Lunglei | L2 | 1 |
|  | Lungsen PHC | Lunglei | L2 | 1 |
|  | Tawipui S PHC | Lunglei | L2 | 1 |
|  | Hrangchalkawn UPHC | Lunglei | L1 | 1 |
|  | Changpui HWC | Lunglei | SC | 1 |
|  | Phairuangkai HWC | Lunglei | SC | 1 |
|  | Mualthuam N HWC | Lunglei | SC | 1 |
|  | Tuichawng AHWC | Lunglei | SC | 1 |
|  | Sertlangpui HWC | Lunglei | SC | 1 |
|  | Thenhlum AHWC | Lunglei | SC | 1 |
|  | Hnahchang/ Zotuithiang HWC | Lunglei | SC | 1 |
|  | Rualalung HWC | Lunglei | SC | 1 |
|  | Lungrang S HWC | Lunglei | SC | 1 |
|  | District Hospital Mamit | Mamit | L3 | 2 |
|  | Kawrthah CHC | Mamit | L3 | 1 |
|  | W Phaileng PHC | Mamit | L2 | 1 |
|  | Marpara PHC | Mamit | L2 | 1 |
|  | Zawlnuam PHC | Mamit | L2 | 1 |
|  | Phuldungsei PHC | Mamit | L1 | 1 |
|  | Rawpuichhip PHC | Mamit | L1 | 1 |
|  | Kawrtethawveng PHC | Mamit | L1 | 1 |
|  | Hriphaw HWC | Mamit | SC | 1 |
|  | Lallen HWC | Mamit | SC | 1 |
|  | Parvatui HWC | Mamit | SC | 1 |
|  | Pukzing HWC | Mamit | SC | 1 |
|  | Rulpuihlim HWC | Mamit | SC | 1 |
|  | W.Bunghmun HWC | Mamit | SC | 1 |
|  | Saitual DH | Saitual | L3 | 1 |
|  | Ngopa CHC | Saitual | L2 | 1 |
|  | Phuaibuang PHC | Saitual | L2 | 1 |
|  | NE Khawdungsei PHC | Saitual | L2 | 1 |
|  | Mimbung PHC | Saitual | L2 | 1 |
|  | District Hospital Serchhip | Serchhip | L3 | 2 |
|  | Thenzawl CHC | Serchhip | L3 | 1 |
|  | Zote S HWC | Serchhip | SC | 1 |
|  | District Hospital Siaha | Siaha | L3 | 2 |
|  | Tuipang/Tipa PHC | Siaha | L2 | 1 |
|  | Phura PHC | Siaha | L2 | 1 |
|  | Chhuarlung (Chhaolo) PHC | Siaha | L2 | 1 |
|  | Zero Point (Amobyu Vaithie) Clinic | Siaha | SC | 1 |
|  | Theiva HWC | Siaha | SC | 1 |
|  | Niawhtlang (Noaotlah) AHWC | Siaha | SC | 1 |
|  | Laki HWC | Siaha | SC | 1 |
|  | Serkawr (Saikao) HWC | Siaha | SC | 1 |
|  | Zawngling (Zyhno) HWC | Siaha | SC | 1 |
|  | Vahai (Vahia) HWC | Siaha | SC | 1 |
|  | Siata HWC | Siaha | SC | 1 |
|  | Chakhang (Chakhei) SC | Siaha | SC | 1 |
|  | Maubawk (Amobyu) HWC | Siaha | SC | 1 |
| TOTAL |  |  |  | 124 |

HSS 19– 204: Scheme: IEC & Printing (Incl. RCH, NDCP, NCD, HSS-Urban, HSS-Rural)

Components: IEC & Printing

Particulars: Printing of IEC materials for National Newborn Week 2026-27

Proposal is for printing of IEC materials for National Newborn Week to be displayed at all level of facilities. State is observing National Newborn Week since 2020 and plan to continue in the coming years.

| Sl.no | Particulars | No. of copies (all level of facilities) | Amount per page | Total amount |
| --- | --- | --- | --- | --- |
| 1. | Breastfeeding poster | 641 | 15 | 9615 |
| 2. | HBNC poster | 641 | 15 | 9615 |
| 3. | Control of diarrhoea | 641 | 15 | 9615 |
| 4. | Newborn care continuum standee | 300 | 500 | 150000 |
| 5. | JSSK standee | 300 | 500 | 150000 |
| Grand Total |  |  |  | Rs. 3,28,845/- |

HSS 16– 201: Scheme: Capacity building incl. training (Incl. RCH, NDCP, NCD, HSS-Urban, HSS-Rural)

Components: Capacity Building including Training

Particulars: Training (NAVJAAT SHISHU SURAKSHA KARYAKRAM (NSSK))

NSSK Training for CHO, Staff Nurses, HWO & ANM

Planned for 1 batch of Staff Nurses, HWO & ANM for in @Rs. 231000/batch

1. Target Load			= 20

2. No of Batches		= 1

3. Participants per batch	= 20

4. Duration of Training	= 2 Days

| Components | Rate/day (Rs) | No of days | Participants/ batch | Amount (Rs) |
| --- | --- | --- | --- | --- |
| DA for trainees | 700 | 2 | 20 | 28000 |
| Honorarium of Resource Person | 2000 | 2 | 2 | 8000 |
| Vehicle hiring for trainer | 500 | 2 | 2 | 2000 |
| Hall rent | 2000 |  | 11 | 22000 |
| Incidental expenditure | 200 |  | 20 | 4000 |
| Training Modules | 1000 |  | 20 | 20000 |
| TA for trainees | 3000 |  | 20 | 60000 |
| Working Lunch, Tea & Snacks | 300 | 2 | 25 | 15000 |
| Accommodation for trainees | 1000 | 3 | 20 | 60000 |
| DA for support staffs | 500 | 2 | 2 | 2000 |
| Institutional overhead |  |  |  | 10000 |
| TOTAL |  |  |  | 231000 |

Total Budget for 4 batches of NSSK for CHO, SN, HWO & ANM= Rs. 231000

HSS 16– 201: Scheme: Capacity building incl. training (Incl. RCH, NDCP, NCD, HSS-Urban, HSS-Rural)

Components: Capacity Building including Training

Particulars: 4 days training on Facility Based Newborn Care (4 Pediatricians / MO & 6 Nursing Officers)

Training on Facility Based Newborn Care (FBNC) is proposed for 4 Pediatricians / Medical Officers and 6 Staff Nurses posted at SNCU/NBSU/NBCC. Training is planned to be undergone outside Mizoram since state does not have State Resource Centre (SRC).

1. Target Load			= 10

2. No of Batches		= 1

3. Participants per batch	= 10

4. Duration of Training           = 4 days

| Components | Rate/day (Rs) | No of days | Participants/batch | Amount (Rs) |
| --- | --- | --- | --- | --- |
| TA for trainees | 20000 | - | 10 | 200000 |
| DA for trainees | 1000 | 6 | 10 | 60000 |
| Fooding for trainees | 2000 | 6 | 10 | 120000 |
| Accommodation for trainees | 1000 | 6 | 10 | 60000 |
| Institutional overhead |  |  |  | 25000 |
| Total |  |  |  | 4,65,000 |

Total Budget for 1 batch = Rs. 4, 65,000/-

HSS 16– 201: Scheme: Capacity building incl. training (Incl. RCH, NDCP, NCD, HSS-Urban, HSS-Rural)

Components: Capacity Building including Training

Particulars: FBNC Training (2 weeks observership for FBNC)

Ongoing. Training is proposed for 6 Nursing Officers and 4 Paediatrician/ Medical Officers posted at SNCU/NBSU/NBCC on FBNC. Training is planned to be undergone outside the state of Mizoram. Observership will be a continuation of 4 days FBNC training.

1. Target Load			= 10

2. No of Batches		= 1

3. Participants per batch	= 10

4. Duration of Training	= 14 days

| Components | Rate/day (Rs) | No of days | Participants/batch | Amount (Rs) |
| --- | --- | --- | --- | --- |
| Fooding for trainees | 2000 | 14 | 10 | 280000 |
| DA for trainees | 1000 | 14 | 10 | 140000 |
| Accommodation for trainees | 1000 | 15 | 10 | 150000 |
| Total |  |  |  | 570000 |

Total Budget for 10 participants = Rs. 5, 70,000/-

HSS 16– 201: Scheme: Capacity building incl. training (Incl. RCH, NDCP, NCD, HSS-Urban, HSS-Rural)

Components: Capacity Building including Training

Particulars: Newborn Stablilisation Unit (NBSU) Training for Paediatrician

Planned for training of 2 Paediatrician from Khawzawl leh Saitual DH at the State Level.

1. Target Load			= 2

2. No of Batches		= 1

3. Participants per batch	= 2

4. Duration of Training	= 3 Days

| Components | Rate/day (Rs) | No of days | Participants/batch | Amount (Rs) |
| --- | --- | --- | --- | --- |
| DA for trainees | 1000 | 3 | 2 | 6000 |
| Honorarium of Resource Person | 2000 | 3 | 2 | 12000 |
| Vehicle hiring for trainer | 500 | 3 | 2 | 3000 |
| Hall rent | 2000 | 3 | 1 | 6000 |
| Incidental expenditure | 200 | 1 | 3 | 600 |
| Training Modules | 1000 | 1 | 3 | 3000 |
| TA for trainees | 3000 | 1 | 2 | 6000 |
| Working Lunch, Tea & Snacks | 300 | 3 | 4 | 3600 |
| Accommodation for trainees | 1000 | 4 | 2 | 8000 |
| DA for support staffs | 500 | 2 | 2 | 2000 |
| Institutional overhead |  |  |  | 9800 |
| Total |  |  |  | 60,000 |

Proposal for NBSU Paediatrician = Rs. 60,000/-

HSS 16– 201: Scheme: Capacity building incl. training (Incl. RCH, NDCP, NCD, HSS-Urban, HSS-Rural)

Components: Capacity Building including Training

Particulars: Newborn Stablilisation Unit (NBSU) Training for NBSU Nursing Officer

Proposal is for training of 2 Nursing Officers from Saitual and Khawzawl DH at State Level.

1. Target Load			= 2

2. No of Batches		= 1

3. Participants per batch	= 2

4. Duration of Training   	= 3 days

| Components | Rate/day (Rs) | No of days | Participants/batch | Amount (Rs) |
| --- | --- | --- | --- | --- |
| DA for trainees | 700 | 3 | 2 | 4200 |
| Honorarium of Resource Person | 2000 | 3 | 2 | 12000 |
| Vehicle hiring for trainer | 500 | 3 | 2 | 3000 |
| Hall rent | 2000 | 3 | 1 | 6000 |
| Incidental expenditure | 200 | 1 | 6 | 1200 |
| Training Modules | 1000 | 1 | 3 | 3000 |
| TA for trainees | 3000 | 1 | 2 | 6000 |
| Working Lunch, Tea & Snacks | 300 | 3 | 4 | 3600 |
| Accommodation for trainees | 1000 | 4 | 2 | 8000 |
| DA for support staffs | 500 | 2 | 2 | 2000 |
| Institutional overhead |  |  |  | 6000 |
| Total |  |  |  | 55000 |

Total Budget for NBSU for Nursing Officers = Rs. 55,000/-

RCH 3 – 25: Scheme – Child Death Review (CDR)

Components: Surveillance, Research, Review, Evaluation (SRRE)

Particulars: Child Death Review (CDR)

Child Death Review (CDR) is a strategy to understand the geographical variation in causes of child deaths and thereby initiating specific child health interventions. Analysis of child deaths provides information about the medical causes of death, helps to identify the gaps in health service delivery and social factors that contribute to child deaths. This information can be used to adopt corrective measures and fill the gaps in community and facility level service delivery. With uniform CDR process and formats across the states, information can be compared over a period of time and common factors identified and addressed through the National Programme. This contributes to overall improvement in quality of care and reducing child mortality.

Some definition under Child death is:

Neonatal deaths: Neonatal deaths are deaths occurring during the neonatal period, commencing at birth and ending 28 completed days after birth

Post-Neonatal deaths: Deaths occurring from 29 days of life to under one year are called post-neonatal deaths

Infant deaths: Deaths of children less than 1 year of age

Child deaths: Deaths of children less than 5 years of age

Still Birth: Still birth is the birth of a new born after 20 completed weeks of gestation, weighing 500gm or more, when the baby does not breathe or show any sign of life after delivery

Calculation and estimated budget for CDR is tabulated below:

- Community Audit

  - ASHA Incentive @ Rs. 50

  - ANM Incentive @ Rs. 100

= Rs. 150 x 180 cases of Under 5 Death = Rs. 27000/-

- TA for Deceased 1 Family Members @ Rs. 100 = Rs. 100/-

Community Audit Team @ Rs. 500

= Rs. 600 X 100 cases = Rs. 60000 /-

- Meeting Expense for the monthly CDR to be held

Total Budget = Rs. 27000/- + Rs. 60000/- = Rs. 87000/-

| Sl No | District | No of expected U5 Deaths | Fund for ASHA Incentive @Rs 50 per case | Fund for FBIR incentives to ANMs @Rs.100 per case | No of expected U5 Child Death audit | Fund for Verbral autopsy @Rs.500 per case | TA for Deceased Family @ 100 per case | Total Amount (Rs) |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Aizawl East | 30 | 1500 | 3000 | 15 | 7500 | 1500 | 13500 |
| 2 | Aizawl west | 20 | 1000 | 2000 | 10 | 5000 | 1000 | 9000 |
| 3 | Champhai | 20 | 1000 | 2000 | 10 | 5000 | 1000 | 9000 |
| 4 | Hnahthial | 6 | 300 | 600 | 6 | 3000 | 600 | 4500 |
| 5 | Khawzawl | 6 | 300 | 600 | 6 | 3000 | 600 | 4500 |
| 6 | Kolasib | 14 | 700 | 1400 | 7 | 3500 | 700 | 6300 |
| 7 | Lawngtlai | 20 | 1000 | 2000 | 10 | 5000 | 1000 | 9000 |
| 8 | Lunglei | 20 | 1000 | 2000 | 10 | 5000 | 1000 | 9000 |
| 9 | Mamit | 14 | 700 | 1400 | 7 | 3500 | 700 | 6300 |
| 10 | Saitual | 6 | 300 | 600 | 6 | 3000 | 600 | 4500 |
| 11 | Serchhip | 4 | 200 | 400 | 3 | 1500 | 300 | 2400 |
| 12 | Siaha | 20 | 1000 | 2000 | 10 | 5000 | 1000 | 9000 |
|  | TOTAL | 180 | 9000 | 18000 | 100 | 50000 | 10000 | 87000 |

HSS 19– 204: Scheme: IEC & Printing (Incl. RCH, NDCP, NCD, HSS-Urban, HSS-Rural)

Components: IEC & Printing

Particulars: Printing of CDR Reporting Format

| Form No | Particulars | No. of copies | Pages | Amount per page | Total Amount |
| --- | --- | --- | --- | --- | --- |
| Form 1 | Notification Card | 546 | 2 | 2 | 2184 |
| Form 2 | First Brief Investigation Report | 398 | 3 | 2 | 2388 |
| Form 3 a | Community Audit - Neonatal | 160 | 5 | 2 | 1600 |
| Form 3 b | Community Audit - Post Neonatal | 238 | 5 | 2 | 2380 |
| Form 3 c | Community Audit - Social Autopsy form | 398 | 4 | 2 | 3184 |
| Form 4 a | Facility Based - Neonatal | 398 | 4 | 2 | 3184 |
| Form 4 b | Facility Based - Post Neonatal | 398 | 5 | 2 | 3980 |
| Form 5 a | Block and District Level line listing | 188 | 1 | 2 | 376 |
| Form 5 b | District Level Reporting Form | 432 | 1 | 2 | 864 |
| Form 5 c | Facility Level Reporting Form | 1000 | 1 | 2 | 2000 |
| Form 5 d | State Level Reporting Form | 30 | 1 | 2 | 60 |
| TOTAL |  |  |  |  | 22200 |

RCH 3 – 26: Scheme – SAANS

Components: Others including operating costs (OOC)

Particulars: State/District Level Launch event of World Pneumonia Day 2026-27

|  | DISTRICT | Radio Jingles(Rs) | News paper advertisement on NDD(Rs) | TV spots/ scrolls(Rs) | Inauguration Event(Rs) | Total Budget for media Activities |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Aizawl East | 0 | 0 | 0 | 10000 | 10000 |
| 2 | Aizawl west | 0 | 0 | 0 | 10000 | 10000 |
| 3 | Champhai | 0 | 0 | 0 | 10000 | 10000 |
| 4 | Hnahthial | 0 | 0 | 0 | 10000 | 10000 |
| 5 | Khawzawl | 0 | 0 | 0 | 10000 | 10000 |
| 6 | Kolasib | 0 | 0 | 0 | 10000 | 10000 |
| 7 | Lawngtlai | 0 | 0 | 0 | 10000 | 10000 |
| 8 | Lunglei | 0 | 0 | 0 | 10000 | 10000 |
| 9 | Mamit | 0 | 0 | 0 |  |  |
| 10 | Saitual | 0 | 0 | 0 | 10000 | 10000 |
| 11 | Serchhip | 0 | 0 | 0 | 10000 | 10000 |
| 12 | Siaha | 0 | 0 | 0 | 10000 | 10000 |
| 13 | State | 33000 | 10000 | 42000 | 45000 | 1,30,000 |
|  | Total | 33000 | 10000 | 42000 | 165000 | 2, 50,000 |

HSS 19– 204: Scheme: IEC & Printing (Incl. RCH, NDCP, NCD, HSS-Urban, HSS-Rural)

Components: IEC & Printing

Particulars: IEC/ BCC Campaign of SAANS Program

IEC activities proposed @Rs.30, 000/district for 12 Districts = Rs. 3, 60,000/- and for State = Rs.2, 30,000 /- Total= Rs.5, 90,000/-

| Sl No. | District | Radio Jingles | Local Newspaper Advertisement on SAANS Campaign | TV Spots/scrolls (Rs) | Talk show on SAANS Campaign at local cable TV | Bulk WhatsApp Message (Rs.1.8/msgx 50000msg) | Total Budget for IEC/BCC |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1. | Aizawl East |  | 5000 | 15000 | 10000 |  | 30,000 |
| 2. | Aizawl west |  | 5000 | 15000 | 10000 |  | 30000 |
| 3. | Champhai |  | 5000 | 15000 | 10000 |  | 30000 |
| 4. | Hnahthial |  | 5000 | 15000 | 10000 |  | 30000 |
| 5. | Khawzawl |  | 5000 | 15000 | 10000 |  | 30,000 |
| 6. | Kolasib |  | 5000 | 15000 | 10000 |  | 30000 |
| 7. | Lawngtlai |  | 5000 | 15000 | 10000 |  | 30000 |
| 8. | Lunglei |  | 5000 | 15000 | 10000 |  | 30000 |
| 9. | Mamit |  | 5000 | 15000 | 10000 |  | 30000 |
| 10. | Saitual |  | 5000 | 15000 | 10000 |  | 30000 |
| 11. | Serchhip |  | 5000 | 15000 | 10000 |  | 30000 |
| 12. | Siaha |  | 5000 | 15000 | 10000 |  | 30000 |
| 13. | State | 30,000 | 50,000 | 60000 | 0 | 90,000 | 2,30,000 |
|  | Total | 30,000 | 1,10,000 | 2,40,000 | 1,20,000 | 90,000 | 5,90,000 |

HSS 16– 201: Scheme: Capacity building incl. training (Incl. RCH, NDCP, NCD, HSS-Urban, HSS-Rural)

Components: Capacity building including training

Particulars: TOT on Integrated Management of Neonatal and Childhood Illness (IMNCI)

Proposal is for training of TOT on IMNCI at National Level. 2 Medical Officers/Paediatricians have been identified as Master Trainers and have undergone training on IMNCI & F-IMNCI. However, these Master trainers are all from one Institution/facility and posted in different administrative and technical fields and cannot be utilized efficiently due to shortage of manpower. Therefore, new Master Trainers for IMNCI & F-IMNCI will be identified and proposal for training is hereby submitted for TOT.

1. Target Load			= 2

2. No of Batches		= 1

3. Participants per batch	= 2

4. Duration of Training	= 5 days

Total Budget for 1 batch = Rs. 2, 83,500/-

| Components | Rate/day (Rs) | No of days | Participants/batch | Amount (Rs) |
| --- | --- | --- | --- | --- |
| TA for trainees | 30000 | 2 | 2 | 120000 |
| Food for trainees | 2000 | 7 | 2 | 28000 |
| Accommodation for trainees | 5000 | 7 | 2 | 70000 |
| DA for trainees | 2000 | 7 | 2 | 28000 |
| Institutional overhead |  |  |  | 37500 |
| Total |  |  |  | 2,83,500 |

HSS 16– 201: Scheme: Capacity building incl. training (Incl. RCH, NDCP, NCD, HSS-Urban, HSS-Rural)

Components: Capacity building including training

Particulars: Integrated Management of Neonatal and Childhood Illness (IMNCI) Training for ANM

IMNCI Training for ANM, SN & HWO from all districts

1. Target Load			= 20

2. No of Batches		= 1

3. Participants per batch 	= 20

4. Duration of Training	= 5 days

Budget for 1 batch		 = Rs. 4,00,000/-

| Components | Rate/day (Rs) | No of days | Participants/ batch | Amount (Rs) |
| --- | --- | --- | --- | --- |
| DA for trainees | 700 | 6 | 20 | 84000 |
| Honorarium of Resource Person | 2000 | 5 | 2 | 20000 |
| Vehicle hiring for trainer | 500 | 5 | 2 | 5000 |
| Hall rent | 2000 | 5 |  | 10000 |
| Incidental expenditure | 200 |  | 22 | 4400 |
| Training Modules | 2000 | 1 | 22 | 44000 |
| TA for trainees | 2000 |  | 20 | 40000 |
| Working Lunch, Tea & Snacks | 300 | 5 | 25 | 37500 |
| Accommodation for trainees | 1000 | 6 | 20 | 120000 |
| DA for support staffs | 500 | 5 | 2 | 5000 |
| Institutional overhead |  |  |  | 30100 |
| TOTAL |  |  |  | 4,00,000 |

TOTAL Proposal for IMNCI Training = Rs. 4, 00,000/-

HSS 16– 201: Scheme: Capacity building incl. training (Incl. RCH, NDCP, NCD, HSS-Urban, HSS-Rural)

Components: Capacity building including training

Particulars: TOT on Facility- Integrated Management of Neonatal and Childhood Illness (F-IMNCI)

Proposal is for training of TOT on F-IMNCI at National Level. 2 Medical Officers/Pediatricians have been identified as Master Trainers and have undergone training on IMNCI & F-IMNCI. However, these Master trainers are all from one Institution/facility and posted in different administrative and technical fields and cannot be utilized efficiently. Therefore, new Master Trainers for IMNCI & F-IMNCI will be identified and proposal for training is hereby submitted for TOT.

1. Target Load			= 2

2. No of Batches		= 1

3. Participants per batch	= 2

4. Duration of Training	              = 5 days

Total Budget for 1 batch = Rs. 2, 83,500/-

| Components | Rate/day (Rs) | No of days | Participants/batch | Amount (Rs) |
| --- | --- | --- | --- | --- |
| TA for trainees | 30000 | 2 | 2 | 120000 |
| Food for trainees | 2000 | 7 | 2 | 28000 |
| Accommodation for trainees | 5000 | 7 | 2 | 70000 |
| DA for trainees | 2000 | 7 | 2 | 28000 |
| Institutional overhead |  |  |  | 37500 |
| Total |  |  |  | 2,83,500 |

HSS 16– 201: Scheme: Capacity building incl. training (Incl. RCH, NDCP, NCD, HSS-Urban, HSS-Rural)

Components: Capacity building including training

Particulars: Facility- Integrated Management of Neonatal and Childhood Illness (F-IMNCI) Training for Medical Officers

Planned for Medical Officers@Rs.5,75,000/batch

1. Target Load			= 20

2. No of Batches		= 1

3. Participants per batch	= 20

4. Duration of Training	= 5 days

| Components | Rate/day (Rs) | No of days | Participants/ batch | Amount (Rs) |
| --- | --- | --- | --- | --- |
| DA for trainees | 1000 | 6 | 20 | 120000 |
| Honorarium of Resource Person | 2000 | 5 | 2 | 20000 |
| Vehicle hiring for trainer | 500 | 5 | 2 | 5000 |
| Hall rent | 2000 | 5 |  | 10000 |
| Incidental expenditure | 200 |  | 22 | 4400 |
| Training Modules | 2000 |  | 22 | 44000 |
| TA for trainees | 8000 |  | 20 | 160000 |
| Working Lunch, Tea & Snacks | 300 | 5 | 25 | 37500 |
| Accommodation for trainees | 1000 | 6 | 20 | 122000 |
| DA for support staffs | 500 | 5 | 2 | 5000 |
| Institutional overhead |  |  |  | 47100 |
| TOTAL |  |  |  | 5,75,000 |

Total proposal for 1 batch of FIMNCI for MO = Rs. 5, 75,000/-

HSS 16– 201: Scheme: Capacity building incl. training (Incl. RCH, NDCP, NCD, HSS-Urban, HSS-Rural)

Components: Capacity building including training

Particulars: Facility- Integrated Management of Neonatal and Childhood Illness (F-IMNCI) Training for Nursing Officers

Planned for Staff Nurses @Rs.4, 20,000/batch

1. Target Load			= 20

2. No of Batches		= 1

3. Participants per batch	= 20

4. Duration of Training	= 5 days

| Components | Rate/day (Rs) | No of days | Participants/ batch | Amount (Rs) |
| --- | --- | --- | --- | --- |
| DA for trainees | 700 | 6 | 20 | 84000 |
| Honorarium of Resource Person | 2000 | 5 | 2 | 20000 |
| Vehicle hiring for trainer | 500 | 5 | 2 | 5000 |
| Hall rent | 2000 |  | 5 | 10000 |
| Incidental expenditure | 200 |  | 22 | 4400 |
| Training Modules | 2000 |  | 22 | 44000 |
| TA for trainees | 3000 |  | 20 | 60000 |
| Working Lunch, Tea & Snacks | 300 | 5 | 25 | 37500 |
| Accommodation for trainees | 1000 | 6 | 20 | 120000 |
| DA for support staffs | 500 | 5 | 2 | 5000 |
| Institutional overhead |  |  |  | 30100 |
| TOTAL |  |  |  | 4,20,000 |

Total proposal for 1 batch of FIMNCI for SN = Rs. 4, 20,000/-

RCH 3 – 28: Scheme: Janani Shishu Suraksha Karyakram (JSSK) (excluding transport)

Component: Drugs

Particulars: JSSK drugs and consumables CH JSSK

Drugs and consumables proposed for 1988 sick infants in all districts @Rs.500 = Rs.9, 94,500/- i.e. Rs.9, 94,000 lakhs.

District wise breakup for Drugs and consumables of Expected Sick Infant and budget is given below:

| Sl.no | Name of District | No. of Expected Sick Infant | (Unit Cost i.e Rs.500) x (No. of Expected Sick Infant) in Rs. |
| --- | --- | --- | --- |
| 1 | Aizawl East | 389 | 194500 |
| 2 | Aizawl west | 288 | 144000 |
| 3 | Champhai | 134 | 67000 |
| 4 | Hnahthial | 48 | 24000 |
| 5 | Khawzawl | 62 | 31000 |
| 6 | Kolasib | 145 | 72500 |
| 7 | Lawngtlai | 224 | 112000 |
| 8 | Lunglei | 220 | 110000 |
| 9 | Mamit | 164 | 82000 |
| 10 | Saitual | 89 | 44500 |
| 11 | Serchhip | 122 | 61000 |
| 12 | Siaha | 104 | 52000 |
| TOTAL |  | 1988 | 994000 |

RCH 3 28 Free Diagnostic for sick infants

Scheme: Janani Shishu Suraksha Karyakram (JSSK) (excluding transport)

Component:  Diagnostics (Consumables, PPP, Sample Transport)

Proposed for Diagnostics of 1988 sick infants in all 9 districts @Rs.300 = Rs. 5, 96,700/- i.e. Rs.5.97 lakhs.

District wise breakup for Diagnostics of Expected Sick Infant and budget is given below:

| Sl.no | Name of District | No. of Expected Sick Infant | (Unit Cost Rs.300) x (No. of Expected Sick Infant) in Rs. |
| --- | --- | --- | --- |
| 1 | Aizawl East | 389 | 116700 |
| 2 | Aizawl west | 288 | 86400 |
| 3 | Champhai | 134 | 40200 |
| 4 | Hnahthial | 48 | 14400 |
| 5 | Khawzawl | 62 | 18600 |
| 6 | Kolasib | 145 | 43500 |
| 7 | Lawngtlai | 224 | 67200 |
| 8 | Lunglei | 220 | 66000 |
| 9 | Mamit | 164 | 49200 |
| 10 | Saitual | 89 | 26700 |
| 11 | Serchhip | 122 | 36600 |
| 12 | Siaha | 104 | 31200 |
| TOTAL |  | 1988 | 596700 |

RCH 3 – 29: Scheme: Janani Shishu Suraksha Karyakram (JSSK) – transport

Component: Others Operating Costs (OOC)

Particulars: Free Referral Transport – JSSK for Sick Infant

Proposed for 1988 expected sick infants in all districts @Rs.1000 =Rs.19, 89,000/- i.e. 19.89 Lakhs

District wise breakup for Free Referral Transport for Expected Sick Infant and budget is given below:

| Sl.no | Name of District | No. of Expected Sick Infant | (Unit Cost Rs.1000) x (No. of Expected Sick Infant) in Rs. |
| --- | --- | --- | --- |
| 1 | Aizawl East | 389 | 389000 |
| 2 | Aizawl west | 288 | 288000 |
| 3 | Champhai | 134 | 134000 |
| 4 | Hnahthial | 48 | 48000 |
| 5 | Khawzawl | 62 | 62000 |
| 6 | Kolasib | 145 | 145000 |
| 7 | Lawngtlai | 224 | 224000 |
| 8 | Lunglei | 220 | 220000 |
| 9 | Mamit | 164 | 164000 |
| 10 | Saitual | 89 | 89000 |
| 11 | Serchhip | 122 | 122000 |
| 12 | Siaha | 104 | 104000 |
| TOTAL |  | 1988 | 1989000 |

HSS 16– 201: Scheme: Capacity building incl. training (Incl. RCH, NDCP, NCD, HSS-Urban, HSS-Rural)

Components: Capacity building including training

Particulars: Half Day Orientation on National Deworming Day (NDD)

Total amount for Half day orientation training on NDD (2 rounds): Rs. 24200 x 2= Rs. 4, 84,000 /-

| Sl No | DISTRICT | No of ANM to be trained | No of teachers to be trained from Govt School | No of teachers to be trained from Pvt School | No of teachers to be trained from all School | Total to be trained under district | Rate per participant | Total Amount req for Training |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Aizawl East | 136 | 418 | 189 | 607 | 743 | 100 | 37150 |
| 2 | Aizawl west | 64 | 241 | 243 | 484 | 548 | 100 | 27400 |
| 3 | Champhai | 50 | 241 | 29 | 270 | 320 | 100 | 16000 |
| 4 | Hnahthial | 17 | 100 | 27 | 127 | 144 | 100 | 7200 |
| 5 | Khawzawl | 24 | 92 | 37 | 129 | 153 | 100 | 7650 |
| 6 | Kolasib | 32 | 205 | 73 | 278 | 310 | 100 | 15500 |
| 7 | Lawngtlai | 40 | 457 | 126 | 583 | 624 | 100 | 31200 |
| 8 | Lunglei | 66 | 447 | 120 | 567 | 632 | 100 | 31600 |
| 9 | Mamit | 52 | 404 | 99 | 503 | 555 | 100 | 27750 |
| 10 | Saitual | 38 | 150 | 47 | 197 | 235 | 100 | 11750 |
| 11 | Serchhip | 42 | 162 | 59 | 221 | 263 | 100 | 13150 |
| 12 | Siaha | 31 | 252 | 30 | 282 | 313 | 100 | 15650 |
|  | Total | 592 | 3169 | 1079 | 4248 | 4840 |  | 242000 |

HSS 17– 202: Scheme: ASHA Incentives (Incl. RCH, NDCP, NCD, HSS-Urban, HSS-Rural)

Components: ASHA Incentive

Particulars: ASHA incentives for National Deworming Day (NDD) for mobilizing beneficiaries for NDD (2 rounds)

Rs.109100 x 2 = Rs. 218200 /-

| Sl.No | Districts | No of ASHA | Amount for incentives for NDD for mobilising school children @Rs 100 per ASHA |
| --- | --- | --- | --- |
| 1 | Aizawl East | 129 | 12900 |
| 2 | Aizawl west | 106 | 10600 |
| 3 | Champhai | 71 | 7100 |
| 4 | Hnahthial | 43 | 4300 |
| 5 | Khawzawl | 44 | 4400 |
| 6 | Kolasib | 87 | 8700 |
| 7 | Lawngtlai | 165 | 16500 |
| 8 | Lunglei | 165 | 16500 |
| 9 | Mamit | 82 | 8200 |
| 10 | Saitual | 51 | 5100 |
| 11 | Serchhip | 71 | 7100 |
| 12 | Siaha | 77 | 7700 |
|  | TOTAL | 1091 | 109100 |

HSS 19– 204: Scheme: IEC & Printing (Incl. RCH, NDCP, NCD, HSS-Urban, HSS-Rural)

Components: IEC & Printing

Particulars: IEC Activities and Launching of NDD for 2 rounds

1. Media Activities and Launching under National Deworming Day

| Sl No. | DISTRICT | Radio Jingles (Rs) | Newspaper advertisement on NDD(Rs) | TV spots/ scrolls (Rs) | Inauguration Event (Rs) | Total Budget for media Activities for 1 Round | Total Budget for media Activities for 2 Rounds |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Aizawl East | 0 |  |  | 10000 | 10000 | 20000 |
| 2 | Aizawl west | 0 |  |  | 10000 | 10000 | 20000 |
| 3 | Champhai | 0 |  |  | 10000 | 10000 | 20000 |
| 4 | Hnahthial | 0 |  |  | 10000 | 10000 | 20000 |
| 5 | Khawzawl | 0 |  |  | 10000 | 10000 | 20000 |
| 6 | Kolasib | 0 |  |  | 10000 | 10000 | 20000 |
| 7 | Lawngtlai | 0 |  |  | 10000 | 10000 | 20000 |
| 8 | Lunglei | 0 |  |  | 10000 | 10000 | 20000 |
| 9 | Mamit | 0 |  |  | 10000 | 10000 | 20000 |
| 10 | Saitual | 0 |  |  | 10000 | 10000 | 20000 |
| 11 | Serchhip | 0 |  |  | 10000 | 10000 | 20000 |
| 12 | Siaha | 0 |  |  | 10000 | 10000 | 20000 |
| 13 | State | 33000 | 10000 | 42000 | 50000 | 135000 | 270000 |
|  | Total | 33000 | 10000 | 42000 | 170000 | 255000 | 510000 |

HSS 19– 204: Scheme: IEC & Printing (Incl. RCH, NDCP, NCD, HSS-Urban, HSS-Rural)

Components: IEC & Printing

Particulars: Printing of IEC materials and monitoring formats for 2 Rounds of National De-worming Day

Total amount proposed:

NDD Reporting formats – Rs.1, 12,168/-

NDD Training Handbook – Rs. 3, 85,000/-

NDD IEC Materials – Rs.66, 690/-

Total: Rs. 5, 98,858/-

1. NDD Formats

| District | Printing of NDD Anganwadi Reporting Format (3 pages) | Printing of NDD ASHA Reporting Format (2 pages) | Printing of NDD School Reporting Format(3 pages) | Printing of NDD Common Reporting Format (1 page) | Printing of NDD Monitoring Form (2 pages) | Printing of NDD college/institute format (2 pages) | Total No of Format to be printed | Cost of Printing of Formats @ Rs.2 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Aizawl East | 756 | 774 | 1821 | 81 | 100 | 50 | 3582 | 7164 |
| Aizawl west | 744 | 636 | 1452 | 75 | 100 | 50 | 3057 | 6114 |
| Champhai | 432 | 426 | 810 | 52 | 100 | 50 | 1870 | 3740 |
| Hnahthial | 345 | 258 | 381 | 27 | 100 | 50 | 1161 | 2322 |
| Khawzawl | 298 | 264 | 387 | 35 | 100 | 50 | 1134 | 2268 |
| Kolasib | 411 | 522 | 424 | 44 | 100 | 50 | 1551 | 3102 |
| Lawngtlai | 906 | 990 | 1749 | 49 | 100 | 50 | 3844 | 7688 |
| Lunglei | 912 | 990 | 1701 | 83 | 100 | 50 | 3836 | 7672 |
| Mamit | 846 | 492 | 1509 | 61 | 100 | 50 | 3058 | 6116 |
| Saitual | 393 | 306 | 591 | 45 | 100 | 50 | 1485 | 2970 |
| Serchhip | 480 | 426 | 663 | 46 | 100 | 50 | 1765 | 3530 |
| Siaha | 198 | 462 | 846 | 43 | 100 | 50 | 1699 | 3398 |
| Total | 6721 | 6546 | 12334 | 641 | 1200 | 600 | 28042 | 56084 |
| Total amount proposed for 2 rounds NDD: Rs.56084 x 2 = Rs.1,12,168/- |  |  |  |  |  |  |  |  |

      - Printing of NDD ASHA, Anganwadi & Teacher’s Training Handbook

| Sl No | DISTRICT | Printing of ASHA, Anganwadi & Teacher’s Training NDD Handbook | Cost of Printing of NDD Handbook @ Rs. 70 (Rs.3.5@20pages) |
| --- | --- | --- | --- |
| 1 | Aizawl East | 250 | 17500 |
| 2 | Aizawl west | 250 | 17500 |
| 3 | Champhai | 250 | 17500 |
| 4 | Hnahthial | 200 | 14000 |
| 5 | Khawzawl | 200 | 14000 |
| 6 | Kolasib | 200 | 14000 |
| 7 | Lawngtlai | 250 | 17500 |
| 8 | Lunglei | 300 | 21000 |
| 9 | Mamit | 250 | 18000 |
| 10 | Saitual | 200 | 14000 |
| 11 | Serchhip | 200 | 14000 |
| 12 | Siaha | 200 | 14000 |
|  | Total | 2750 | Rs.1,92,500 /- |
| Total amount for 2 rounds of NDD Teacher, Anganwadi and ASHA Handbook- Rs.1,92,500 x 2 = Rs.3,85,000 /- |  |  |  |

      - IEC Print Material for NDD

| NDD IEC Materials |  |  |  |
| --- | --- | --- | --- |
| Sl No | District | No of Health Facilities | Cost of printing NDD posters for Health facility @Rs.15x 3 Poster |
| 1. | Aizawl East | 81 | 3645 |
| 2. | Aizawl west | 75 | 3375 |
| 3. | Champhai | 52 | 2340 |
| 4. | Hnahthial | 27 | 1215 |
| 5. | Khawzawl | 35 | 1575 |
| 6. | Kolasib | 44 | 1980 |
| 7. | Lawngtlai | 49 | 2205 |
| 8. | Lunglei | 83 | 3735 |
| 9. | Mamit | 61 | 2745 |
| 10. | Saitual | 45 | 2025 |
| 11. | Serchhip | 46 | 2070 |
| 12. | Siaha | 43 | 1935 |
| 13. | State | 100 | 4500 |
|  | Total | 741 | 33345 |
| Total amount for 2 rounds of NDD IEC Materials - Rs.33345 x 2 = Rs.66,690 /- |  |  |  |

RCH 7 – 53: Scheme: National Deworming Day

Components: Planning & M&E

Particulars: State/District Coordination Committee on NDD

| Sl No | DISTRICT | Budget for Committee Expense | Budget for 2 Rounds of NDD |
| --- | --- | --- | --- |
| 1 | Aizawl East | 4000 | 8000 |
| 2 | Aizawl west | 4000 | 8000 |
| 3 | Champhai | 4000 | 8000 |
| 4 | Hnahthial | 4000 | 8000 |
| 5 | Khawzawl | 4000 | 8000 |
| 6 | Kolasib | 4000 | 8000 |
| 7 | Lawngtlai | 4000 | 8000 |
| 8 | Lunglei | 4000 | 8000 |
| 9 | Mamit | 4000 | 8000 |
| 10 | Saitual | 4000 | 8000 |
| 11 | Serchhip | 4000 | 8000 |
| 12 | Siaha | 4000 | 8000 |
| 13 | State | 4000 | 8000 |
|  | TOTAL | 52000 | 104000 |

HSS 17– 202: Scheme: ASHA Incentives (Incl. RCH, NDCP, NCD, HSS-Urban, HSS-Rural)

Components: ASHA Incentive

Particulars: ASHA Incentives under NRC

| Sl.No | Districts | Expected SAM Case | ASHA incentives under NRC @Rs 300 for SAM Identification , referred and follow-up | Total Amount |
| --- | --- | --- | --- | --- |
| 1. | Aizawl East | 70 | 300 | 21000 |
| 5. | Lawngtlai | 30 | 300 | 9000 |
|  | TOTAL | 100 | 300 | 30000 |

RCH 7 – 54: Scheme: Nutritional Rehabilitation Centers (NRC)

Components: Others including operating costs (OOC)

Particulars: Operating Cost under NRC

| Recurrent Expenditure |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Sl no | Districts | Kitchen Supplies (Rs. 7500/month) | Contingency (Rs.750/month) | Food for mother/care giver for 10 mothers (Rs.100/day) | Total | Remarks |
| 1 | Aizawl East | 90000 | 9000 | 168000 | 2,67,000 | 10 patient/DH each month |
| 2 | Lawngtlai DH | 90000 | 9000 | 168000 | 2,67,000 |  |
|  | Sub Total | 180000 | 18000 | 336000 | 5,34,000 |  |

TOTAL COST FOR 2 NRC – Rs. 5, 34,000/-

HSS 17– 202: Scheme: ASHA Incentives (Incl. RCH, NDCP, NCD, HSS-Urban, HSS-Rural)

Components: ASHA Incentive

Particulars: ASHA incentives under MAA Programme

| Sl.No | Districts | No of ASHA | ASHA incentives under MAA @Rs 100 per quarterly mothers meeting (100x4) | Total Amount |
| --- | --- | --- | --- | --- |
| 1 | Aizawl East | 129 | 400 | 51600 |
| 2 | Aizawl west | 106 | 400 | 42400 |
| 3 | Champhai | 71 | 400 | 28400 |
| 4 | Hnahthial | 43 | 400 | 17200 |
| 5 | Khawzawl | 44 | 400 | 17600 |
| 6 | Kolasib | 87 | 400 | 34800 |
| 7 | Lawngtlai | 165 | 400 | 66000 |
| 8 | Lunglei | 165 | 400 | 66000 |
| 9 | Mamit | 82 | 400 | 32800 |
| 10 | Saitual | 51 | 400 | 20400 |
| 11 | Serchhip | 71 | 400 | 28400 |
| 12 | Siaha | 77 | 400 | 30800 |
|  | TOTAL | 1091 |  | 4,36,400 |

HSS 19– 204: Scheme: IEC & Printing (Incl. RCH, NDCP, NCD, HSS-Urban, HSS-Rural)

Components: IEC & Printing

Particulars: Media Activities under MAA (Mothers Absolute Affection) Programme

Broadcasting of Video and radio spots

•	DDK @ Rs. 1900 X 4 Days X 12 months = Rs. 91,200

•	AIR @ Rs. 2300 X 4 Days X 12 months = Rs. 1, 10, 440

Total amount for IEC under MAA Programme = Rs. 2, 01,640/-

HSS 17– 202: Scheme: ASHA Incentives (Incl. RCH, NDCP, NCD, HSS-Urban, HSS-Rural)

Components: ASHA Incentive

Particulars: ASHA Incentive (STOP Diarrhoea Campaign ORS distribution to family with Under 5 years children)

Total Amount for ASHA Incentives for SDC Rs.109100 /-

| Sl.No | Districts | No of ASHA | Amount for incentives for SDC for ORS distribution to a family under 5 children @Rs.100 per ASHA |
| --- | --- | --- | --- |
| 1 | Aizawl East | 129 | 12900 |
| 2 | Aizawl west | 106 | 10600 |
| 3 | Champhai | 71 | 7100 |
| 4 | Hnahthial | 43 | 4300 |
| 5 | Khawzawl | 44 | 4400 |
| 6 | Kolasib | 87 | 8700 |
| 7 | Lawngtlai | 165 | 16500 |
| 8 | Lunglei | 165 | 16500 |
| 9 | Mamit | 82 | 8200 |
| 10 | Saitual | 51 | 5100 |
| 11 | Serchhip | 71 | 7100 |
| 12 | Siaha | 77 | 7700 |
|  | TOTAL | 1091 | 109100 |

RCH 7 – 58: Scheme: Intensified Diarrhoea Control Fortnight (STOP Diarrhoea Campaign)

Components: Drugs

Particulars: ORS for STOP Diarrhoea Campaign 2026-27

| SNo | District | Total Under 5 population For distribution by ASHA | Prepositioning of ORS 2 Packet for each children | ORS for ASHA @ 20 packets per ASHA | ORS for ANM @ 20 packets per ANM | ORS for ORS-Zinc Corner @100 packets per corner | # ORS for Mobile team @ 20 packets per team | ORS for demonstration | Total qty of ORS required |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Aizawl East | 17640 | 35280 | 2580 | 2760 | 44100 | 2400 | 200 | 87320 |
| 2 | Aizawl west | 12010 | 24020 | 2120 | 1320 | 31600 | 1800 | 200 | 61060 |
| 3 | Champhai | 6889 | 13778 | 1420 | 1040 | 26400 | 1800 | 200 | 44638 |
| 4 | Hnahthial | 2992 | 5984 | 860 | 380 | 20000 | 1200 | 200 | 28624 |
| 5 | Khawzawl | 3143 | 6286 | 880 | 520 | 20000 | 1200 | 200 | 29086 |
| 6 | Kolasib | 7521 | 15042 | 1740 | 680 | 32400 | 1200 | 200 | 51262 |
| 7 | Lawngtlai | 15000 | 30000 | 3300 | 860 | 28100 | 1200 | 200 | 63660 |
| 8 | Lunglei | 12960 | 25920 | 3300 | 1360 | 25100 | 2400 | 200 | 58280 |
| 9 | Mamit | 9167 | 18334 | 1640 | 1080 | 47100 | 1800 | 200 | 70154 |
| 10 | Saitual | 4003 | 8006 | 1020 | 800 | 20000 | 1200 | 200 | 31226 |
| 11 | Serchhip | 5166 | 10332 | 1420 | 880 | 17000 | 1200 | 200 | 31032 |
| 12 | Siaha | 7495 | 14990 | 1540 | 660 | 35200 | 1200 | 200 | 53790 |
|  | Total | 103986 | 207972 | 21820 | 12340 | 347000 | 18600 | 2400 | 610132 |
| Total amount proposed for 610132 ORS packets @ Rs. 4.20 = Rs.25,62,554.4/- |  |  |  |  |  |  |  |  |  |

RCH 7 – 58: Scheme: Intensified Diarrhoea Control Fortnight (STOP Diarrhoea Campaign)

Components: Drugs

Particulars: Zinc tablets for STOP Diarrhoea Campaign 2026-27

| SNo | District | Under 5 population | Zinc for Under 5 population @ 14 tablet each | Zinc for ASHA @ 140 tablets per ASHA | Zinc for ANM @ 140 tablets per ANM | Zinc for ORS-Zinc Corner @280tablets per corner | # Zinc for Mobile team @ 700 packets per team | Total amount of Zinc tablets required |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Aizawl East | 17640 | 246960 | 18060 | 19320 | 47320 | 1400 | 333060 |
| 2 | Aizawl west | 12010 | 168140 | 14840 | 9240 | 90440 | 1400 | 284060 |
| 3 | Champhai | 6889 | 96446 | 9940 | 7280 | 54880 | 1400 | 169946 |
| 4 | Hnahthial | 2992 | 41888 | 6020 | 2660 | 47040 | 1400 | 99008 |
| 5 | Khawzawl | 3143 | 44002 | 6160 | 3640 | 37240 | 1400 | 92442 |
| 6 | Kolasib | 7521 | 105294 | 12180 | 4760 | 50680 | 1400 | 174314 |
| 7 | Lawngtlai | 15000 | 210000 | 23100 | 6020 | 98280 | 1400 | 338800 |
| 8 | Lunglei | 12960 | 181440 | 23100 | 9520 | 100800 | 1400 | 316260 |
| 9 | Mamit | 9167 | 128338 | 11480 | 7560 | 96040 | 1400 | 244818 |
| 10 | Saitual | 4003 | 56042 | 7140 | 5600 | 49280 | 1400 | 119462 |
| 11 | Serchhip | 5166 | 72324 | 9940 | 6160 | 57680 | 1400 | 147504 |
| 12 | Siaha | 7495 | 104930 | 10780 | 4620 | 47320 | 1400 | 169050 |
|  | Total | 103986 | 1455804 | 152740 | 86380 | 777000 | 16800 | 2488724 |
| Total amount proposed for procurement of Zinc tablets 2488724@ Rs 0.60 per tablet = Rs,14,93,234.4 /- |  |  |  |  |  |  |  |  |

HSS 16– 201: Scheme: Capacity building incl. training (Incl. RCH, NDCP, NCD, HSS-Urban, HSS-Rural)

Components: Capacity building including training

Particulars: Orientation cum training on STOP Diarrhoea Campaign at District/ Block Level

| Sl No | District | ASHA | From DH/SDH/CHC/PHC/UPHC/UHWC | AHWC/HWC/SC | SC/ clinic | AWW | Total No to be trained | Amount for Orientation @ Rs. 100 at Block level |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Aizawl East | 129 | 26 | 40 | 28 | 252 | 475 | 47500 |
| 2 | Aizawl west | 106 | 26 | 38 | 24 | 194 | 388 | 38800 |
| 3 | Champhai | 71 | 16 | 30 | 14 | 144 | 275 | 27500 |
| 4 | Hnahthial | 43 | 14 | 16 | 4 | 115 | 192 | 19200 |
| 5 | Khawzawl | 44 | 14 | 19 | 9 | 98 | 184 | 18400 |
| 6 | Kolasib | 87 | 18 | 28 | 7 | 137 | 277 | 27700 |
| 7 | Lawngtlai | 165 | 16 | 35 | 6 | 302 | 524 | 52400 |
| 8 | Lunglei | 165 | 22 | 57 | 15 | 303 | 562 | 56200 |
| 9 | Mamit | 82 | 22 | 40 | 10 | 282 | 436 | 43600 |
| 10 | Saitual | 51 | 16 | 27 | 10 | 131 | 235 | 23500 |
| 11 | Serchhip | 71 | 16 | 29 | 9 | 160 | 285 | 28500 |
| 12 | Siaha | 77 | 12 | 24 | 13 | 126 | 252 | 25200 |
|  | Total | 1091 | 218 | 383 | 149 | 2244 | 4085 | 408500 |

HSS 11 – 194: Scheme: Planning and Program Management

Particulars: Launch event at State/ District (Including IEC/BCC) of IDCF

|  | DISTRICT | Radio Jingles(Rs) | News paper advertisement on NDD(Rs) | TV spots/ scrolls(Rs) | Inauguration Event(Rs) | Total Budget for media Activities |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Aizawl East | 0 | 0 | 0 | 10000 | 10000 |
| 2 | Aizawl west | 0 | 0 | 0 | 10000 | 10000 |
| 3 | Champhai | 0 | 0 | 0 | 10000 | 10000 |
| 4 | Hnahthial | 0 | 0 | 0 | 10000 | 10000 |
| 5 | Khawzawl | 0 | 0 | 0 | 10000 | 10000 |
| 6 | Kolasib | 0 | 0 | 0 | 10000 | 10000 |
| 7 | Lawngtlai | 0 | 0 | 0 | 10000 | 10000 |
| 8 | Lunglei | 0 | 0 | 0 | 10000 | 10000 |
| 9 | Mamit | 0 | 0 | 0 |  |  |
| 10 | Saitual | 0 | 0 | 0 | 10000 | 10000 |
| 11 | Serchhip | 0 | 0 | 0 | 10000 | 10000 |
| 12 | Siaha | 0 | 0 | 0 | 10000 | 10000 |
| 13 | State | 33000 | 10000 | 42000 | 30000 | 115000 |
|  | Total | 33000 | 10000 | 42000 | 150000 | 235000 |

RCH 7 – 58: Scheme: Intensified Diarrhoea Control Fortnight (STOP Diarrhoea Campaign)

Components: IEC & Printing

Particulars: Printing of IEC materials and monitoring formats for STOP Diarrhoea Campaign

Total amount proposed: Rs. 2, 00,000/-

1. Printing of STOP Diarrhoea Campaign Formats

| Sl No | DISTRICT | Printing of ASHA Monitoring Format | Printing of SC Reporting Format | Printing of SDC Block Reporting Format | Supervision Checklist | Total No of Formats to be Printed | Cost of Printing of formats @ Rs.2 |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Aizawl East | 1500 | 1200 | 1000 | 15 | 3715 | 7430 |
| 2 | Aizawl west | 1500 | 1200 | 750 | 15 | 3465 | 6930 |
| 3 | Champhai | 1300 | 1100 | 800 | 15 | 3215 | 6430 |
| 4 | Hnahthial | 1200 | 1000 | 700 | 15 | 2915 | 5830 |
| 5 | Khawzawl | 1200 | 1000 | 700 | 15 | 2915 | 5830 |
| 6 | Kolasib | 1300 | 1100 | 700 | 15 | 3115 | 6230 |
| 7 | Lawngtlai | 1400 | 1200 | 1100 | 15 | 3315 | 6630 |
| 8 | Lunglei | 1500 | 1200 | 700 | 15 | 3415 | 6830 |
| 9 | Mamit | 1400 | 1200 | 600 | 15 | 3215 | 6430 |
| 10 | Saitual | 1200 | 1000 | 700 | 15 | 2915 | 5830 |
| 11 | Serchhip | 1300 | 1100 | 800 | 15 | 3215 | 6430 |
| 12 | Siaha | 1300 | 1100 | 800 | 15 | 3215 | 6430 |
|  | Total | 16100 | 13400 | 9350 | 180 | 38630 | 77260 |

2. IEC Print Material

Total amount proposed for Printing of Posters and Leaflets: Rs.1, 22,740 /-

| Sl No | DISTRICT | No of ORS Zinc Corner at Health Facilities | Cost of Printing of Posters Required at Zinc ORS Corner at health facility@ Rs. 15 X 3Posters | Zn ORS Corner at AWC | Cost of Printing of Posters Required at Zinc ORS Corner at AWC@ Rs. 15 X 2 Poster | Total Cost of Printing posters | Cost of Printing Leaflets for ORS- Zinc Corners @ Rs. 5 | Total cost of printing posters and Leaflet |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Aizawl East | 81 | 3645 | 252 | 7560 | 11205 | 4075 | 15280 |
| 2 | Aizawl west | 75 | 3375 | 194 | 5820 | 9195 | 3000 | 12195 |
| 3 | Champhai | 52 | 2340 | 144 | 4320 | 6660 | 2000 | 8660 |
| 4 | Hnahthial | 27 | 1215 | 115 | 3450 | 4665 | 1500 | 6165 |
| 5 | Khawzawl | 35 | 1575 | 98 | 2940 | 4515 | 1500 | 6015 |
| 6 | Kolasib | 44 | 1980 | 137 | 4110 | 6090 | 2000 | 8090 |
| 7 | Lawngtlai | 49 | 2205 | 302 | 9060 | 11265 | 2500 | 13765 |
| 8 | Lunglei | 83 | 3735 | 303 | 9090 | 12825 | 2500 | 15325 |
| 9 | Mamit | 61 | 2745 | 282 | 8460 | 11205 | 2000 | 13205 |
| 10 | Saitual | 45 | 2025 | 131 | 3930 | 5955 | 1500 | 7455 |
| 11 | Serchhip | 46 | 2070 | 160 | 4800 | 6870 | 2000 | 8870 |
| 12 | Siaha | 43 | 1935 | 126 | 3780 | 5715 | 2000 | 7715 |
|  | Total | 641 | 28845 | 2244 | 67320 | 96165 | 26500 | 122740 |

HSS 11 – 194: Scheme: Planning and Program Management

Particulars: State/District Coordination Committee on STOP Diarrhoea Campaign

| Sl No | DISTRICT | Budget for STOP Diarrhoea Campaign Coordination Committee Expense |
| --- | --- | --- |
| 1 | Aizawl East | 4000 |
| 2 | Aizawl west | 4000 |
| 3 | Champhai | 4000 |
| 4 | Hnahthial | 4000 |
| 5 | Khawzawl | 4000 |
| 6 | Kolasib | 4000 |
| 7 | Lawngtlai | 4000 |
| 8 | Lunglei | 4000 |
| 9 | Mamit | 4000 |
| 10 | Saitual | 4000 |
| 11 | Serchhip | 4000 |
| 12 | Siaha | 4000 |
| 13 | State | 4000 |
|  | TOTAL | 52000 |

FAMILY PLANNING

RCH 6 - Sl. no. 42: Scheme - Sterilization - Female

Component: DBT

Particulars: Beneficiary Compensation under FP services - Compensation for Female Sterilization (Public Institutions)

Budget estimated for compensation of female sterilization for Interval Sterilisation 500 acceptors at public institution@ Rs.2800 is Rs.14,00,000/- and budget estimated for compensation of female sterilization for postpartum sterilization 835 acceptors@ Rs.4000 is Rs. 33,40,000/-. Therefore, total budget estimated for 1385 Female Compensation is Rs. 47,40,000/- and is tabulated below:

| S.NO | DISTRICT | ACCEPTOR | TOTAL ACCEPTOR |
| --- | --- | --- | --- |
| 1. | AIZAWL EAST | Interval Sterilisation 150 | 550 |
|  |  | Postpartum Sterilisation 400 |  |
| 2. | AIZAWL WEST | Interval Sterilisation 100 | 170 |
|  |  | Postpartum Sterilisation 70 |  |
| 3. | CHAMPHAI | Interval Sterilisation 50 | 110 |
|  |  | Postpartum Sterilisation 60 |  |
| 4. | HNAHTHIAL | Interval Sterilisation 10 | 20 |
|  |  | Postpartum Sterilisation 10 |  |
| 5. | KHAWZAWL | Interval Sterilisation 10 | 25 |
|  |  | Postpartum Sterilisation 15 |  |
| 6. | KOLASIB | Interval Sterilisation 50 | 80 |
|  |  | Postpartum Sterilisation 30 |  |
| 7. | LAWNGTLAI | Interval Sterilisation 20 | 70 |
|  |  | Postpartum Sterilisation50 |  |
| 8. | LUNGLEI | Interval Sterilisation 40 | 130 |
|  |  | Postpartum Sterilisation 90 |  |
| 9. | MAMIT | Interval Sterilisation 20 | 60 |
|  |  | Postpartum Sterilisation40 |  |
| 11. | SAITUAL | Interval Sterilisation 10 | 20 |
|  |  | Postpartum Sterilisation 10 |  |
| 10. | SERCHHIP | Interval Sterilisation 20 | 50 |
|  |  | Postpartum Sterilisation 30 |  |
| 12. | SIAHA | Interval Sterilisation 20 | 50 |
|  |  | Postpartum Sterilisation 30 |  |
| TOTAL |  | Interval Sterilisation 500 | 1385 |
|  |  | Postpartum Sterilisation 835 |  |
| BUDGET ESTIMATE |  | Interval Sterilisation 500x 2800 | Rs. 14,00,000/- |
|  |  | Postpartum Sterilisation 835 x 4000 | Rs. 33,40,000/- |
|  |  | TOTAL | Rs.47,40,000/- |

| Proce dure | Accep tor | Motivator | Drugs And Dressing | Surgeon charges | Anesthe tist Charges | Staff Nurse | OT Techni cian | Clerks/Documentation | Refreshment | Miscellaneous | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Tubectomy (Interval) | 2000 | 300 | 100 | 200 | 50 | 40 | 40 | 30 | 20 | 20 | 2800 |
| Post Partum Sterilization | 3000 | 400 | 100 | 325 | 75 | 50 | 50 | - | - | - | 4000 |

RCH 6 - Sl. no. 42: Scheme - Sterilization - Female

Component: DBT

Particulars: Beneficiary Compensation under FP services - Compensation for Female Sterilization (Private Institutions)

Budget estimated for compensation of female sterilization for Interval Sterilisation 108 acceptors at private institution@ Rs.3500 is Rs. 3,78,000/- and budget estimated for compensation of female sterilization for postpartum sterilization 140 acceptors@ Rs.4000 is Rs. 5,60,000/-. Therefore, total budget estimated for 248 Female Compensation is Rs. 9,38,000/- and is tabulated below:

| S.No | DISTRICT | AMOUNT | TOTAL ACCEPTOR |
| --- | --- | --- | --- |
| 1. | AIZAWL EAST PRIVATE HOSPITAL | Interval Sterilisation 23 | 88 |
|  |  | Postpartum Sterilisation 65 |  |
| 2. | AIZAWL WEST PRIVATE HOSPITAL | Interval Sterilisation 40 | 65 |
|  |  | Postpartum sterilization 25 |  |
| 3 | LUNGLEI PRIVATE HOSPITAL | Interval Sterilisation 45 | 95 |
|  |  | Postpartum Sterilisation 50 |  |
| TOTAL |  | Interval Sterilisation 108 | 275 |
|  |  | Postpartum Sterilisation 140 |  |
| Budget Estimate |  | Interval Sterilisation 108 x 3500 | Rs.3,78,000/- |
|  |  | Postpartum Sterilisation 140 x 4000 | Rs. 5,60,000/- |
|  |  | Total | Rs. 9,38,000/- |

Fund Break-up

| Procedure | Facility | Acceptor | Total |
| --- | --- | --- | --- |
| Tubectomy (Interval) | 2500 | 1000 | 3500 |
| Post Partum Sterilization | 3000 | 1000 | 4000 |

RCH 6 - Sl. no. 43: Scheme - Sterilization - Male

Component: DBT

Particulars: Beneficiary Compensation under FP services - Compensation for Male Sterilization

Vasectomy is one of the safest and most effective contraceptive method having very lowcomplication and failure rates. Non-Scalpel Vasectomy which is now recommended than the Conventional Vasectomy neither requires any cut on the skin with a scalpel blade nor any skin stitch, after the procedure is completed and it is much less painful and faster procedure. Since male participation in Family Planning is greatly desired scheme to compensation acceptors was laid out.Budget estimated for compensation of male sterilizationfor 1 acceptor is Rs.4000 (Four Thousand Rupees Only) and is tabulated below: -

| Breakage of the Compensation package | Acceptor | Motivator | Drugs And Dressing | Surgeon charges | Staff Nurse | OT Technician/ helper | Clerks/Documentation | Refreshment | Miscellaneous | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Vasectomy | 3000 | 400 | 50 | 400 | 45 | 40 | 30 | 20 | 20 | 4000 |

Accredited Private/ NGO Facilities

| Procedure | Facility | Acceptor | Motivator | Total (in Rupees) |
| --- | --- | --- | --- | --- |
| Vasectomy (ALL) | 2500 | 1000 | 200 | 3500 |

| Sl.no | Target Number of Client | Target District | Amount ( in rupees) |
| --- | --- | --- | --- |
| 1. | 1 | Civil Hospital, Aizawl East District | 1 x 4000 |
| TOTAL |  |  | 4,000/- |

RCH 6 - Sl. no. 44: Scheme - IUCD Insertion (PPIUCD and PAIUCD)

Component: DBT

Particulars: Beneficiary Compensation under FP services - Compensation for IUCD Insertion

Family planning is important not only for population stabilization, but it has been increasingly realized that family planning is central to improve maternal and newborn survival and health. Intrauterine contraceptive devices (IUCD) provide very effective, safe, and long-term—yet reversible—protection from pregnancy. IUCD is one of the most cost-effective contraceptive methods because modern IUCDs can be used safely for many years and such contraceptive is desirable for maintaining 3 years gap.Budget estimated for compensation of IUCD at Public Health Facilities for 2201 acceptors @ Rs.20 is Rs. 44,020/- and is tabulated below: -

Provide breakup:

Public Sector (@Rs.20/insertion)/Private Sector (@Rs.75/insertion for EAG states)

| S.NO | DISTRICT | NUMBER OF ACCEPTOR | BUDGET @ Rs.20/INSERTION | BUDGET @ Rs.20/INSERTION |
| --- | --- | --- | --- | --- |
| 1. | AIZAWL EAST | 426 | 8520 | 44,020/- |
| 2. | AIZAWL WEST | 300 | 6000 |  |
| 3. | CHAMPHAI | 200 | 4000 |  |
| 4. | HNAHTHIAL | 70 | 1400 |  |
| 5. | KHAWZAWL | 80 | 1600 |  |
| 6. | KOLASIB | 200 | 4000 |  |
| 7. | LAWNGTLAI | 125 | 2500 |  |
| 8. | LUNGLEI | 200 | 4000 |  |
| 9. | MAMIT | 130 | 2600 |  |
| 10 | SAITUAL | 100 | 2000 |  |
| 11 | SERCHHIP | 200 | 4000 |  |
| 12 | SIAHA | 170 | 3400 |  |
| TOTAL |  | 2201 | 44020 |  |

RCH 6 - Sl. no. 44: Scheme - IUCD Insertion (PPIUCD and PAIUCD)

Component: DBT

Particulars:Beneficiary Compensation under FP services - Compensation for PPIUCD Services

IUCD is one of the most cost-effective contraceptive methods because modern IUCDs can be used safely for many years and such contraceptive is desirable for maintaining 3 years gap. Postpartum women who breastfeed their infants can also use Cu IUCD safely, as it does not interfere with breastfeeding. Postpartum IUCD can be inserted immediately after vaginal delivery, during caesarean section and up to 48 hours after birth, before women get discharged from the health facilities. This increases the rate of insertion of contraceptives. It is effective immediately after insertion and Fertility returns promptly on removal. Budget estimated for PPIUCD insertion for 1090 acceptors is Rs. 3,27,000/- only and is tabulated below:

Incentives to beneficiary @ Rs.300 per PPIUCD:

| S.NO | DISTRICT | NUMBER OF ACCEPTOR | BUDGET @ Rs.300/INSERTION for acceptor | BUDGET @ Rs.300/INSERTION for acceptor |
| --- | --- | --- | --- | --- |
| 1. | AIZAWL EAST | PPIUCD 172 | 51600 | 3,27,000/- |
| 2. | AIZAWL WEST | PPIUCD 90 | 27000 |  |
| 3. | CHAMPHAI | PPIUCD 210 | 63000 |  |
| 4. | HNAHTHIAL | PPIUCD 40 | 12000 |  |
| 5. | KHAWZAWL | PPIUCD 50 | 15000 |  |
| 6. | KOLASIB | PPIUCD 63 | 18900 |  |
| 7. | LAWNGTLAI | PPIUCD 89 | 26700 |  |
| 8. | LUNGLEI | PPIUCD 79 | 23700 |  |
| 9. | MAMIT | PPIUCD 89 | 26700 |  |
| 10 | SAITUAL | PPIUCD 40 | 12000 |  |
| 11 | SERCHHIP | PPIUCD 68 | 20400 |  |
| 12 | SIAHA | PPIUCD 100 | 30000 |  |
| TOTAL |  | 1090 | 3,27,000 |  |

Incentive to provider for PPIUCD Services:

| S.NO | DISTRICT | NUMBER OF ACCEPTOR | BUDGET @ Rs.150/INSERTION for Providers | BUDGET @ Rs.150/INSERTION Providers |
| --- | --- | --- | --- | --- |
| 1. | AIZAWL EAST | PPIUCD 172 | 25800 | 1,63,500/- |
| 2. | AIZAWL WEST | PPIUCD 90 | 13500 |  |
| 3. | CHAMPHAI | PPIUCD 210 | 31500 |  |
| 4. | HNAHTHIAL | PPIUCD 40 | 6000 |  |
| 5. | KHAWZAWL | PPIUCD 50 | 7500 |  |
| 6. | KOLASIB | PPIUCD 63 | 9450 |  |
| 7. | LAWNGTLAI | PPIUCD 89 | 13350 |  |
| 8. | LUNGLEI | PPIUCD 79 | 11850 |  |
| 9. | MAMIT | PPIUCD 89 | 13350 |  |
| 10 | SAITUAL | PPIUCD 40 | 6000 |  |
| 11 | SERCHHIP | PPIUCD 68 | 10200 |  |
| 12. | SIAHA | PPIUCD 100 | 15000 |  |
| TOTAL |  | 1090 | 1,63,500 |  |

RCH 6 - Sl. no. 44: Scheme - IUCD Insertion (PPIUCD and PAIUCD)

Component: DBT

Particulars:Beneficiary Compensation under FP services - Compensation for PAIUCD Services

To avoid unwanted pregnancy which can effect the health of a woman PAIUCD service provides long term reversible method of contraceptive. There are 80 nos. 1st trimester spontaneous abortion and 66 nos. 2nd trimester spontaneous abortion. PAIUCD services will decrease the number of abortions. Budget estimated for compensation of PAIUCD Services for 94 beneficiaries is Rs. 28200/- only:

PAIUCD SERVICES: Compensation to beneficiary

| S.NO | DISTRICT | NUMBER OF ACCEPTOR | AMOUNT @ Rs.300/INSERTION FOR BENEFICIARY | AMOUNT @ Rs.300/INSERTION FOR BENEFICIARY |
| --- | --- | --- | --- | --- |
| 1. | AIZAWL EAST | PAIUCD 11 | 3300 | 28200 |
| 2. | AIZAWL WEST | PAIUCD 11 | 3300 |  |
| 3 | HNAHTHIAL | PAIUCD 5 | 1500 |  |
| 4. | KHAWZAWL | PAIUCD 5 | 1500 |  |
| 5. | KOLASIB | PAIUCD 6 | 1800 |  |
| 6. | CHAMPHAI | PAIUCD 11 | 3300 |  |
| 7. | LAWNGTLAI | PAIUCD 16 | 4800 |  |
| 8. | LUNGLEI | PAIUCD 6 | 1800 |  |
| 9. | MAMIT | PAIUCD 6 | 1800 |  |
| 10. | SAITUAL | PAIUCD 5 | 1500 |  |
| 11. | SERCHHIP | PAIUCD 6 | 1800 |  |
| 12. | SIAHA | PAIUCD 6 | 1800 |  |
| TOTAL |  | 94 | 28200 |  |

Incentive to provider for PAIUCD Services:

Compensation of Service Provider for 94 PAIUCD acceptors is Rs. 14100/- only and is tabulated below

| S.NO | DISTRICT | NUMBER OF ACCEPTOR | AMOUNT @ Rs.150/INSERTION FOR Provider | AMOUNT @ Rs.150/INSERTION FOR Provider |
| --- | --- | --- | --- | --- |
| 1. | AIZAWL EAST | PAIUCD 11 | 1650 | 14100 |
| 2. | AIZAWL WEST | PAIUCD 11 | 1650 |  |
| 3 | HNAHTHIAL | PAIUCD 5 | 750 |  |
| 4. | KHAWZAWL | PAIUCD 5 | 750 |  |
| 5. | KOLASIB | PAIUCD 6 | 900 |  |
| 6. | CHAMPHAI | PAIUCD 11 | 1650 |  |
| 7. | LAWNGTLAI | PAIUCD 16 | 2400 |  |
| 8. | LUNGLEI | PAIUCD 6 | 900 |  |
| 9. | MAMIT | PAIUCD 6 | 900 |  |
| 10 | SAITUAL | PAIUCD 5 | 750 |  |
| 11 | SERCHHIP | PAIUCD 6 | 900 |  |
| 12 | SIAHA | PAIUCD 6 | 900 |  |
| TOTAL |  | 94 | 14100 |  |

HSS 17– 202: Scheme: ASHA Incentives (Incl. RCH, NDCP, NCD, HSS-Urban, HSS-Rural)

Component: ASHA incentives

Particulars: ASHA PPIUCD incentive for accompanying the client for PPIUCD insertion

Estimated budget for ASHA PPIUCD incentive for accompanying the client for PPIUCD insertion; Rs. 46,500/-

| Component/ Activities | Incentive Amount proposed per ASHA (A) | Measurable Output (B) | Target Population | Total Amount Proposed (in lakhs) (A*B/100000) | Remarks |
| --- | --- | --- | --- | --- | --- |
| ASHA PPIUCD incentive for accompanying the client for PPIUCD insertion | 300 | 155 | 1282835 | 0.46 (Rs 46,500) | Ongoing activity: Proposed @ 300/- per performance/motivating mother for using IUCD after delivery. Expected number of PPIUCD insertion is 1090. 14% of PPIUCD i.e., 155 is expected to be ASHA motivated and proposed for the incentive. |

HSS 17– 202: Scheme: ASHA Incentives (Incl. RCH, NDCP, NCD, HSS-Urban, HSS-Rural)

Component: ASHA incentives

Particulars:PAIUCD

Estimated budget for ASHA PPIUCD incentive for accompanying the client for PPIUCD insertion; Rs. 3900/-

| Component/ Activities | Incentive Amount proposed per ASHA (A) | Measurable Output (B) | Target Population | Total Amount Proposed (in lakhs) (A*B/100000) | Remarks |
| --- | --- | --- | --- | --- | --- |
| PAIUCD | 300 | 13 | 1282835 | 0.04 (Rs 3900) | Ongoing activity: Proposed @ 300/- per performance/motivating mother for using IUCD after delivery. Expected number of PAIUCD insertion is 94. 15% of PAIUCD i.e., 13 is expected to be ASHA motivated and proposed for the incentive. |

HSS 16– 201: Scheme: Capacity building incl. training (Incl. RCH, NDCP, NCD, HSS-Urban, HSS-Rural)

Component: Capacity building incl. training

Particulars:Interval IUCD Insertion training for SN/LHV/ANM

Budget for 1 batch = Rs.60,000/-

| Sl | Particular Activities | Rate/Day | No of Days | Participants/Batch | Amount(Rs) |
| --- | --- | --- | --- | --- | --- |
| 1 | Venue Hiring | 2000 | 3 |  | 6000 |
| 2 | Refreshment | 150 | 3 | 10 | 4500 |
| 3 | Honorarium for Trainer | 1000 | 3 | 3 | 9000 |
| 4 | Training Materials | 100 |  | 8 | 800 |
| 5 | Banner | 1500 |  |  | 1500 |
| 6 | TA | 2500 |  | 5 | 12500 |
| 7 | DA | 500 | 3 | 5 | 7500 |
| 8 | Lodging | 1000 | 3 | 5 | 15000 |
| 9 | Contingency |  |  |  | 3200 |
| TOTAL |  |  |  |  | 60,000 |

HSS 16– 201: Scheme: Capacity building incl. training (Incl. RCH, NDCP, NCD, HSS-Urban, HSS-Rural)

Component: Capacity building incl. training

Particulars:Training of PPIUCD for SN/ANM/LHV

Budget for 1 batch: Rs. 60,000/-

| Sl No | Particular Activities | Rate/Day (Rs) | No of Days | Participants/Batch | Amount (Rs) |
| --- | --- | --- | --- | --- | --- |
| 1 | Venue Hiring | 2000 | 3 |  | 6000 |
| 2 | Refreshment | 150 | 3 | 10 | 4500 |
| 3 | Honorarium for Trainer | 1000 | 3 | 3 | 9000 |
| 4 | Training Materials | 100 |  | 8 | 800 |
| 5 | Banner | 1500 |  |  | 1500 |
| 6 | TA | 2500 |  | 5 | 12500 |
| 7 | DA | 500 | 3 | 5 | 7500 |
| 8 | Lodging | 1000 | 3 | 5 | 15000 |
| 9 | Contingency |  |  |  | 3200 |
| TOTAL |  |  |  |  | 60,000 |

RCH 6 - Sl. no. 45: Antara

Component: DBT

Particulars:Mission parivar Vikas - Incentivizing beneficiary @ Rs. 100/ dose received

• Incentivizing beneficiary @ Rs. 100/ dose received. Total Rs. 5,90,000/-

| Sl.No | District | No.of doses | Incentives 100/dose |
| --- | --- | --- | --- |
| 1 | Aizawl East | 500 | 50000 |
| 2 | Aizawl West | 450 | 45000 |
| 3 | Champhai | 650 | 65000 |
| 4 | Hnahthial | 400 | 40000 |
| 5 | Khawzawl | 300 | 30000 |
| 6 | Kolasib | 350 | 35000 |
| 7 | Lawngtlai | 800 | 80000 |
| 8 | Lunglei | 600 | 60000 |
| 9 | Mamit | 700 | 70000 |
| 10 | Saitual | 200 | 20000 |
| 11 | Serchhip | 400 | 40000 |
| 12 | Siaha | 550 | 55000 |
|  | Total | 5900 | 5,90,000 |

HSS 17– 202: Scheme: ASHA Incentives (Incl. RCH, NDCP, NCD, HSS-Urban, HSS-Rural)

Component: ASHA incentives

Particulars: Mission parivar Vikas - Incentivizing beneficiary @ Rs. 100/ dose received (1st, 2nd & 3rd Dose) & Rs. 200 for 4th Doses

| Sl.No | District | No. of Claims | Incentives @100/dose | No of Claims @4th Doses | Incentives @200/4th dose |
| --- | --- | --- | --- | --- | --- |
| 1 | Aizawl East | 100 | 10000 | 20 | 4000 |
| 2 | Aizawl West | 90 | 9000 | 10 | 2000 |
| 3 | Champhai | 130 | 13000 | 30 | 6000 |
| 4 | Hnahthial | 80 | 8000 | 10 | 2000 |
| 5 | Khawzawl | 60 | 6000 | 10 | 2000 |
| 6 | Kolasib | 70 | 7000 | 10 | 2000 |
| 7 | Lawngtlai | 160 | 16000 | 40 | 8000 |
| 8 | Lunglei | 120 | 12000 | 40 | 8000 |
| 9 | Mamit | 140 | 14000 | 30 | 6000 |
| 10 | Saitual | 40 | 4000 | 10 | 2000 |
| 11 | Serchhip | 80 | 8000 | 10 | 2000 |
| 12 | Siaha | 110 | 11000 | 20 | 4000 |
|  | Total | 1180 | 1,18,000 | 240 | 48000 |

Total Budget – Rs. 118000 + 48000 = Rs. 1, 66,000/-

HSS 17– 202: Scheme: ASHA Incentives (Incl. RCH, NDCP, NCD, HSS-Urban, HSS-Rural)

Component: ASHA incentives

Particulars: NAYI PAHEL- an FP Kit for newly weds

Incentivising ASHA @ Rs 300/kit distribution. The ASHA will be provided 3 Nayi Pahel kit and they are expected to distribute 3 kits for the newly weds couple ASHA incentives @Rs.6,54,600/-

| S.NO | DISTRICT | NUMBER OF ASHA | Amount (Rs. 200/Kit * 3 NPK) |
| --- | --- | --- | --- |
| 1. | AIZAWL EAST | 129 | 77,400 |
| 2. | AIZAWL WEST | 106 | 63,600 |
| 3. | CHAMPHAI | 71 | 42600 |
| 4. | HNAHTHIAL | 43 | 25800 |
| 5. | KHAWZAWL | 44 | 26400 |
| 6. | KOLASIB | 87 | 52200 |
| 7. | LAWNGTLAI | 165 | 99,000 |
| 8. | LUNGLEI | 165 | 99,000 |
| 9. | MAMIT | 82 | 49200 |
| 10 | SAITUAL | 51 | 30600 |
| 11 | SERCHHIP | 71 | 42600 |
| 12 | SIAHA | 77 | 46200 |
| TOTAL |  | 1091 | 6,54,600 |

HSS 17– 202: Scheme: ASHA Incentives (Incl. RCH, NDCP, NCD, HSS-Urban, HSS-Rural)

Component: ASHA incentives

Particulars:Incentives for ASHA on Saas Bahu

Total Budget: Rs. 1, 53,200/-

The ASHA is expected to attend the awareness campaign about the various health initiatives programme by the Health Department. Apart from the health awareness various others societal issues were also targeted like Ending existing societal evil, ending myths and misconceptions regarding health and to work for better understanding among daughter-in-law and mother-in-law (Saas and Bahu). The meeting is expected to occur every quarter in a year.

| S.NO | DISTRICT | NUMBER OF SC | Amount |
| --- | --- | --- | --- |
|  |  |  | (Rs. 200/ASHA * 2Q * Nos of SC) |
| 1 | AIZAWL EAST | 40 | 16000 |
| 2 | AIZAWL WEST | 38 | 15200 |
| 3 | CHAMPHAI | 30 | 12000 |
| 4 | HNAHTHIAL | 16 | 6400 |
| 5 | KHAWZAWL | 19 | 7600 |
| 6 | KOLASIB | 28 | 11200 |
| 7 | LAWNGTLAI | 35 | 14000 |
| 8 | LUNGLEI | 57 | 22800 |
| 9 | MAMIT | 40 | 16000 |
| 10 | SAITUAL | 27 | 10800 |
| 11 | SERCHHIP | 29 | 11600 |
| 12 | SIAHA | 24 | 9600 |
| TOTAL |  | 383 | 1,53,200 |

HSS 19– 204: Scheme: IEC & Printing (Incl. RCH, NDCP, NCD, HSS-Urban, HSS-Rural)

Component: IEC & Printing

Particulars:Mission parivar Vikas - MPV Campaigns

‘Mission Parivar Vikas’ Campaigns: (4 per year)

Districts may organize Mission Parivar Vikas Campaign in April, July, November and January (11th to 25th of the designated months). In July and November, the activity will be clubbed with WPD and Vasectomy Fortnight. For April and January, the activity is proposed to be divided into:

• 7 days- preparatory work and client mobilization activities

• 7 days- service delivery

Financial Package: Rs. 25,000/district/campaign for 2 campaigns other than WPD and Vasectomy fortnight.

Budget Estimate for MPV Campaigns for 12 districts is 25000x12x2=Rs. 600000/-

RCH 6 - Sl. no. 46: MPV (Mission Parivar Vikas)

Component: Drugs

Particulars:NAYI PAHEL

Financial Package:

• Permissible cost per kit: Rs. 250/NayiPahel kit

Estimated kit = 3273 kit

Budget estimated for 3273 kit is 3273x250= 8,18,250/-

RCH 6 - Sl. no. 46: MPV (Mission Parivar Vikas)

Component: Others including operating costs (OOC)

Particulars:Saas Bahu and Pati Sammelan

Saas Bahu and PatiSammelan is aimed to facilitate improved communication between mothers-in-law, daughters-in-law and husband through interactive games and exercises and building on their experiences to bring about changes in their attitudes and beliefs about reproductive and sexual health.

| Financial Package: |  |  |
| --- | --- | --- |
| 1. | Organization of Sammelan | 500 |
| 2. | Token Gifts for Participants (Max. Rs 20/-participant) | 1000 (as per actuals) |
|  |  | 1500 |

No of SC = 383

No of meeting to be held per year= 2

Total Cost 383 SC x 2 x 1500 = Rs. 11,49,000

| S.NO | DISTRICT | NUMBER OF SC | Amount (Rs. 1500 * 2Q * Nos of SC) |
| --- | --- | --- | --- |
| 1. | AIZAWL EAST | 40 | 1,20,000 |
| 2. | AIZAWL WEST | 38 | 1,14,000 |
| 3. | CHAMPHAI | 30 | 90,000 |
| 4. | HNAHTHIAL | 16 | 48,000 |
| 5. | KHAWZAWL | 19 | 57,000 |
| 6. | KOLASIB | 28 | 84,000 |
| 7. | LAWNGTLAI | 35 | 1,05,000 |
| 8. | LUNGLEI | 57 | 1,71,000 |
| 9. | MAMIT | 40 | 1,20,000 |
| 10 | SAITUAL | 27 | 81,000 |
| 11 | SERCHHIP | 29 | 87,000 |
| 12 | SIAHA | 24 | 72,000 |
| TOTAL |  | 383 | 11,49,000 |

RCH 6 - Sl. no. 46: MPV (Mission Parivar Vikas)

Component: Others including operating costs (OOC)

Particulars : SAARTHI - Awareness on Wheels

A smartly designed bus/van equipped with interactive communication devices, IEC material and FP commodities shall be operationalized in the districts during Mission parivarvikas campaign (April, July, November and January (11th to 25thof the designated months)) to sensitize and disseminate FP messages in the far-flung areas.

Financial Package: Estimated Cost for SAARTHI= Rs. 6 lakhs for all four campaigns.  1 vehicle may be hired for 12 districts

Estimated cost for Saarthi Campaign:  Rs. 6,00,000/-

RCH 6 - Sl. no. 46: MPV (Mission Parivar Vikas)

Component: Others including operating costs (OOC)

Particulars: Alternate contraceptive delivery system

An alternate contraceptive delivery system (ACD)to be adopted for ensuring supplies in difficult geographical terrain. Identified local person/s may be engaged in the activity on a part time basis for transporting and replenishing the FP commodities till the Sub Centre level.

Financial Package:Estimated Cost for alternate contraceptive delivery = Rs. 200/day/person for a maximum of 10-man days/month (Rs. 2000/month/district)

Estimated cost = 2000x12x12 = 2,88,000

RCH 6 - Sl. no. 46: MPV (Mission Parivar Vikas)

Component: Others including operating costs (OOC)

Particulars: Mission parivar Vikas - Advocacy and Inter-sectoral Convergence

Advocacy and Inter-sectoral Convergence to improve contraceptive access for a healthy mother and child:

• District level (Biannually): Meeting under DM/DC with CMO and BMOs/ BDOs, and line functionaries and other stakeholders working in the district.

• Block level (Quarterly): meeting under BMO/ BDO with all MOs, Nurses, and Sarpanch & Patwaris, Nehru Yuvak Kendra volunteers and National Service Scheme volunteers)

Financial Package: The Budget for Advocacy meetings @ Rs 10,000/district for 12 districts is Rs. 1,20,000/-.

RCH 6 - Sl. no. 47: FPIS

Component: DBT

Particulars: Family Planning Indemnity Scheme (FPIS)

Sterilization is a very effective Family Planning method adopted by the clients to limit their family size. Under the Family Planning Indemnity Scheme, it has been decided that States/UTs would process and make payment of claims to beneficiaries of sterilization in the event of Death/Failure/Complication and Indemnity cover to doctors/health facilities. The State FPISC meets twice a year. They also conduct facility audit in a scheduled manner. Budget estimated for Family Planning Indemnity Scheme 10 failures, 1 case of litigation is Rs.5,00,000 (Five lakhs Rupees only) and is tabulated below as: -

| Section Coverage Limits |  |  |
| --- | --- | --- |
| SECTION I (A-D) : For Beneficiaries |  |  |
| IA | Death following sterilization (inclusive of death during process of sterilization operation) in hospital or within 7 days from the date of discharge from the hospital | Rs. 2 lakh |
| IB | Death following sterilization within 8-30 days from the date of discharge from the hospital | Rs. 50,000/- |
| IC | Failure of sterilization | Rs. 30,000/- |
| ID | Cost of treatment in hospital and up to 60 days arising out of complication following sterilization operation (inclusive of complication during process of sterilization operation) from the date of discharge. | Actual not exceeding Rs. 25,000/- |
| SECTION II : Empanelled Doctors under Public and Accredited Private/NGO Sector and Health Facilities under Public and Accredited Private / NGO sector |  |  |
| II | Indemnity coverage up to 4 cases of litigations per doctor and per health facility in a year | Upto Rs.2 lakh per case of litigation |

- Breakup of the Indemnity coverage

| Sl.no | Coverage | Beneficiary/ies | Amount (in rupees) |
| --- | --- | --- | --- |
| 1. | Death following sterilization (inclusive of death during process of sterilization operation) in hospital or within 7 days from the date of discharge from the hospital | 0 | 0 |
| 2. | Failure of sterilization | 10 @ Rs. 30,000 (2 at Aizawl ‘E’ Dist, 1 at Aizawl ‘W’ Dist, 1 at Champhai Dist, 1 at Kolasib Dist, 1 at LawngtlaiDist, 1 at Lunglei Dist, 1 at MamitDist, 1 at Serchhip Dist& 1 at Saiha Dist) | 3,00,000 |
| 3. | Cost of treatment in hospital and up to 60 days arising out of complication following sterilization operation (inclusive of complication during process of sterilization operation) from the date of discharge | 0 | 0 |
| 4. | Indemnity coverage up to 4 cases of litigations per doctor and per health facility in a year | @ Rs. 2 Lakhs | 200,000 |
| TOTAL |  |  | 500,000 |

HSS 19– 204: Scheme: IEC & Printing (Incl. RCH, NDCP, NCD, HSS-Urban, HSS-Rural)

Component: IEC & Printing

Particulars: World Population Fortnight celebration

Total Estimation: State Rs. 42,000 + Districts Rs. 4,80,000 (12 x 40,000) = Rs. 5,22,000/-

| 1. | LAUNCHING AT STATE | REFRESHMENT @ Rs. 100 for 80 participants | Rs. 8,000 |
| --- | --- | --- | --- |
| 2. |  | POSTERS @ Rs. 50 x 650 nos | Rs. 32,500 |
|  |  | BANNER PRINTING | Rs. 1,000 |
|  |  | Contingencies | Rs 500 |
| TOTAL |  |  | Rs. 42,000 |

HSS 19– 204: Scheme: IEC & Printing (Incl. RCH, NDCP, NCD, HSS-Urban, HSS-Rural)

Component: IEC & Printing

Particulars: Observation of World Vasectomy Fortnight

Male participation in improving the reproductive health of a couple is crucial. Vasectomy is one of the safest and most effective contraceptive method having very low complication and failure rates. Vasectomy is a very important act where male participation in Family Planning can be achieved. World Vasectomy Day will be observed on 7th November 2017 with a theme provided by the GOI. Launching at State Level will be observed and IEC in the form of Short Video clip will be broadcasted to attract clients throughout the whole fortnight. 50 participants are expected to be invited in the launching. Budget estimated (with fund breakage) for Observation of World Vasectomy Fortnight for both the State and Districts is Rs.1,53,000 (One Lakh Fifty Three Thousand Rupees only) and is tabulated below:-

| Sl.no |  | ACTIVITIES |  | AMOUNT (in Rs.) |
| --- | --- | --- | --- | --- |
| 1. | STATE LEVEL | LAUNCHING (Hall Rent, Refreshment, misc) |  | 5,000 |
| 2. |  | BANNER x2 |  | 2400 |
| 3. |  | IEC | Broadcasting of short video clip = Rs. 34,400 | 37,600 |
|  |  |  | Posters @ Rs. 40 upto PHC i.e 76 facilities + State = 80 * 40= Rs. 3200 |  |
| TOTAL |  |  |  | 45,000 |
| 1. | DISTRICT LEVEL | LAUNCHING (Hall rent, Refreshment ,etc ) |  | 2000 |
| 2. |  | BANNER |  | 1000 |
| 3. |  | AWARENESS GENERATION (Miking/ Wall Writing etc) |  | 3500 |
| 4. |  | POL FOR MONITORING |  | 2000 |
| 5. |  | MISCELLENOUS (Printing of Report format, Ribbon, etc) |  | 500 |
| TOTAL |  |  |  | 9,000 |

Total Estimation: State Rs. 45,000 + Districts Rs. 108,000 (12 x 9,000) = Rs.1,53,000

RCH 6 - Sl. no. 50: Other Family Planning Components

Component: Others including operating costs (OOC)

Particulars: POL for family Planning / Others

Total estimated budget: Rs. 3,00,000/-

Monitoring family planning activities from the state to the district level is essential for effective implementation, identifying gaps, ensuring accountability, and tailoring interventions. It enables evidence-based decision-making, helps achieve desired outcomes, and ultimately contributes to improving reproductive health and well-being of individuals and communities.

| Sl. No | ACTIVITY |  | DISTRICT | UNIT COST to &fro | Distance in km | NO. OF UNITS | Amount (Rs.) |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Tinghmun |  | Aizawl East | 25 | 170 | 2 | 8,500 |
| 2 | Lungsen |  | Lunglei | 25 | 130 | 2 | 6,500 |
| 3 | Hriphaw |  | Mamit | 25 | 160 | 2 | 8,000 |
| 4 | New Eden |  | Mamit | 25 | 150 | 2 | 7,500 |
| 5 | Phura |  | Siaha | 25 | 320 | 2 | 16,000 |
| 6 | Vaseitlang |  | Lawngtlai | 25 | 310 | 2 | 15,500 |
| 7 | Hmunlai |  | Lawngtlai | 25 | 260 | 2 | 13,000 |
| 8 | Parva |  | Lawngtlai | 25 | 292 | 2 | 14,600 |
| 9 | Night Halt charge (1000x8) |  | All Districts | 8000 |  | 2 | 16,000 |
| 10 | Accomodation andFood (1100 x 9 persons) |  | All Districts | 15300 |  | 8 nights | 1,22,400 |
| 11 | DA (1000 x 9 persons) |  | All Districts | 9000 |  | 8 | 72,000 |
|  |  | TOTAL |  |  |  |  | 3,00,000 |

Total no. of team:  1 (9 members per team including State Programme Officer)

No. of visits: 8

Vehicle Hiring:  2 vehicles x 224 km (average) x 25 per km = Rs. 11,200/- + Night Halt (1000 x 2 vehicles) Rs. 2,000/- = Rs. 13,200/- per visit

Accommodation: 9 members x 1100 per night x 1 night per visit = Rs. 9,900 + Food (600 per member x 9) Rs. 5400= Rs. 15,300/- per visit

DA: 1000 x 9 members = 9,000/- per visit

| Particulars | Cost per visit | No. of visits | Amount |
| --- | --- | --- | --- |
| Vehicle Hiring inc night halt | 13,200 | 8 | 1,05,600/- |
| Accomodation + food | 15,300 | 8 | 1,22,400/- |
| DA | 9,000 | 8 | 72,000/- |
|  | 37,500 | TOTAL | 3,00,000/- |

Cost per visit Rs. 37,500/- x 8 visits = Rs. 3 lakhs

HSS 17– 202: Scheme: ASHA Incentives (Incl. RCH, NDCP, NCD, HSS-Urban, HSS-Rural)

Component: ASHA incentives

Particulars: ASHA incentive under ESB scheme for promoting spacing of births

Total estimated budget: Rs. 50,000/-

| Component/ Activities | Incentive Amount proposed per ASHA (A) | Measurable Output (B) | Target Population | Total Amount Proposed (in lakhs) (A*B/100000) | Remarks |
| --- | --- | --- | --- | --- | --- |
| ASHA incentive under ESB scheme for promoting spacing of births | 500 | 100 | 1282835 | 0.5 | Ongoing activity: Proposed @500/- per performance/motivating mother for spacing of 3 years between 2 babies. |

HSS 17– 202: Scheme: ASHA Incentives (Incl. RCH, NDCP, NCD, HSS-Urban, HSS-Rural)

Component: ASHA incentives

Particulars: ASHA Incentive under ESB scheme for promoting adoption of limiting method upto two children

Total Estimated Budget; Rs. 50000/-

| Component/ Activities | Incentive Amount proposed per ASHA (A) | Measurable Output (B) | Target Population | Total Amount Proposed (in lakhs) (A*B/100000) | Remarks |
| --- | --- | --- | --- | --- | --- |
| ASHA Incentive under ESB scheme for promoting adoption of limiting method up to two children | 1000 | 50 | 1282835 | 0.5 | Ongoing activity: Proposed @ 1000/- per performance/motivating mother for permanent sterilization after having 2 children. |

HSS 19– 204: Scheme: IEC & Printing (Incl. RCH, NDCP, NCD, HSS-Urban, HSS-Rural)

Component: IEC & Printing

Particulars: IEC under FP

Media Mix of Mid Media/Mass Media

- Video translation, dubbing and relay @ Rs 6000

For 2 videos =2 x 6000=Rs12,000/-

- Broadcasting of FP video and radio spots

- DDK @ 2400 x 2 Days x 12 months = Rs 57600/-

- AIR @ Rs 1800 x 2 Days x 12 months = Rs 43200/-

Total amount proposed for IEC under Family Planning: Rs 1,12,800/-

HSS 19– 204: Scheme: IEC & Printing (Incl. RCH, NDCP, NCD, HSS-Urban, HSS-Rural)

Component: IEC & Printing

Particulars: Printing of IUCD cards, MPA cards, FP manuals & guidelines, etc

Budget estimated for Printing of IUCD cards, PPIUCD cards, Sterilisation certificate, consent and post operation card, FPIS claim form, etcis Rs. 92,948/- only and is tabulated below:

| Sl.no | Particulars | No. of copies | Rate (in Rs.) | Total amount (In Rs.) |
| --- | --- | --- | --- | --- |
| 1. | IUCD cards | 2535 | 4 | 10140 |
| 2. | PPIUCD cards | 1090 | 4 | 4360 |
| 3 | Inj.MPA cards | 6142 | 4 | 24568 |
| 3. | Sterilisation Certificate | 2200 | 2 | 4400 |
| 4. | Claim form for FPIS | 10 for each district i.e 90 | 4 | 360 |
| 5. | Application cum consent form for Sterilisation | 2200 | 6 | 13200 |
| 6. | Medical record & checklist for male/female sterilisation | 2200 | 12 | 26400 |
| 7. | Postoperative instruction card | 2200 | 4 | 8800 |
| 8. | Report on Complications/Failures following sterilisation | 10 for each district i.e 90 | 8 | 720 |
|  | TOTAL |  |  | 92948 |

FP QAC Meeting

Budget estimated for FP QAC Meeting (including FPIS) is Rs. 30,800 (Rupees Thirty Thousand Eight Hundred) only and is tabulated below:-

| Refreshment | Rate ( in Rs.) | No of days | No of participants | no of committee | Total( in Rs.) |
| --- | --- | --- | --- | --- | --- |
| State | 100 | 1 day | 10 | 2 times | 2000 |
| Aizawl East | 100 | 1 day | 8 | 4 times | 3200 |
| Aizawl West | 100 | 1 day | 8 | 4 times | 3200 |
| Champhai | 100 | 1 day | 8 | 4 times | 3200 |
| Kolasib | 100 | 1 day | 8 | 4 times | 3200 |
| Lawngtlai | 100 | 1 day | 8 | 4 times | 3200 |
| Lunglei | 100 | 1 day | 8 | 4 times | 3200 |
| Mamit | 100 | 1 day | 8 | 4 times | 3200 |
| Serchhip | 100 | 1 day | 8 | 4 times | 3200 |
| Siaha | 100 | 1 day | 8 | 4 times | 3200 |
| Hnahthial | 100 | 1 day | 8 | 4 times | 3200 |
| Saitual | 100 | 1 day | 8 | 4 times | 3200 |
| Khawzawl | 100 | 1 day | 8 | 4 times | 3200 |
| TOTAL |  |  |  |  | 40400 |

| PROGRAMME MANAGEMENT HSS.11(Sl.194) |  |  |
| --- | --- | --- |
| Mobility Support for State/District PMU | State | Rs. 15,43,169/- |
|  | District | Rs. 12,56,800 /- |
|  | Sub- Total | Rs. 27,99,969 /- |
| Review Meeting | State Level | Rs. 6,89,640/- |
| Office Expenditure | State | Rs. 1,25,26,860 /- |
|  | District | Rs. 66,22,947 /- |
|  | Sub- Total | Rs. 1,91,49,807 /- |
| Programme Management Total: |  | Rs. 2,47,02,396/- |

HSS 11 -  Sl. no. 194: Planning and Program Management

Component: Planning & M & E

Particulars: Mobility Support for SPMU/State

  - State		-	Rs. 15,43,169/-

  - District	-	Rs. 12,56,800/-

Total		-	Rs. 27,99,969/-

STATE MONITORING AND SUPERVISION 2026-27

| Aizawl East District |  |  | Kms | POL | DA | Accomodation | Fooding | Night Halt | Nos of Day |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Aizawl | Sakawrdai | 186 | 186 | 5000 | 30000 | 20000 | 2 | 1 |
|  | Sakawrdai | Tinghmun SC | 19 | 19 | 5000 |  |  |  | 1 |
|  |  | Sakawrdai CHC |  |  |  |  |  |  |  |
|  |  | Sakawrdai SC |  |  |  |  |  |  |  |
|  |  | Khawruhlian PHC |  |  |  |  |  |  |  |
|  |  | Darlawn PHC |  |  |  |  |  |  |  |
|  |  | Ratu PHC |  |  |  |  |  |  |  |
|  | Sakawrdai | Aizawl | 186 | 186 | 5000 |  | 5000 |  | 1 |
|  |  |  | TOTAL KMs | 391 |  |  |  |  |  |
|  |  |  | ₹. | 9775 | 15000 | 30000 | 25000 | 2 | 3 |
|  |  |  | TOTAL | 79775 |  |  |  |  |  |
| Aizawl East District |  |  | Kms | POL | DA | Accomodation | Fooding | Night Halt | Nos of Day |
|  |  | Sihphir UPHC | 17 | 17 | 5000 |  | 5000 |  | 1 |
|  |  | Sihphir SC |  |  |  |  |  |  |  |
|  |  | Durtlang Mel-5 SC |  |  |  |  |  |  |  |
|  |  | Zemabawk UPHC |  |  |  |  |  |  |  |
|  |  | Zemabawk SC |  |  |  |  |  |  |  |
|  |  | Thuampui SC |  |  |  |  |  |  |  |
|  |  |  | TOTAL KMs | 17 |  |  |  |  |  |
|  |  |  | ₹. | 425 | 5000 | 0 | 5000 | 0 | 1 |
|  |  |  | TOTAL | 10425 |  |  |  |  |  |
| Aizawl West District |  |  | Kms | POL | DA | Accomodation | Fooding | Night Halt | Nos of Day |
|  | Aizawl | Sialsuk | 65 | 130 | 5000 |  | 5000 |  | 1 |
|  |  | Sialsuk PHC |  |  |  |  |  |  |  |
|  |  | Sialsuk SC |  |  |  |  |  |  |  |
|  |  | Hmuifang SC |  |  |  |  |  |  |  |
|  |  | Aibawk PHC |  |  |  |  |  |  |  |
|  |  | ZMCH |  |  |  |  |  |  |  |
|  | ZMCH | Aizawl |  |  |  |  |  |  |  |
|  |  |  | TOTAL KMs | 130 |  |  |  |  |  |
|  |  |  | ₹. | 3250 | 5000 | 0 | 5000 | 0 | 1 |
|  |  |  | TOTAL | 13250 |  |  |  |  |  |
| Aizawl West District |  |  | Kms | POL | DA | Accomodation | Fooding | Night Halt | Nos of Day |
|  | Aizawl | Lengpui | 37 | 74 | 5000 |  | 5000 |  | 1 |
|  |  | Lengpui CHC |  |  |  |  |  |  |  |
|  |  | Sairang PHC |  |  |  |  |  |  |  |
|  |  | Sairang SC |  |  |  |  |  |  |  |
|  |  | Tanhril SC |  |  |  |  |  |  |  |
|  |  | Chhawlhhmun UPHC |  |  |  |  |  |  |  |
|  |  |  | TOTAL KMs | 74 |  |  |  |  |  |
|  |  |  | ₹. | 1850 | 5000 | 0 | 5000 | 0 | 1 |
|  |  |  | TOTAL | 11850 |  |  |  |  |  |
| Champhai District |  |  | Kms | POL | DA | Accomodation | Fooding | Night Halt | Nos of Day |
|  | Aizawl | Khawkawn | 175 | 175 | 5000 | 10000 | 10000 | 1 | 1 |
|  |  | Farkawn PHC |  |  |  |  |  |  |  |
|  |  | Farkawn SC |  |  |  |  |  |  |  |
|  |  | Khankawn SC |  |  |  |  |  |  |  |
|  | Khankawn | Champhai | 108 | 108 | 5000 | 10000 | 10000 | 1 | 1 |
|  |  | Vaphai SC |  |  |  |  |  |  |  |
|  |  | Samthang SC |  |  |  |  |  |  |  |
|  |  | Khawbung PHC |  |  |  |  |  |  |  |
|  |  | Khungleng SC |  |  |  |  |  |  |  |
|  |  | Kelkang SC |  |  |  |  |  |  |  |
|  | Champhai | Hnahlan | 55 | 55 | 5000 | 10000 | 10000 | 1 | 1 |
|  |  | Zote SC |  |  |  |  |  |  |  |
|  |  | Ngur SC |  |  |  |  |  |  |  |
|  |  | Hnahlan PHC |  |  |  |  |  |  |  |
|  |  | Hnahlan SC |  |  |  |  |  |  |  |
|  | Hnahlan | Vaikhawtlang | 33 | 33 | 5000 | 10000 | 10000 | 1 | 1 |
|  |  | Vaikhawtlang SC |  |  |  |  |  |  |  |
|  |  | Khuangphah SC |  |  |  |  |  |  |  |
|  | Khuangphah | Tualcheng | 40 | 40 |  |  |  |  |  |
|  |  | Tualcheng SC |  |  |  |  |  |  |  |
|  | Tualcheng | Hnahlan | 20 | 20 |  |  |  |  |  |
|  | Hnahlan | Aizawl | 207 | 207 | 5000 |  | 5000 |  | 1 |
|  |  |  | TOTAL KMs | 638 |  |  |  |  |  |
|  |  |  | ₹. | 15950 | 25000 | 40000 | 45000 | 4 | 5 |
|  |  |  | TOTAL | 125950 |  |  |  |  |  |
| Hnahthial District |  |  | Kms | POL | DA | Accomodation | Fooding | Night Halt | Nos of Day |
|  | Aizawl | Hnahthial | 153 | 153 | 5000 | 10000 | 10000 | 1 | 1 |
|  |  | Rawpui SC |  |  |  |  |  |  |  |
|  |  | Pangzawl PHC |  |  |  |  |  |  |  |
|  |  | Pangzawl SC |  |  |  |  |  |  |  |
|  |  | Hnahthial SC |  |  |  |  |  |  |  |
|  | Hnahthial | Bualpui H | 65 | 65 | 5000 | 10000 | 10000 | 1 | 1 |
|  |  | Tarpho SC |  |  |  |  |  |  |  |
|  |  | Cherhlun PHC |  |  |  |  |  |  |  |
|  |  | Cherhlun SC |  |  |  |  |  |  |  |
|  |  | Thingsai PHC |  |  |  |  |  |  |  |
|  |  | Thingsai SC |  |  |  |  |  |  |  |
|  |  | Bualpui H SC |  |  |  |  |  |  |  |
|  | Bualpui H | Aizawl | 213 | 213 | 5000 |  | 5000 |  | 1 |
|  |  |  | TOTAL KMs | 431 |  |  |  |  |  |
|  |  |  | ₹. | 10775 | 15000 | 20000 | 25000 | 2 | 3 |
|  |  |  | TOTAL | 70775 |  |  |  |  |  |
| Hnahthial District |  |  | Kms | POL | DA | Accomodation | Fooding | Night Halt | Nos of Day |
|  | Aizawl | S. Vanlaiphai | 205 | 205 | 10000 | 20000 | 15000 | 2 | 2 |
|  |  | Tuipui D SC |  |  |  |  |  |  |  |
|  |  | Darzo SC |  |  |  |  |  |  |  |
|  |  | S. Vanlaiphai PHC |  |  |  |  |  |  |  |
|  |  | S. Vanlaiphai SC |  |  |  |  |  |  |  |
|  | S. Vanlaiphai | Muallianpui | 24 | 24 |  |  |  |  |  |
|  |  | Muallianpui SC |  |  |  |  |  |  |  |
|  | S. Vanlaiphai | Aizawl | 205 | 205 | 5000 |  | 5000 |  | 1 |
|  |  |  | TOTAL KMs | 434 |  |  |  |  |  |
|  |  |  | ₹. | 10850 | 15000 | 20000 | 20000 | 2 | 3 |
|  |  |  | TOTAL | 65850 |  |  |  |  |  |
| Khawzawl District |  |  | Kms | POL | DA | Accomodation | Fooding | Night Halt | Nos of Day |
|  | Aizawl | Khawzawl | 128 | 128 | 5000 | 20000 | 20000 | 2 | 1 |
|  |  | Dulte SC |  |  |  |  |  |  |  |
|  |  | Kawlkulh PHC |  |  |  |  |  |  |  |
|  |  | Kawlkulh SC |  |  |  |  |  |  |  |
|  |  | Khawzawl SC |  |  |  |  |  |  |  |
|  | Khawzawl | Rabung | 35 | 35 | 5000 |  |  |  | 1 |
|  |  | Rabung PHC |  |  |  |  |  |  |  |
|  |  | Rabung SC |  |  |  |  |  |  |  |
|  | Rabung | Chawngtlai | 49 | 49 |  |  |  |  |  |
|  |  | Chawngtlai SC |  |  |  |  |  |  |  |
|  | Chawngtlai | Khawzawl | 14 | 14 |  |  |  |  |  |
|  | Khawzawl | Biate | 59 | 59 | 5000 | 10000 | 10000 | 1 | 1 |
|  |  | New Chalrang SC |  |  |  |  |  |  |  |
|  |  | Khawhai PHC |  |  |  |  |  |  |  |
|  |  | Khawhai SC |  |  |  |  |  |  |  |
|  |  | Sialhawk PHC |  |  |  |  |  |  |  |
|  |  | Sialhawk SC |  |  |  |  |  |  |  |
|  |  | Biate SC |  |  |  |  |  |  |  |
|  | Biate | Aizawl | 185 | 185 | 5000 |  | 5000 |  | 1 |
|  |  |  | TOTAL KMs | 470 |  |  |  |  |  |
|  |  |  | ₹. | 11750 | 20000 | 30000 | 35000 | 3 | 4 |
|  |  |  | TOTAL | 96750 |  |  |  |  |  |
| Kolasib District |  |  | Kms | POL | DA | Accomodation | Fooding | Night Halt | Nos of Day |
|  | Aizawl | Bukpui | 64 | 64 | 5000 | 10000 | 10000 | 1 | 1 |
|  |  | Lungdai PHC |  |  |  |  |  |  |  |
|  |  | Lungdai SC |  |  |  |  |  |  |  |
|  |  | Serkhan SC |  |  |  |  |  |  |  |
|  |  | Nisapui SC |  |  |  |  |  |  |  |
|  |  | Lungmuat SC |  |  |  |  |  |  |  |
|  |  | Bukpui SC |  |  |  |  |  |  |  |
|  | Bukpui | Vairengte | 88 | 88 | 5000 | 10000 | 10000 | 1 | 1 |
|  |  | Bukpui PHC |  |  |  |  |  |  |  |
|  |  | Bukpui SC |  |  |  |  |  |  |  |
|  |  | N. Hlimen SC |  |  |  |  |  |  |  |
|  |  | Saipum SC |  |  |  |  |  |  |  |
|  |  | Saiphai SC |  |  |  |  |  |  |  |
|  |  | Phainuam SC |  |  |  |  |  |  |  |
|  | Vairengte | Bairabi | 72 | 72 | 5000 | 10000 | 10000 | 1 | 1 |
|  |  | Phaisen SC |  |  |  |  |  |  |  |
|  |  | Buhchangphai SC |  |  |  |  |  |  |  |
|  |  | Pangbalkawn SC |  |  |  |  |  |  |  |
|  |  | Bairabi PHC |  |  |  |  |  |  |  |
|  |  | Bairabi SC |  |  |  |  |  |  |  |
|  | Bairabi | Kolasib | 36 | 36 |  |  |  |  |  |
|  | Kolasib | Aizawl | 78 | 78 | 5000 |  | 10000 |  | 1 |
|  |  | Kawnpui PHC |  |  |  |  |  |  |  |
|  |  | Kawnpui SC |  |  |  |  |  |  |  |
|  |  |  | TOTAL KMs | 338 |  |  |  |  |  |
|  |  |  | ₹. | 8450 | 20000 | 30000 | 40000 | 3 | 4 |
|  |  |  | TOTAL | 98450 |  |  |  |  |  |
| Lawngtlai District |  |  | Kms | POL | DA | Accomodation | Fooding | Night Halt | Nos of Day |
|  | Aizawl | Bungtlang 'S' | 311 | 311 | 5000 | 30000 | 35000 | 4 | 1 |
|  |  | Bungtlang 'S' PHC |  |  |  |  |  |  |  |
|  |  | Bungtlang 'S' SC |  |  |  |  |  |  |  |
|  | Bungtlang 'S' | Hmawngbuchhuah | 32 | 32 | 5000 |  |  |  | 1 |
|  |  | Ngengpuitlang SC |  |  |  |  |  |  |  |
|  |  | Tuithumhnar SC |  |  |  |  |  |  |  |
|  |  | Hruitezawl SC |  |  |  |  |  |  |  |
|  |  | Hmawngbuchhuah |  |  |  |  |  |  |  |
|  | Hmawngbuchhuah | Bungtlang 'S' |  |  |  |  |  |  |  |
|  | Bungtlang 'S' | Parva | 70 | 70 | 5000 |  |  |  | 1 |
|  |  | M. Kawnpui SC |  |  |  |  |  |  |  |
|  |  | Vaseitlang SC |  |  |  |  |  |  |  |
|  |  | Lawngpuighat SC |  |  |  |  |  |  |  |
|  |  | Damdep SC |  |  |  |  |  |  |  |
|  |  | Parva SC |  |  |  |  |  |  |  |
|  | Parva | Bungtlang 'S' SC |  |  |  |  |  |  |  |
|  | Bungtlang 'S' | Lawngtlai | 86 | 86 | 5000 | 10000 | 10000 | 1 | 1 |
|  |  | Diltlang 'S' SC |  |  |  |  |  |  |  |
|  |  | Khawmawi SC |  |  |  |  |  |  |  |
|  |  | Mampui SC |  |  |  |  |  |  |  |
|  | Lawngtlai | Aizawl | 243 | 243 | 5000 |  | 5000 |  | 1 |
|  |  |  | TOTAL KMs | 742 |  |  |  |  |  |
|  |  |  | ₹. | 18550 | 25000 | 40000 | 50000 | 5 | 5 |
|  |  |  | TOTAL | 133550 |  |  |  |  |  |
| Lunglei District |  |  | Kms | POL | DA | Accomodation | Fooding | Night Halt | Nos of Day |
|  | Aizawl | Bunghmun 'W' | 180 | 180 | 5000 | 10000 | 10000 | 1 | 1 |
|  |  | Darlung SC |  |  |  |  |  |  |  |
|  |  | S. Khawlek SC |  |  |  |  |  |  |  |
|  |  | Buarpui PHC |  |  |  |  |  |  |  |
|  |  | Buarpui SC |  |  |  |  |  |  |  |
|  |  | Changpui SC |  |  |  |  |  |  |  |
|  |  | Thenhlum SC |  |  |  |  |  |  |  |
|  | Bunghmun 'W' | Lungsen | 140 | 140 | 5000 | 10000 | 10000 | 1 | 1 |
|  |  | Bunghmun 'W' PHC |  |  |  |  |  |  |  |
|  |  | Tuisenchhuah SC |  |  |  |  |  |  |  |
|  |  | Zawlpui SC |  |  |  |  |  |  |  |
|  |  | Putlungasih SC |  |  |  |  |  |  |  |
|  |  | Phairuangkai SC |  |  |  |  |  |  |  |
|  | Lungsen | Lunglei | 114 | 114 | 5000 | 10000 | 10000 | 1 | 1 |
|  |  | Lungrang 'S' SC |  |  |  |  |  |  |  |
|  |  | Lunglei |  |  |  |  |  |  |  |
|  |  | Hauruang SC |  |  |  |  |  |  |  |
|  | Lunglei | Aizawl | 169 | 169 | 5000 |  | 5000 |  | 1 |
|  |  |  | TOTAL KMs | 603 |  |  |  |  |  |
|  |  |  | ₹. | 15075 | 20000 | 30000 | 35000 | 3 | 4 |
|  |  |  | TOTAL | 100075 |  |  |  |  |  |
| Mamit District |  |  | Kms | POL | DA | Accomodation | Fooding | Night Halt | Nos of Day |
|  | Aizawl | Marpara | 161 | 161 | 5000 | 10000 | 10000 | 1 | 1 |
|  |  | Marpara PHC |  |  |  |  |  |  |  |
|  |  | Marpara SC |  |  |  |  |  |  |  |
|  |  | Pukzing SC |  |  |  |  |  |  |  |
|  |  | Phuldungsei PHC |  |  |  |  |  |  |  |
|  |  | Phuldungsei SC |  |  |  |  |  |  |  |
|  | Marpara | Zawlnuam | 172 | 172 | 5000 | 10000 | 10000 | 1 | 1 |
|  |  | Lallen SC |  |  |  |  |  |  |  |
|  |  | W. Phaileng PHC |  |  |  |  |  |  |  |
|  |  | W. Phaileng SC |  |  |  |  |  |  |  |
|  |  | Damparengpui SC |  |  |  |  |  |  |  |
|  |  | W. Bunghmun SC |  |  |  |  |  |  |  |
|  |  | Kawrtethawveng PHC |  |  |  |  |  |  |  |
|  |  | Kawrtethawveng SC |  |  |  |  |  |  |  |
|  | Zawlnuam | Hriphaw | 30 | 30 | 5000 | 10000 | 10000 | 1 | 1 |
|  |  | Zawlnuam PHC |  |  |  |  |  |  |  |
|  |  | Zawlnuam SC |  |  |  |  |  |  |  |
|  |  | Hriphaw SC |  |  |  |  |  |  |  |
|  |  | Zamuang SC |  |  |  |  |  |  |  |
|  |  | Rengdil SC |  |  |  |  |  |  |  |
|  |  | Kawrthah CHC |  |  |  |  |  |  |  |
|  |  | Kawrthah SC |  |  |  |  |  |  |  |
|  |  | Tuidam SC |  |  |  |  |  |  |  |
|  |  | Darlak SC |  |  |  |  |  |  |  |
|  | Hriphaw | Mamit | 72 | 72 |  |  |  |  |  |
|  | Mamit | Aizawl | 87 | 87 | 5000 |  | 5000 |  | 1 |
|  |  |  | TOTAL KMs | 522 |  |  |  |  |  |
|  |  |  | ₹. | 13050 | 20000 | 30000 | 35000 | 3 | 4 |
|  |  |  | TOTAL | 98050 |  |  |  |  |  |
| Saitual District |  |  | Kms | POL | DA | Accomodation | Fooding | Night Halt | Nos of Day |
|  | Aizawl | N Khawlek | 151 | 151 | 5000 | 10000 | 10000 | 1 | 1 |
|  |  | Suangpuilawn PHC |  |  |  |  |  |  |  |
|  |  | Suangpuilawn SC |  |  |  |  |  |  |  |
|  |  | Vanbawng SC |  |  |  |  |  |  |  |
|  |  | N. Khawlek SC |  |  |  |  |  |  |  |
|  | N Khawlek | Suangpuilawn | 22 | 22 |  |  |  |  |  |
|  | Suangpuilawn | Daido | 94 | 94 | 5000 | 10000 | 10000 | 1 | 1 |
|  |  | Daido SC |  |  |  |  |  |  |  |
|  |  | NE Tlangnuam SC |  |  |  |  |  |  |  |
|  |  | Khawlian SC |  |  |  |  |  |  |  |
|  |  | Phuaibuang PHC |  |  |  |  |  |  |  |
|  |  | Phuaibuang SC |  |  |  |  |  |  |  |
|  | Daido | Phuaibuang | 21 | 21 |  |  |  |  |  |
|  | Phuaibuang | Saitual | 95 | 95 | 5000 | 10000 | 10000 | 1 | 1 |
|  |  | Phullen PHC |  |  |  |  |  |  |  |
|  |  | Phullen SC |  |  |  |  |  |  |  |
|  |  | Thanglailung SC |  |  |  |  |  |  |  |
|  |  | Tualbung SC |  |  |  |  |  |  |  |
|  |  | Sihfa SC |  |  |  |  |  |  |  |
|  | Saitual | Maite | 35 | 35 | 5000 |  | 5000 |  | 1 |
|  |  | Maite SC |  |  |  |  |  |  |  |
|  |  | Lenchim SC |  |  |  |  |  |  |  |
|  |  | Rulchawm SC |  |  |  |  |  |  |  |
|  |  | Keifang SC |  |  |  |  |  |  |  |
|  |  | Saitual SC |  |  |  |  |  |  |  |
|  | Maite | Aizawl | 106 | 106 |  |  |  |  |  |
|  |  |  | TOTAL KMs | 524 |  |  |  |  |  |
|  |  |  | ₹. | 13100 | 20000 | 30000 | 35000 | 3 | 4 |
|  |  |  | TOTAL | 98100 |  |  |  |  |  |
| Serchhip District |  |  | Kms | POL | DA | Accomodation | Fooding | Night Halt | Nos of Day |
|  | Aizawl | Khawbel | 111 | 111 | 5000 | 10000 | 10000 | 1 | 1 |
|  |  | Khawbel SC |  |  |  |  |  |  |  |
|  |  | Hmuntha SC |  |  |  |  |  |  |  |
|  | Khawbel | Hualtu | 61 | 61 |  |  |  |  |  |
|  |  | Hualtu SC |  |  |  |  |  |  |  |
|  | Hualtu | Serchhip | 28 | 28 |  |  |  |  |  |
|  |  | Chhingchhip PHC |  |  |  |  |  |  |  |
|  |  | Chhingchhip SC |  |  |  |  |  |  |  |
|  |  | Chhiahtlang SC |  |  |  |  |  |  |  |
|  | Serchhip | E. Lungdar | 82 | 82 | 5000 | 10000 | 10000 | 1 | 1 |
|  |  | Sailulak SC |  |  |  |  |  |  |  |
|  |  | Leng SC |  |  |  |  |  |  |  |
|  |  | E. Lungdar PHC |  |  |  |  |  |  |  |
|  |  | E. Lungdar SC |  |  |  |  |  |  |  |
|  | E. Lungdar | Lungkawlh | 41 | 41 | 5000 | 10000 | 10000 | 1 | 1 |
|  |  | Lungkawlh SC |  |  |  |  |  |  |  |
|  | Lungkawlh | N Vanlaiphai | 11 | 11 |  |  |  |  |  |
|  |  | N Mualcheng SC |  |  |  |  |  |  |  |
|  |  | N Vanlaiphai PHC |  |  |  |  |  |  |  |
|  |  | N Vanlaiphai SC |  |  |  |  |  |  |  |
|  | N. Vanlaiphai | Ngentiang | 50 | 50 | 5000 | 10000 | 10000 | 1 | 1 |
|  |  | Ngentiang PHC |  |  |  |  |  |  |  |
|  |  | Lungpho SC |  |  |  |  |  |  |  |
|  |  | Rullam SC |  |  |  |  |  |  |  |
|  |  | Chhawrtui |  |  |  |  |  |  |  |
|  | Ngentiang | Aizawl | 155 | 155 | 5000 |  | 5000 |  | 1 |
|  |  |  | TOTAL KMs | 539 |  |  |  |  |  |
|  |  |  | ₹. | 13475 | 25000 | 40000 | 45000 | 4 | 5 |
|  |  |  | TOTAL | 123475 |  |  |  |  |  |
| Siaha District |  |  | Kms | POL | DA | Accomodation | Fooding | Night Halt | Nos of Day |
|  | Aizawl | Phura | 324 | 324 | 5000 | 20000 | 20000 | 2 | 1 |
|  | Phura | Tongkolong | 22 | 22 | 5000 |  |  |  | 1 |
|  |  | Tongkolong SC |  |  |  |  |  |  |  |
|  |  | Phura PHC |  |  |  |  |  |  |  |
|  |  | Phura SC |  |  |  |  |  |  |  |
|  | Phura | Tuipang | 57 | 57 | 5000 | 10000 | 10000 | 1 | 1 |
|  |  | Vahai SC |  |  |  |  |  |  |  |
|  |  | Laki SC |  |  |  |  |  |  |  |
|  |  | Zawngling SC |  |  |  |  |  |  |  |
|  |  | Tuipang PHC |  |  |  |  |  |  |  |
|  | Tuipang | Chapui | 43 | 43 | 5000 | 10000 | 10000 | 1 | 1 |
|  |  | Chapui SC |  |  |  |  |  |  |  |
|  | Chapui | Chakhang | 85 | 85 |  |  |  |  |  |
|  |  | Chakhang PHC |  |  |  |  |  |  |  |
|  |  | Chakhang SC |  |  |  |  |  |  |  |
|  | Chakhang | Siaha | 73 | 73 | 5000 | 10000 | 10000 | 1 | 1 |
|  |  | Siata SC |  |  |  |  |  |  |  |
|  |  | Chhuarlung PHC |  |  |  |  |  |  |  |
|  |  | Chhuarlung SC |  |  |  |  |  |  |  |
|  |  | Niawhtlang SC |  |  |  |  |  |  |  |
|  | Siaha | Aizawl | 300 | 300 | 5000 |  | 5000 |  | 1 |
|  |  |  | TOTAL KMs | 904 |  |  |  |  |  |
|  |  |  | ₹. | 22600 | 30000 | 50000 | 55000 | 5 | 6 |
|  |  |  | TOTAL | 157600 |  |  |  |  |  |
|  |  |  | TOTAL KMS | 6757 |  |  |  |  |  |
|  |  |  | ₹. | 168925 |  |  |  |  |  |
|  |  |  | TOTAL DA | 265000 |  |  |  |  |  |
|  |  |  | TOTAL ACCOMODATION | 390000 |  |  |  |  |  |
|  |  |  | TOTAL FOODING | 460000 |  |  |  |  |  |
|  |  |  | TOTAL NIGHT HALT | 39 |  |  |  |  |  |
|  |  |  | TOTAL DAYS | 53 |  |  |  |  |  |
|  |  |  | TOTAL VEHICLES HIRING | 236495 |  |  |  |  |  |
|  |  |  | TOTAL LUNCH | 15900 |  |  |  |  |  |
|  |  |  | GRAND TOTAL | 1543169 |  |  |  |  |  |

Mobility Support for District

| Sl. No | Name of District | Total Distance Kms from CMO Office | TA/DA (500 per day X 3 nos X Days) | Fooding& Lodging | POL | TOTAL |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Aizawl East | 2200 | 45000 | 20000 | 77000 | 144200 |
| 2 | Aizawl West | 800 | 30000 | 10000 | 28000 | 68800 |
| 3 | Champhai | 1600 | 45000 | 20000 | 56000 | 122600 |
| 4 | Hnahthial | 1400 | 30000 | 10000 | 49000 | 90400 |
| 5 | Khawzawl | 1200 | 30000 | 10000 | 42000 | 83200 |
| 6 | Kolasib | 1200 | 30000 | 10000 | 42000 | 83200 |
| 7 | Lawngtlai | 3400 | 45000 | 20000 | 119000 | 187400 |
| 8 | Lunglei | 2200 | 45000 | 20000 | 77000 | 144200 |
| 9 | Mamit | 1200 | 30000 | 10000 | 42000 | 83200 |
| 10 | Saitual | 1800 | 30000 | 10000 | 63000 | 104800 |
| 11 | Serchhip | 900 | 30000 | 10000 | 31500 | 72400 |
| 12 | Siaha | 900 | 30000 | 10000 | 31500 | 72400 |
|  | TOTAL | 18800 | 420000 | 160000 | 658000 | 1256800 |

District Total: Rs. 12,56,800

HSS 11 -  Sl. no. 194: Planning and Program Management

Component: Others including operating costs(OOC)

Particulars: Review Meeting under NHM

  - State		-	Rs. 6,89,640/-

State Level Annual Review Meeting on NHM / RMNCH+A

State Level Review Meeting at State Hqrs. to be conducted with Chief Medical Officer, Senior Medical Officer and Med. Superintendent from District Headquarter. Staff from District Programme Management Unit (DPMU) like District RCH Medical Officer, District Programme Manager, District Accounts Manager etc. may also attend the said Review Meeting.

Each District will prepare presentation on different activities under NHM / RMNCH+A and highlight their delicate point. After having open discussion with the other associate, they will try to make more desirable effort on their weaknesses by having Monitoring at each facility.

1 day Review Meeting will be sufficient for better achievement of the Programme. Estimated Budget Breakup as below:

| Sl. No. | Particulars |  | Amount in Rs. |
| --- | --- | --- | --- |
| 1 | Hall Rent | Rs. 3000 | 3000 |
| 2 | Banner |  | 1500 |
| 3 | Training Materials | Rs. 100x100 | 10000 |
| 4 | Refreshment | Rs.150x150 | 22500 |
| 5 | DA for participants(Dist Officers/State Officers/Consultants) | Rs. 1000x58 | 58000 |
| 6 | DA for participants (Dist staff/State staff) | Rs. 700x80 | 56000 |
| 7 | DA for Drivers | Rs. 200x36 | 7200 |
| 8 | TA | 212600+44800 | 257400 |
| 9 | Accommodation |  | 241200 |
|  |  | Total | 656800 |
| 10 | Contingencies | 5% of Total | 32840 |
|  | TOTAL BUDGET |  | 689640 |

Budget Breakup

Accomodation/Lodging

| Designation | Nos | Lodging | Days | Amount total |
| --- | --- | --- | --- | --- |
| CMO | 12 | 1000 | 3 | 36000 |
| Med Sups | 12 | 1000 | 3 | 36000 |
| SMO | 12 | 800 | 3 | 28800 |
| RCH MO | 12 | 800 | 3 | 28800 |
| DPM | 12 | 700 | 3 | 25200 |
| DEO / EA / DAM | 36 | 500 | 3 | 54000 |
| Drivers | 36 | 300 | 3 | 32400 |
|  | 90 |  | Total | 241200 |

Travel Allowance (TA)

| TA for CMO/DMS/SMO/DRCHO |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Districts |  | Distance in kms | Distance in kms(to n fro) |  | POL(1 ltr POL/6kms) |  | Amount in Rs. (POL @ Rs.100/ltr) |  | No. of CMO+DMS+SMO+DRCHO |  | Total TA in Rs. |
| Aizawl West |  | 0 | 0 |  | 0 |  |  |  | 4 |  | 0 |
| Aizawl East |  | 0 | 0 |  | 0 |  |  |  | 3 |  | 0 |
| Champhai |  | 194 | 388 |  | 65 |  | 6454 |  | 4 |  | 6500 |
| Hnahthial |  | 153 | 306 |  | 51 |  | 5064 |  | 2 |  | 5100 |
| Khawzawl |  | 128 | 256 |  | 43 |  | 4269 |  | 2 |  | 4300 |
| Kolasib |  | 83 | 166 |  | 28 |  | 2780 |  | 3 |  | 2800 |
| Lawngtlai |  | 296 | 592 |  | 99 |  | 9830 |  | 5 |  | 9900 |
| Lunglei |  | 175 | 350 |  | 58 |  | 5759 |  | 5 |  | 5800 |
| Mamit |  | 112 | 224 |  | 37 |  | 3674 |  | 4 |  | 3700 |
| Saitual |  | 70 | 140 |  | 23 |  | 2284 |  | 2 |  | 2300 |
| Serchhip |  | 112 | 224 |  | 37 |  | 3674 |  | 3 |  | 3700 |
| Siaha |  | 378 | 756 |  | 126 |  | 12511 |  | 4 |  | 12600 |
| TOTAL |  |  |  |  |  |  |  |  | 34 |  | 212600 |
| TA of DPM/DAM/DDM/EA |  |  |  |  |  |  |  |  |  |  |
| Districts |  | Actual Sumo Fare in Rs. |  |  | Actual Sumo Fare in Rs. (to n fro) |  | No. of DPM+DAM+DDM+EA |  | Total TA in Rs. |  |
| Aizawl West |  | 0 |  |  | 0 |  | 4 |  | 0 |  |
| Aizawl East |  | 0 |  |  | 0 |  | 4 |  | 0 |  |
| Champhai |  | 700 |  |  | 1400 |  | 4 |  | 5600 |  |
| Hnahthial |  | 550 |  |  | 1100 |  | 3 |  | 3300 |  |
| Khawzawl |  | 550 |  |  | 1100 |  | 3 |  | 3300 |  |
| Saitual |  | 300 |  |  | 600 |  | 3 |  | 1800 |  |
| Serchhip |  | 350 |  |  | 700 |  | 4 |  | 2800 |  |
| Kolasib |  | 300 |  |  | 600 |  | 4 |  | 2400 |  |
| Mamit |  | 350 |  |  | 700 |  | 4 |  | 2800 |  |
| Lunglei |  | 550 |  |  | 1100 |  | 4 |  | 4400 |  |
| Lawngtlai |  | 1000 |  |  | 2000 |  | 4 |  | 8000 |  |
| Siaha |  | 1300 |  |  | 2600 |  | 4 |  | 10400 |  |
| TOTAL |  |  |  |  |  |  | 54 |  | 44800 |  |

HSS 11 -  Sl. no. 194: Planning and Program Management

Component: Others including operating costs(OOC)

Particulars: State & Dist Level Office expenditure under RCH / NHM

Requirement for Office Expenses

  - State		-	Rs. 116.26/-

  - District	-	Rs. 41.3/-

Total		-	Rs. 157.56/-

| State Requirement for Office Expenses for FY 2026-27 |  |  |  |
| --- | --- | --- | --- |
| S/N | Activities/Particulars | Amount in Rs. |  |
|  |  | 1 month | 12 months |
| 1 | House Rent for NHM Building | 1,10,100 | 13,21,200 |
| 2 | Electric Bill for NHM Building | 25,000 | 3,00,000 |
| 3 | Water Bill for NHM Building | 1,500 | 18,000 |
| 4 | Internet Bill (Paid Annually) |  | 4,40,000 |
| 5 | NHM Parking Fee paid to AMC | 13,090 | 1,57,080 |
| 6 | HP 60.5 cm (23.8) All-in-One Desktop PC 24-cr0016in - 60.5 cm (23.8) (C34WKPA) Form Factor: All-in-One PC Processor: AMD Ryzen™ 3 7320U (up to 4.1 GHz max boost clock, 4 MB L3 cache, 4 cores, 8 threads) Memory: 8 GB LPDDR5-5500 MT/s (onboard) Hard Drive: 512 GB PCIe® NVMe™ M.2 SSD Display: 60.5 cm (23.8) diagonal, FHD (1920 x 1080), IPS, three-sided micro-edge, anti-glare, 250 nits, 99% sRGB Graphics: Intel® UMA Graphics Screen Size: 60.45 cm (23.8) |  | 7, 80,000 (Rs. 60000 X 13 nos) |
| 7 | Maintenance of Vehicle of SPO (RCH) |  | 50,000 |
| 8 | POL 2000 ltrs @ Rs.99.29/ltr |  | 70,000 |
| 9 | Stationery items ( Pens, papers,notesheets, file covers, printer cartridges etc. ) |  | 70,000 |
| 10 | TA DA for Officers and Staff |  | 50,00,000 |
| 11 | Vehicle Hiring for 2 NHM Officers @ Rs. 20000 each for 1 month | 40,000 | 4,80,000 |
| 12 | Concurrent Audit Fee @ Rs. 472500 per quarter |  | 18,90,000 |
| 13 | Statutory Audit Fees |  | 10,50,000 |
|  | STATE TOTAL |  | 116.26 |

| District Requirement for Office Expenses for FY 2026-27 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Particulars | Azl. E | Azl. W | Champhai | Hnahthial | Khawzawl | Kolasib | Lawngtlai | Lunglei | Mamit | Saitual | Serchhip | Siaha | Total |
| 1 | Internet Bill (2500 pm x 12 months) and other Office expenditure | 1.3 | 1.3 | 1.2 | 0.7 | 0.7 | 0.9 | 1.2 | 1.2 | 0.9 | 0.7 | 0.9 | 0.9 | 11.9 |
| 2 | HP 60.5 cm (23.8) All-in-One Desktop PC 24-cr0016in - 60.5 cm (23.8) (C34WKPA) Form Factor: All-in-One PC Processor: AMD Ryzen™ 3 7320U (up to 4.1 GHz max boost clock, 4 MB L3 cache, 4 cores, 8 threads) Memory: 8 GB LPDDR5-5500 MT/s (onboard) Hard Drive: 512 GB PCIe® NVMe™ M.2 SSD Display: 60.5 cm (23.8) diagonal, FHD (1920 x 1080), IPS, three-sided micro-edge, anti-glare, 250 nits, 99% sRGB Graphics: Intel® UMA Graphics Screen Size: 60.45 cm (23.8) | 3 | 2.4 | 2.4 | 2.4 | 2.4 | 2.4 | 2.4 | 2.4 | 2.4 | 2.4 | 2.4 | 2.4 | 29.4 |
|  | TOTAL | 4.7 | 3.4 | 3.4 | 3.2 | 3.2 | 3.4 | 3.7 | 3.76 | 3.4 | 3.2 | 3.3 | 3.3 | 41. |

District Total: Rs. 41.3 Lakhs/-