INTEGRATED DISEASE SURVEILLANCE PROJECT

IDSP Annexure and Formats for PIP

Annexure 1

STATE LEVEL: Progress on key IDSP indicators

| Name of the State: MIZORAM |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Variables | 2011-12 |  |  | 2012-13 (Avg. Upto Previous Month) |  |  | Target 2013-14 |  |  |
| - Percentage of the total districts reporting weekly data in ‘P’ form through portal. | 2.56% |  |  | 11.34% |  |  | 75% |  |  |
| - Percentage of the total reporting units which are submitting weekly (S, P, L) Data on epidemic prone diseases through portal. | S | P | L | S | P | L | S | P | L |
|  | 3.03% | 2.46% | 4.96% | 21.71% | 9.83% | 31.06% | 75% | 75% | 80% |
| - Percentage of total outbreaks investigated and responded to by States/UTs by sending samples for testing in laboratory. | 100% |  |  | 100% |  |  | 100% |  |  |
| - Number of district public health labs strengthened for diagnosis of epidemic prone diseases. | 1 |  |  | 1 |  |  | 4 |  |  |
| - Percentage of Epidemiologists/Microbiologist/Entomologist (total) in position out of total number of sanctioned positions. | 35% |  |  | 35% |  |  | 100% |  |  |
| - Percentage of Data Manager in position out of total number of sanctioned positions. | 100% |  |  | 100% |  |  | 100% |  |  |
| - Percentage of Data Entry Operators in position out of total number of sanctioned positions. | 100% |  |  | 100% |  |  | 100% |  |  |

Annexure 2

DISTRICT LEVEL: Reporting Format on Delivery Points on key Performance Indicators (KPI)

| Name of the State:MIZORAM |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Name of District |  | Sl.No (Delivery Point) |  |  |  |  |  |  |  |  |
| 1. Aizawl East |  | - Percentage of Reporting units reporting >75% of times in last 12 weeks through IDSP Portal. |  | Reporting Format |  | S |  | P |  | L |
|  |  |  |  | No. of identified reporting units |  | 54 |  | 17 |  | 15 |
|  |  |  |  | % reporting |  | Nil |  | Nil |  | Nil |
|  |  | - Number of supervisory field visits by DSU officials/staff (Epidemiologists/DSO/Data Manager etc) in last year. |  | 8 |  |  |  |  |  |  |
|  |  | - Number of outbreaksin past12months investigated by Rapid Response Teams (RRT). |  | Nil |  |  |  |  |  |  |
|  |  | - Number of outbreaksin past 12 months where appropriate samples were sent for laboratory investigations to District Lab/Referral Lab. |  | Nil |  |  |  |  |  |  |
| 2.Aizawl West |  | - Percentage of Reporting units reporting >75% of times in last 12 weeks through IDSP Portal. |  | Reporting Format |  | S |  | P |  | L |
|  |  |  |  | No. of identified reporting units |  | 38 |  | 6 |  | 12 |
|  |  |  |  | % reporting |  | 76.31% |  | Nil |  | 25% |
|  |  | - Number of supervisory field visits by DSU officials/staff (Epidemiologists/DSO/Data Manager etc) in last year. |  | 11 |  |  |  |  |  |  |
|  |  | - Number of outbreaks in past 12 months investigated by Rapid Response Teams (RRT). |  | Nil |  |  |  |  |  |  |
|  |  | - Number of outbreaks in past 12 months where appropriate samples were sent for laboratory investigations to District Lab/Referral Lab. |  | Nil |  |  |  |  |  |  |
| Name of the State:MIZORAM |  |  |  |  |  |  |  |  |  |  |  |
| Name of District |  | Sl. No (Delivery Point) |  |  |  |  |  |  |  |  |  |
| 3.Champhai |  | - Percentage of Reporting units reporting >75% of times in last 12 weeks through IDSP Portal. |  | Reporting Format |  | S |  | P |  |  | L |
|  |  |  |  | No. of identified reporting units |  | 59 |  | 9 |  |  | 11 |
|  |  |  |  | % reporting |  | Nil |  | Nil |  |  | Nil |
|  |  | - Number of supervisory field visits by DSU officials/staff (Epidemiologists/DSO/Data Manager etc) in last year. |  | 7 |  |  |  |  |  |  |  |
|  |  | - Number of outbreaks in past 12 months investigated by Rapid Response Teams (RRT). |  | Nil |  |  |  |  |  |  |  |
|  |  | - Number of outbreaks in past 12 months where appropriate samples were sent for laboratory investigations to District Lab/Referral Lab. |  | Nil |  |  |  |  |  |  |  |
| 4.Kolasib |  | - Percentage of Reporting units reporting >75% of times in last 12 weeks through IDSP Portal. |  | Reporting Format |  | S |  | P |  |  | L |
|  |  |  |  | No. of identified reporting units |  | 34 |  | 8 |  |  | 7 |
|  |  |  |  | % reporting |  | 91.18% |  | 100% |  |  | 100% |
|  |  | - Number of supervisory field visits by DSU officials/staff (Epidemiologists/DSO/Data Manager etc) in last year. |  | 12 |  |  |  |  |  |  |  |
|  |  | - Number of outbreaks in past 12 months investigated by Rapid Response Teams (RRT). |  | Nil |  |  |  |  |  |  |  |
|  |  | - Number of outbreaks in past 12 months where appropriate samples were sent for laboratory investigations to District Lab/Referral Lab. |  | Nil |  |  |  |  |  |  |  |

| Name of the State:MIZORAM |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Name of District | Sl. No (Delivery Point) |  |  |  |  |
| 5.Lawngtlai | - Percentage of Reporting units reporting >75% of times in last 12 weeks through IDSP Portal. | Reporting Format | S | P | L |
|  |  | No. of identified reporting units | 38 | 7 | 7 |
|  |  | % reporting | Nil | Nil | Nil |
|  | - Number of supervisory field visits by DSU officials/staff (Epidemiologists/DSO/Data Manager etc) in last year. | 4 |  |  |  |
|  | - Number of outbreaks in past 12 months investigated by Rapid Response Teams (RRT). | Nil |  |  |  |
|  | - Number of outbreaks in past 12 months where appropriate samples were sent for laboratory investigations to District Lab/Referral Lab. | Nil |  |  |  |
| 6.Lunglei | - Percentage of Reporting units reporting >75% of times in last 12 weeks through IDSP Portal. | Reporting Format | S | P | L |
|  |  | No. of identified reporting units | 77 | 10 | 9 |
|  |  | % reporting | 2.60% | Nil | Nil |
|  | - Number of supervisory field visits by DSU officials/staff (Epidemiologists/DSO/Data Manager etc) in last year. | 15 |  |  |  |
|  | - Number of outbreaks in past 12 months investigated by Rapid Response Teams (RRT). | 1 |  |  |  |
|  | - Number of outbreaks in past 12 months where appropriate samples were sent for laboratory investigations to District Lab/Referral Lab. | 1 |  |  |  |

| Name of the State:MIZORAM |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Name of District | Sl. No (Delivery Point) |  |  |  |  |
| 7.Mamit | - Percentage of Reporting units reporting >75% of times in last 12 weeks through IDSP Portal. | Reporting Format | S | P | L |
|  |  | No. of identified reporting units | 31 | 9 | 8 |
|  |  | % reporting | Nil | Nil | Nil |
|  | - Number of supervisory field visits by DSU officials/staff (Epidemiologists/DSO/Data Manager etc) in last year. | 5 |  |  |  |
|  | - Number of outbreaks in past 12 months investigated by Rapid Response Teams (RRT). | Nil |  |  |  |
|  | - Number of outbreaks in past 12 months where appropriate samples were sent for laboratory investigations to District Lab/Referral Lab. | Nil |  |  |  |
| 8.Saiha | - Percentage of Reporting units reporting >75% of times in last 12 weeks through IDSP Portal. | Reporting Format | S | P | L |
|  |  | No. of identified reporting units | 31 | 5 | 4 |
|  |  | % reporting | Nil | Nil | Nil |
|  | - Number of supervisory field visits by DSU officials/staff (Epidemiologists/DSO/Data Manager etc) in last year. | 4 |  |  |  |
|  | - Number of outbreaks in past 12 months investigated by Rapid Response Teams (RRT). | Nil |  |  |  |
|  | - Number of outbreaks in past 12 months where appropriate samples were sent for laboratory investigations to District Lab/Referral Lab. | Nil |  |  |  |

| Name of the State:MIZORAM |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Name of District | Sl. No (Delivery Point) |  |  |  |  |
| 9.Serchhip | - Percentage of Reporting units reporting >75% of times in last 12 weeks through IDSP Portal. | Reporting Format | S | P | L |
|  |  | No. of identified reporting units | 26 | 7 | 7 |
|  |  | % reporting | Nil | Nil | Nil |
|  | - Number of supervisory field visits by DSU officials/staff (Epidemiologists/DSO/Data Manager etc) in last year. | 7 |  |  |  |
|  | - Number of outbreaks in past 12 months investigated by Rapid Response Teams (RRT). | 1 |  |  |  |
|  | - Number of outbreaks in past 12 months where appropriate samples were sent for laboratory investigations to District Lab/Referral Lab. | 1 |  |  |  |

Annexure 3

Summary of contractual HR & Training Status at State Surveillance Unit under IDSP in 2012-13 (current status)

| Name of the State: MIZORAM |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Name of State Surveillance Unit | Epidemiologists |  |  | Microbiologists |  |  | Entomologist |  |  | Data Manager |  |  | Data Entry Operator |  |  | Consultant Training |  |  | Consultant (Finance/Procurement) |  |  |
|  | Sanctioned post | In position | Trained | Sanctioned post | In position | Trained | Sanctioned post | In position | Trained | Sanctioned post | In position | Trained | Sanctioned post | In position | Trained | Sanctioned post | In position | Trained | Sanctioned post | In position | Trained |
| MIZORAM | 1 | 1 | - | 2 | 2 | 2 | 1 | 1 | - | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | - | 1 | 1 | - |

Annexure 4

Summary of District wise contractual HR & Training Status under IDSP in 2012-13 (current status)

|  | Name of the State: MIZORAM |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| S. No. | Name of District Surveillance Unit/ | Epidemiologists |  |  | Microbiologists |  |  | Data Manager |  |  | Data Entry Operator |  |  |
|  |  | Sanctioned | In position | Trained | Sanctioned | In position | Trained | Sanctioned | In position | Trained | Sanctioned | In position | Trained |
| 1 | Aizawl East | - | - | - | - | - | - | 1 | 1 | 1 | 1 | 1 | 1 |
| 2 | Aizawl West | 1 | - | - | - | - | - | 1 | 1 | 1 | 1 | 1 | 1 |
| 3 | Champhai | 1 | - | - | - | - | - | 1 | 1 | 1 | 1 | 1 | 1 |
| 4 | Kolasib | 1 | - | - | - | - | - | 1 | 1 | 1 | 1 | 1 | 1 |
| 5 | Lawngtlai | 1 | - | - | - | - | - | 1 | 1 | 1 | 1 | 1 | 1 |
| 6 | Lunglei | 1 | - | - | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |
| 7 | Mamit | 1 | - | - | - | - | - | 1 | 1 | 1 | 1 | 1 | 1 |
| 8 | Saiha | 1 | - | - | - | - | - | 1 | 1 | 1 | 1 | 1 | 1 |
| 9 | Serchhip | 1 | - | - | - | - | - | 1 | 1 | 1 | 1 | 1 | 1 |
| Total |  | 8 | - | - | 1 | 1 | 1 | 9 | 9 | 9 | 9 | 9 | 9 |

IDSP Trg- Annexure 5

IDSP Trainings - Background Information Required for Approval of State PIPs for 2013-14

| Name of the State:MIZORAM |  |  |
| --- | --- | --- |
| Training Category | Total trained in 2012-13 | Proposed numbers to be trained in 2013-14 |
| Medical Officers (3 days) | - | 60 |
| Medical College Doctors (1 day) | - | - |
| Hospital Pharmacists/Nurses Training (1 day) | - | 100 |
| Lab. Technician (3 days) | - | 100 |
| Data Managers (2days) | 10 | 10 |
| Date Entry Operators cum Accountant (2 days) | 10 | 10 |
| ASHA & MPWs, AWW & Community volunteers (1 day) | - | 100 |
| One day training for Data entry and analysis for Block Health Team (including Block Programme Manager) | - | - |
| Others (Newly recruited Health Workers) | - | 100 |
| The State may decide about the reasonable & feasible number of batches that could be trained in 2013-14 (IDSP trainings are generally conducted for 20 participants per batch) and the budget may be calculated as per NRHM guidelines. |  |  |

Annexure 6

Summary of District wise laboratory strengthening status

| Name of the State: MIZORAM |  |  |  |
| --- | --- | --- | --- |
| Sl.No | Name of District | Name of District Lab already strengthened as District Public Health lab for diagnosis & testing for epidemic prone diseases under IDSP (including District Lab which are already functional requiring no strengthening) | Name of District Labs proposed to be strengthened as District Public Health lab in 2013-14(Do not include those labs which are not yet strengthened but budget was approved in previous ROPs) |
| 1 | Aizawl East |  |  |
| 2 | Aizawl West |  |  |
| 3 | Champhai |  | Champhai Civil Hospital Laboratory |
| 4 | Kolasib |  |  |
| 5 | Lawngtlai |  | Lawngtlai Civil Hospital Laboratory |
| 6 | Lunglei | Lunglei Civil Hospital Laboratory |  |
| 7 | Mamit |  |  |
| 8 | Saiha |  | Saiha Civil Hospital Laboratory |
| 9 | Serchhip |  |  |
| Total |  | 1 | 3 |

Annexure 7

IDSP – HR Background Information Required for Approval of State PIPs for 2013-14

Annexure 7.a

OVERALL HUMAN RESOURCE SHEET

| Name of the State: MIZORAM |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Sr. No | Category/ type of personnel | State total |  |  | Total in position | Total posts proposed in 2013-14 PIP (existing + new) |
|  |  | Sanctioned posts | In position (through state/other sources) | In position from IDSP/ NRHM |  | State total |
|  |  |  | (A) | (B) | A+B |  |
| 1 | State Epidemiologist | 1 | - | 1 | 1 | 1 |
| 2 | Consultant (Training) | 1 | - | 1 | 1 | 1 |
| 3 | Entomologist | 1 | - | 1 | 1 | 1 |
| 4 | Microbiologist | 3 | - | 3 | 3 | 6 |
| 5 | Consultant (Finance & Procurement) | 1 | - | 1 | 1 | 1 |
| 6 | State Data Manager | 1 | - | 1 | 1 | 1 |
| 7 | State Data Entry Operator | 1 | - | 1 | 1 | 1 |
| 8 | District Epidemiologist | 8 | - | - | - | 9 |
| 9 | District Data Manager | 9 | - | 9 | 9 | 9 |
| 10 | District Data Entry Operator | 9 | - | 9 | 9 | 9 |
| 11 | Veterinary Consultant | - | - | - | - | 1 |
| 12 | Laboratory Assistant | - | - | - | - | 5 |

*The Basis of requirement to be spelt out clearly (e.g. IPHS, State Norms etc.)

Annexure 7.b

Status of Technical HR

| Name of the State: MIZORAM |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Sr. No | Category | Existing staff in 2012-13 (Approved by GoI) |  |  | Proposed staff in 2013-14 |  |  |
|  |  | No. of existing staff | Remuneration per month | Total amount approved (Rs. In lakhs) | No. of staff proposed | Remuneration per month | Total amount (Rs. In lakhs) |
| 1 | Epidemiologist | 9 | 40,000 | 37.2 | 10 | 40,000 | 48 |
| 2 | Consultant (Training) | 1 | 28,000 | 3.36 | 1 | 40,000 | 4.8 |
| 3 | Entomologist | 1 | 25,000 | 3 | 1 | 35,000 | 4.2 |
| 4 | Microbiologist | 3 | 25,000 | 9 | 6 | 35,000 | 25.2 |
| 5 | Veterinary Consultant | - | - | - | 1 | 40,000 | 4.8 |
| 6 | Laboratory Assistant | - | - | - | 5 | 15,000 | 9 |

Annexure 7.c

Status of Newly proposed HR

| Sr. No | Category | Total No. Of existing staff in 2012-13 | Total No. Of proposed staff for 2013-14 | No. Of additional staff proposed for 2013-14 | Justification for the additional posts proposed in the year 2013-14 |
| --- | --- | --- | --- | --- | --- |
| 1 | Veterinary Consultant | - | 1 | 1 | In some situations when disease caused by animals and which can be contracted from animals are prevalent their knowledge and experience is required. |
| 2 | Microbiologist | 3 | 6 | 3 | Three new laboratories proposed to be strengthened. If approved, Microbiologist needs to be posted under IDSP. |
| 3 | Laboratory Assistant | - | 5 | 5 | At present, there is no post of Lab Assistant under IDSP. This post is needed for efficient functioning of the Laboratories. |

Annexure 8

Background Information Required for Approval of State PIPs for Innovations/ New Initiatives

In 2013-14

Innovations/ New Initiatives

Activities Proposed:

- Sero-prevalence screening for Scrub Typhus in Mizoram.

- Name of the Activity:Screening and highlighting Scrub Typhus

- Justification:It is confirmed that an outbreak of Scrub Typhus prevails in the different district of Mizoram,cases are increasing alarmingly in the state recently.Hence it is very needful that IDSP must take responsibility and put an effort in this particular Disease(all the list of confirmed cases of Scrub Typhus is enclosed).It has been postulated that many valuable lives might have been lost due to this disease and even higher number of cases going undetected or misdiagnosed.

The percentage of positive findings in the general population varied from 2% in India to 40% in Malaysia (WHO (1983).Bull WHO 61:443).Therefore the need of conducting Sero-surveillance among general population to highlight the magnitude of Scrub Typhus,which has been a lesser known disease in Mizoram till the recent past,in order to increase public awareness as well as for implementation of preventive and timely curative measures.

Details of Scrub Typhus data in Mizoram is given in Annexure 11

- Funding Proposed: 32.8 Lakhs

See table below for details.

Budget proposal of Sero-prevalence screening for Scrub typhus in Mizoram

| Sl. No. | ACTIVITY | UNIT COST (in Rupees) | PHYSICAL TARGET | AMOUNT Rs in Lakhs | REMARKS |
| --- | --- | --- | --- | --- | --- |
| 1 | HUMAN RESOURCE |  |  |  |  |
| 1.1 | Principal Investigator (PI) | - | 1 | - | Epidemiologist from the state Health Department |
| 1.2 | Field Investigators (FI) |  | 1 |  | State Entomologist, IDSP |
| 1.3 | Laboratory Technicians (LT) | 10,000 | 2 | 1.2 | for 2 LTs for 6 months |
| 1.4 | OPERATIONAL COST |  |  |  |  |
| 2 | Laboratory Equipments | 7,00,000 | 1 | 7 |  |
| 2.1 | Laboratory consumables | 2,40,000 | 1 | 2.4 |  |
| 2.2 | Training for investigators | 38,000 | 11 | 4.2 | At National Institute identified by MoHFW, New Delhi |
| 2.3 | Mobility support for PO and Field Investigators | 4,00,000 | 3 districts | 12 |  |
| 2.4 | Publication of reports |  |  | 1 |  |
| 2.5 | Diagnostic Kit for Scrub Typhus | 50,000 | 9 District + State | 5 |  |
| Total |  |  |  | 32.8 |  |

Annexure 9

Background Information Required for Approval of State PIPs forState Specific Activities

In 2013-14

State Specific Activities

Activities Proposed:

- Name of the Activity: Report of outbreaks through SMS.

- Achievements in previous years:NIL

- Justification:There are many places in the state where internet facilities cannot be utilized,as most of the remote places can be reached by mobile phones.So,it will be very helpful if Health Worker can report any outbreak in their respective jurisdiction to the District Epidemiologist and to the state as well in order to take immediate and rapid actions.If Health programme workers could be equipped with mobile services it will really be helpful for combating any outbreaks and epidemic.

- Funding Proposed:Included in Operational Cost.

- Name of the Activity:Laboratory Support

- Achievements in previous years:2 Existing Laboratories maintained

- Justification: It is proposed that 3 newly identified District Hospitals Laboratory during 2013 – 14 namely (District Hospital Champhai, Saiha, Lawngtlai) along with the existing 2 identified laboratories. These three Districts are lying in the periphery / boundary of Mizoram Bordering to Myanmar and Bangladesh and they are the remotest districts in the state. It is very needful that these Hospital laboratory might be identified and equipped with non recurring budget like renovation, Computer set, Furniture, Communication set etc and recurring budget, Laboratory materials and consumables.

- Funding Proposed:Rs. 41.7 Lakhs

- Name of the Activity:Toll Free Telephone

- Achievements in previous years:Nil

- Justification: As most of the outbreak in the state usually takes place amongst the poorer section of the people. It would be definitely helpful to establish a toll free telephone in the state so that anyone can report an outbreak without any expense from their side. It is noted that many outbreaks has been occurring without proper report to the medical personnel.

- Funding Proposed:Included in Operational Cost

Name of the Activity:Mobility Support

- Achievements in previous years:Nil

- Justification: IDSP is responsible to take rapid action to any outbreak and epidemics it is therefore the state needs to be equipped with good and fit conditioned Vehicles to respond to any outbreaks even in the remotest part of the state. It is suggested that vehicle Hiring system (Monthly basis) might be applicable if new vehicle cannot be provided from the CSU at this stage.

- Funding Proposed:Included in Operational Cost

- Name of the Activity:IEC

- Achievements in previous years:Nil

- Justification: IEC is a must for educating the personnel and public on impending/possible outbreak. The containment measure of any particular disease is not effective with the health department intervention only but it both equally important to educated the people to check the spread of disease. IEC in the form of pamphlet, Radio/TV announcement, Talk show, Hoardings (atleast one in each district), SLR Camera for documentation and other innovation will be initiated during the current year.

- Funding Proposed:Rs. 11 Lakhs

State Level					Rs. 2 Lakhs

District Level @ Rs. 1 Lakhs each for 9 Districts	Rs. 9 Lakhs

Total:	Rs. 11 Lakhs

- Name of the Activity:Diagnostic Kit For Scrub Typhus

- Achievements in previous years:Nil

- Justification: As an outbreak of Scrub typhus disease is alarmingly increase in the state and there is no supply of diagnostic kit for this particular disease, valuable lives are lost due to misdiagnosed and without giving proper and timely medication due to lack of diagnostic kit in the district Hospital and even in the state hospital as well. It is very needful that SSU might be supplied with rapid diagnostic kit for further distribution to the state and district hospitals.

- Funding Proposed:Included in New Initiative Budget.

Annexure 10

JUSTIFICATION FOR PROPOSED SALARY:

** It is imperative to mention that under the Sixth Pay Commission even the salary of 4th Grade is more than

Rs.15,000.

Entomologist: The Entomologist under IDSP serves as the sole Entomologist for the State. Since there is only one post, the Entomologist also works for SVBDCP at the same time without any incentives. It should also be mentioned that our present Entomologist is highly qualified according to the recruitment rule.

Consultant (Training): The remuneration for Consultant (Training) is relatively low compared to other Medical Officers under different programmes. Also, his qualification is same as our Epidemiologist. So, same salary as Epidemiologist is justified.

Microbiologist: The Microbiologist serves an active role in the activities and operations of IDSP. They are also simultaneously working for Microbiology Department. A raise in salary is rightfully deserved.

Consultant (Finance & Procurement): The salary for Consultant (F & P) is a bit low considering the state of things in the present day. Now that the Sixth Pay Commission is adopted even 4th Grade employees are paid more than Rs.14,000. This is highly inconsistent with the norms and a bit of a blunder. Their counterpart posts under other programmes are relatively higher. To cite an example, their equivalent BFO under NLEP are paid Rs.30,000, which is more than double the salary of our Finance Consultant.

State Data Manager: The desired qualification for this post is B.E (Computer) / B.Tech as per ROP. In this regard, the current remuneration of Rs.14,000 is very unbefitting for their caliber. It may be noted that other posts such as District Data Officer under NRHM, which has the same qualification criteria, are paid Rs.25,000. Thus, it is only fair that the salary for State Data Manager should be at least equivalent to them.

It has to be strongly pointed out that the State Data Manager salary is even lower than DEO at other programmes,(E.g. DEO under NLEP are paid Rs.20,000 and DEO under Blindness are paid Rs.15,000). This is very far from being reasonable and it is highly desirable that it is rectified.

Data Entry Operators: The salary is comparatively lower than their counterpart in other programmes. For instance, DEO under NLEP are paid Rs.20,000 and DEO under blindness are paid Rs.15,000. It is very much desired that this discrepancy is addressed and that there is some standardized pay for equivalent posts.

| NAME OF THE STATE: MIZORAM |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| S. No. | Budget Head |  | Proposed 2013-14 |  |  | Remarks | % expenditure during previous year | Difference previous budget vis-à-vis current proposed (Rs. Lakhs) | % increase in proposed budget |
|  |  |  |  |  |  | State to mention whether the activity proposed is new or to be continued from previous year. Justification to be given. |  |  |  |
|  |  | Unspent balance (as on November 2012) | Quantity / Target | Unit Cost (Rs) | Budget (Rs. Lakhs) |  |  |  |  |
| A | INTEGRATED DISEASE SURVEILLANCE PROGRAMME (IDSP) |  |  |  |  |  |  |  |  |
| A1 | REMUNERATION FOR CONTRACTUAL HUMAN RESOURCE |  |  |  |  |  |  |  |  |
| A1.1 | State Epidemiologist | 0 | 1 | 40000 | 4.8 | Continued. Justification may be seen in Annexure 10 | 100% | 0 | 0% |
| A1.2 | State Microbiologist | 0 | 2 | 35000 | 8.4 | Continued. Justification may be seen in Annexure 10 | 100% | 2.4 | 40% |
| A1.3 | State Veterinary Consultant | 0 | 1 | 40000 | 4.8 | New. In some situations when disease caused by animals and which can be contracted from animals are prevalent their knowledge and experience is required. | – | 4.8 | – |
| A1.4 | State Consultant (Training) | 0 | 1 | 40000 | 4.8 | Continued. Justification may be seen in Annexure 10 | 100% | 1.44 | 43% |
| A1.5 | State Entomologist | 0 | 1 | 35000 | 4.2 | Continued. Justification may be seen in Annexure 10 | 100% | 1.2 | 40% |
| A1.6 | State Consultant (Finance/Procurement) | 0 | 1 | 30000 | 3.6 | Continued. Justification may be seen in Annexure 10 | 100% | 1.92 | 114% |
| A1.7 | State Data Manager | 0 | 1 | 30000 | 3.6 | Continued. Justification may be seen in Annexure 10 | 100% | 1.92 | 114% |
| A1.8 | State Data Entry Operator cum accountant | 0 | 1 | 20000 | 2.4 | Continued. Justification may be seen in Annexure 10 | 100% | 1.38 | 135% |
| A1.9 | District Epidemiologists | 0 | 9 | 40000 | 43.2 | Continued. Justification may be seen in Annexure 10 | 100% | 0 | 0% |
| A1.10 | District Microbiologist at District labs | 0 | 4 | 35000 | 16.8 | Continued. Justification may be seen in Annexure 10 | 100% | 13.8 | 460% |
| A1.11 | District Data Manager | 0 | 9 | 25000 | 27 | Continued. Justification may be seen in Annexure 10 | 100% | 12.42 | 85% |
| A1.12 | Data Entry Operator | 0 | 9 | 20000 | 21.6 | Continued. Justification may be seen in Annexure 10 | 100% | 12.42 | 135% |
| A1.13 | Others if any/new positions proposed if any (Laboratory Assistant) | 0 | 5 | 15000 | 9 | New. At present, there is no post of Lab Assistant under IDSP. This post is needed for efficient functioning of the Laboratories. | – | 9 | – |
|  | Sub Total (A) | 0 | 45 | 405000 | 154.2 |  | 100% | 62.7 | 69% |
| A2 | TRAINING |  |  |  |  |  |  |  |  |
|  | Training at State/District Level (1 batch = 20 participants) |  |  |  |  |  |  |  |  |
| A2.1 | Medical Officers (3 days) | 0 | 60 | 121765 | 3.66 | Continued | 100% | 2.56 | 233% |
| A2.2 | Medical College Doctors (1 day) | 0 | – | – | – | – | – | 0 | – |
| A2.3 | Hospital Pharmacists/Nurses Training (1 day) | 0 | 100 | 61500 | 3.075 | Continued | 100% | 2.325 | 310% |
| A2.4 | Lab. Tecnician (3 days) | 0 | 100 | 93015 | 4.65 | New. Only one training has been given til date. Training needed as sensitization is highly required | – | 4.65 | – |
| A2.5 | Data Managers (2days) | 0 | 20 | 55800 | 1.116 | Continued | 100% | 0.966 | 644% |
| A2.6 | Date Entry Operators cum Accountant (2 days) |  |  |  |  |  |  |  |  |
| A2.7 | ASHA & MPWs, AWW & Community volunteers (1 day) | 0 | 100 | 61500 | 3.075 | New. No training has been given til date. Training needs to be given so that they could be utilised for IDSP activities. | – | 3.075 | – |
| A2.8 | One day training for Data entry and analysis for Block Health Team (including Block Programme Manager) | 0 | – | – | – | – | – | 0 | – |
| A2.9 | Others (Newly Recruited Health Workers) | 0 | 100 | 77260 | 3.863 | New. Training needs to be given as there are many newly recruited Health Workers. | – | 3.863 | – |
|  | The State may decide about the reasonable & feasible number of batches that could be trained in 2013-14 (IDSP trainings are generally conducted for 20 participants per batch) and the budget may be calculated as per NRHM guidelines. |  |  |  |  |  |  |  |  |
|  | Sub Total (B) | 0 | 480 | 470840 | 19.439 |  | 100% | 17.439 | 872% |
| A3 | LABORATORY SUPPORT |  |  |  |  |  |  |  |  |
| A3.1 | District Public Health Laboratory Strengthening |  |  |  |  |  |  |  |  |
| A3.1.1 | Non-recurring costs on account of equipment for district public health labs requiring strengthening. | 0 | 3 | 390000 | 11.7 | New. Three new District Lab proposed to be strengthened. If approved, new materials needs to be purchased | 100% | 11.7 | – |
| A3.1.2 | Recurring costs on account of Consumables, kits, communication, misc expenses etc at each district public health lab (applicable only for functional labs having requisite manpower). | 0 | 5 | 600000 | 30 | Continued. Three new District Lab proposed to be strengthened. If approved, new materials needs to be purchased | 100% | 22 | 275% |
|  | A reasonable & feasible target (No. of labs to be strengthened in 2013-14) to be set and States/UTs to provide list of labs identified for strengthening. |  |  |  |  |  |  |  |  |
|  | The state is requested to continue to take up this activity in a phased manner and to utilize the funds judiciously as suggested below: 1. First step is to identify the districts where such facility is not available. 2. Next is to identify the district hospital where the lab would be strengthened for diagnosis of epidemic prone diseases. 3. Subsequently, an initial survey of the identified labs is to be conducted for the gaps in equipment and manpower and the budget required is to be identified. 4. Manpower should be based on the workload expected . Cost of kits and reagents are to be budgeted as per the number of tests expected to be conducted per annum. I f manpower is proposed other than currently sanctioned then it should reflect in HR under IDSP and the Justification for the same should be given) |  |  |  |  |  |  |  |  |
| A3.2 | Referral Network of laboratories (Govt. Medical College labs) |  |  |  |  |  |  |  |  |
| A3.2.1 | Reimbursement based payment for laboratory tests. (Already approved labs in States are as follows: Andhra Pradesh-9, Gujarat-8, Karnataka-8, Maharashtra-10, Punjab-4, Rajasthan-6, Tamil Nadu-8, Uttarakhand-3, West Bengal-9, Kerala - 5, Haryana - 2, Bihar - 6, Orissa - 3, J&K - 3, Assam - 3, Tripura - 1, Manipur - 1). |  |  |  |  |  |  |  |  |
| A3.2.2 | A total of 28 labs (Govt. Medical College) are proposed to be included into the network in 2013-14 from Chandigarh-1, Chattisgarh-3, Himachal Pradesh-2, Madhya Pradesh-6, Meghalaya-1, Sikkim-1, UP-11 and Jharkhand-3). |  |  |  |  |  |  |  |  |
|  | (Identified Tests- ELISA /rapid test for leptospirosis, ELISA for Dengue/Chikunguniya, ELISA for Viral Hepatitis, ELISA for Measles, Rapid test for Meningococci, Blood culture for Typhoid, Diphtheria culture, Cholera culture, other (state specific diseases). Kits for Dengue and Chikunguniya are provided by NVBDCP. |  |  |  |  |  |  |  |  |
|  | Sub Total ( C) | 0 | 8 | 990000 | 41.7 |  | 100% | 33.7 | 421% |
| A4 | COSTS ON ACCOUNT OF NEWLY FORMED DISTRICTS |  |  |  |  |  |  |  |  |
| A4.1 | For each newly formed district to cover for the expenses on account of Non-recurring costs on Computer Hardware, some office equipment & accessories. The indicative list of equipment for ICT & Office equipment support for each newly created district is as follows: |  |  |  |  |  |  |  |  |
| A4.1.1 | Two Desktop Computers (one for Training centre & one for Data Centre) |  |  |  |  |  |  |  |  |
| A4.1.2 | One Webcam |  |  |  |  |  |  |  |  |
| A4.1.3 | One Microphone |  |  |  |  |  |  |  |  |
| A4.1.4 | One Desktop Speakers |  |  |  |  |  |  |  |  |
| A4.1.5 | One LCD Projector |  |  |  |  |  |  |  |  |
| A4.1.6 | One UPS (1 KV) for Training Centre |  |  |  |  |  |  |  |  |
| A4.1.7 | One UPS (0.6 KV) for Data Centre |  |  |  |  |  |  |  |  |
| A4.1.8 | One Scanner (A4 Size) |  |  |  |  |  |  |  |  |
| A4.1.9 | One Laser Printer |  |  |  |  |  |  |  |  |
| A4.1.10 | One Fax Machine |  |  |  |  |  |  |  |  |
| A4.1.11 | One Photocopier |  |  |  |  |  |  |  |  |
|  | Sub Total (D) | 0 | 0 | 0 | 0 |  | 0% | 0 | – |
| A5 | OPERATIONAL COSTS |  |  |  |  |  |  |  |  |
| A5.1 | MOBILITY: Travel Cost, POL, etc during outbreak investigations and field visits for monitoring programme activities at SSU & DSU on need basis | 0 | – | 4090000 | 40.9 | Continued. Justification may be seen in Annexure 9 | 100% | 14.3 | 54% |
| A5.2 | Office expenses on telephone, fax, Broadband Expenses, Weekly Alert Bulletin/Annual Disease Surveillance report, minor repairs and AMC of IT/office equipment supplied under IDSP, Meetings and other miscellenious expenditures etc. |  |  |  |  |  |  |  |  |
|  | Sub Total (E) | 0 | 0 | 4090000 | 40.9 |  | 100% | 14.3 | 54% |
| A6 | INNOVATIONS/NEW INITIATIVES (Provide details as in Annexure) | 0 | 0 | 3280000 | 32.8 | New. Justification may be seen in Annexure 8 | – | 32.8 | – |
| A7 | ANY STATE SPECIFIC ACTIVITY NOT MENTIONED ABOVE (provide details in Annexure) | 0 | – | 1100000 | 11 | New. Justification may be seen in Annexure 9 | – | 11 | – |
|  | Sub Total (F) | 0 | 0 | 4380000 | 43.8 |  |  | 43.8 | – |
|  | GRAND TOTAL (A+B+C+D+E+F) | 0 | 533 | 10335840 | 300.039 |  | 100% | 171.94 | 134% |