Answers to comments on PIP 2013-14 of SVBDCP, Mizoram

- Achievement with respect to proposed physical and financial targets for 2012 -13 not given.

- Reasons may also be given for not achieving these targets.

=	(Combined answer to Sl.no 1 & 2) Reasons are as follows:-

- Decrease in acceptance of IRS

- Insufficient coverage of families with LLINs

- Communication problem against delivery service along the border Districts namely Lunglei, Lawngtlai and Mamit

- Non-availability of K-Othrine for impregnation of self owned nets.

- Physical and financial targets for the year 2013-14 may also be given.

=	This is reflected in the Action Plan 2013-14 as per proforma received.

- There is a decline in Malaria cases from 8440 cases (2011) to 7717 (2012) but still mortality due to Malaria remains quite high (20 deaths till Sept) during 2012.

=	Till Sept 2011, the total number of cases is 6932 and death amounts to 29. In 2012 (till Sept), there are 7717 cases with 20 deaths. This clearly indicates a decline in mortality.

- API has reduced from 8.58 to 6.55 (upto Sept) and ABER reduced from 17.41 to 10.52

=	Suspected cases during 2011-2012 (upto Sept) declined. Also, collaboration with the CMAI on CHV reports was in a transitional period. Hence blood examined and cases were reduced during this stage. With the re-orientation on report forms, better outcome is anticipated. This is in response to the comment given by the GOI.

- The post of 186 numbers of Multi Purpose Health Workers are lying vacant in the State.

=	The filling of vacant MPW posts is not under the purview of SVBDCP, Mizoram. However, 75 Malaria Programe Workers were sanctioned by the GoI. In addition to this, 124 Malaria Programme Workers are proposed to be posted at inaccessible areas where there are no Sub-Centres.

- Only Rs. 3 lakhs distributed towards ASHA incentive as against Rs. 15 lakhs. The reason for poor performance is not given.

=	For the 1st installment of funds, only Rs. 3 lakhs was received for ASHA incentives. The remaining balance is yet to be released and received as 2nd installment.

- Justification for increased amount of Rs. 36.97 lakhs for proposed ASHA incentives not given.

=	ASHA incentives include Slides and RDK examination incentives, distribution of LLINs and impregnation charge. Kindly refer to PIP page B-2, S.no F.1.1.b

- No action plan for IRS activities to justify Rs. 134 lakhs for spraymen wagfes and operational cost.

=	The number of spray men is increased from 334 to 350 along with their wages which was from Rs. 180/- to Rs. 250/- per day. This is because the new rate for unskilled labourer in Mizoram has recently increased. The amount for spray wages is Rs. 105 lakhs for 2 rounds. Operational costs which includes PPE, purchase of pumps etc amounts to Rs. 60 lakhs. The total amount for the wages and operational cost is Rs. 165 lakhs as against Rs. 134 lakhs mentioned in the comment. Kindly refer to the Action Plan page B-3, S.no F.1.1.c.i&ii.

- Justification for Rs. 48 lakhs towards monitoring and supervision not given.

=	Monitoring and supervision is envisaged for all State and District Consultants, MTS/VBD Supervisors and other staff which is reflected on the PIP page no B-3, S.no F.1.1.d; B-6, S.no F.1.2.c; B-8, S.no F.1.3.d; B-14, S.no F.3.d.

- Justification for Rs. 40 lakhs towards training not given.

=	Detailed training programme enclosed on PIP page no25-26, PIP budget B-4, S.No F.1.1.g. (Annex VII)

- Justification for Rs. 35.20 lakhs towards biological and environmental management not given.

=	Under Vector control & environmental management, only Rs. 2.40 lakhs is proposed and reflected in the PIP page no 18 and B-7, S.no F.1.2.f

- Justification for Rs. 76.19 lakhs towards Urban Malaria Scheme not given.

=	Justification for the above amounting to Rs. 78.29 lakhs speaks for itself on PIP page no 13-14 and B-5, S.no F.1.1.1

- Budget of Dengue and JE need a re-look and need to be given proper technical justification.

=   Budget of Dengue and JE reflected on PIP page no 15-21 and B-5 – B-9, S.no F.1.2 – F.1.3

- Since Dengue cases are very low, the existing sentinel sites may be strengthened fully before expanding the sentinel sites, where there is no case of Dengue due to climatic conditions.

=	The State started case report w.e.f October 2012. Out of 32 suspected cases, 6 cases of Dengue were found and treated. This could just be the tip of an iceberg. Inorder to ascertain the magnitude of Dengue in Mizoram, 3 new sentinel sites at strategic locations, 1 in the northern part and another 2 in the southern parts are proposed. The sites are indispensible to promptly detect the disease as the only existing site at Aizawl Civil Hospital may be too far for instantaneous diagnosis owing to the difficulty of the terrain. Besides, an influx of people from the border areas carrying the disease may contribute to the spread locally. The Programme does not wish to leave any chance to explore the possibility of an occurrence. Ref: PIP budget, B-6, S.No F.1.2.a.(ii).

- Justification for the decentralized may be given in details.

=	Decentralized items were calculated on the basis of norms given by the NVBDCP and reflected in the PIP page no B-15-17, F.5.

- District wise financial allocation, release and expenditure for 2012 -13 not given in the PIP.

=	This is enclosed for perusal on PIP page no 26 under the same head.

- One pager activity plan with expected outputs is not enclosed.

=	This is enclosed for perusal on PIP page no 27.

Training details : Annex VII of PIP

| S.No | Training | Cost per batch (Rs) | To be trained in the current year (no) |  |  |  | Total (no) | Total cost (Rs) |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Q1 | Q2 | Q3 | Q4 |  |  |
| 1 | Medical Officers | 200000 |  |  | 2 |  | 2 | 400000 |
| 2 | Lab Techs (re-orientation) | 100000 |  | 2 |  |  | 2 | 200000 |
| 3 | H/S (M) | 150000 |  | 2 |  |  | 2 | 300000 |
| 4 | H/S (F) | 150000 |  | 1 | 1 |  | 2 | 300000 |
| 5 | H/W (M) | 200000 |  |  | 3 | 2 | 5 | 1000000 |
| 6 | H/W (F) | 200000 |  |  |  | 5 | 5 | 1000000 |
| 7 | ASHA (re-orientation) | 100000 |  | 2 | 2 |  | 4 | 400000 |
| 8 | Malaria Programme Worker | 200000 |  |  |  | 1 | 1 | 200000 |
| 9 | Private Sector Providers | 100000 |  |  | 2 |  | 2 | 200000 |
|  | TOTAL |  |  |  |  |  |  | 4000000 |

District wise financial allocation, release and expenditure 2012-13 (upto Dec 2012): Annex VIII of PIP

| S.No | District | Allocation | Release | Expenditure |
| --- | --- | --- | --- | --- |
| 1 | Saiha | 22.46 | 11.23 | 15.91 |
| 2 | Serchhip | 28.32 | 14.16 | 13.31 |
| 3 | Lunglei | 44.74 | 22.37 | 21.72 |
| 4 | Champhai | 30.30 | 15.15 | 15.51 |
| 5 | Kolasib | 35.90 | 17.95 | 19.69 |
| 6 | Mamit | 34.66 | 17.33 | 17.33 |
| 7 | Lawngtlai | 40.18 | 20.09 | 22.96 |
| 8 | Aizawl West | 33.48 | 16.74 | 22.41 |
| 9 | Aizawl East | 24.52 | 12.26 | 17.13 |
| 10 | TOTAL | 294.56 | 147.28 | 165.97 |

Activity plan with expected outputs:

| S.No | Activity | Output |
| --- | --- | --- |
| 1 | DDT Spray | Increase in quality and acceptance of preventive measures |
| 2 | LLIN Distribution |  |
| 3 | Impregantion of bednets |  |
| 4 | Prompt surveillance | Quality surveillance, detection and monitoring. Increase of blood and case detections |
| 5 | Revival of Home visits: |  |
| a. | Once a month for H/W (F) |  |
| b. | Twice a month for H/W (M) |  |
| c. | Twice a month for Malaria Programme Worker |  |
| 6 | Training | Strengthening and assurance of manpower excellence |
| 7 | IEC/BCC : Print & Electronic media, infotainments, awareness etc | Public awareness, compliance and sustenance of healthy behavior |
| 8 | Monitoring & Supervision | Minimizing gaps in logistics, reports, administration etc by the Consultants |