No.G.20011/7/2011 – NRHM/PIP – II

National Rural Health Mission

Government of Mizoram

Directorate of Health Services

Mizoram : Aizawl

Dated Aizawl the 6th February 2013

To,

Smt.Anuradha Gupta

Additional Secretary & Mission Director

Ministry of Health & Family Welfare

Government of India

Nirman Bhavan, New Delhi

Subj :	Submission of Additional Plan to address NACP-NRHM Convergence in Mizoram

Madam,

I am submitting herewith an additional plan to address NACP-NRHM Convergence in Mizoram based on co-ordinated discussion with the Mizoram State AIDS Control Society under directives given by the National AIDS Control Organization, Deptt. Of AIDS, MoHFW during their Annual Action Plan discussion held at Guwahati during 29th February – 1st February 2013 for your kind consideration.

A soft copy of the same is also sent by email.

Yours faithfully,

(ESTHER LALRUATKIMI)

Secretary

Health & Family Welfare Department

Govt. of Mizoram

Memo No.G.20011/7/2011 – NRHM/PIP – II 			Dated Aizawl the 6th February 2013

Copy to :

- Ms.Preeti Pant, Director, NRHM-III, MoHFW

- Director, RRC-NE, Guwahati, MoHFW

- Director (Finance), NACO, Deptt of AIDS, MoHFW

- Project Director, Mizoram State AIDS Control Society

Secretary

Health & Family Welfare Department

Govt. of Mizoram

NACP – NRHM Convergence Plan for Mizoram

Intro : Practically on the ground NRHM and Mizoramsacs shared most of the delivery points for their program implementation. Mizoramsacs has the following facilities for carrying activities under National AIDS Control Program. Converge efforts in the previous financial year has yielded to high MCH service quality. IPC has been done with almost 100% of ANC attending women who came to the ICTC which is annually more than 20,000. The counselling done by the ICTC comprehensively address MCH, FP, psycho-social support which has been of immense importance among the Mizos. This has accelerated further the objectives in terms of institutional delivery, infant feeding practice, routine vaccine and immunization and parental care for infants and children.

| s/n | Category and number of delivery points | Number of ICTCs | Number of Mobile ICTCs | Facility Integrated ICTCs | Number of Blood Bank | Number of ART Centre | Number of Link ART Centre | Designated STI/RTI Clinic | Community care centre |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | 8 District Hospital | 8 | 9 | 0 | 8 | 3 | 5 | 8 |  |
| 2 | 2 Mother NGOs viz Synod Hospital Durtlang and Serkawn Christian Hospital, Lunglei | 2 | 1 |  | 2 |  |  |  | 2 |
| 3 | CHCs | 9 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |
| 4 | 5, 24x7 PHCs | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
| 3 | 27, 24x7 PHCs | 0 | 0 | 27 | 0 | 0 | 0 | 0 | 0 |
| 4 | Falkawn Referral Hospital | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 |

From the above table it can be seen that in the Major Health Service units that exist in the State, to say, total 8 District Hospital, 1 Referral Hospital, all the existing 9 CHCs, 41, 24x7 PHCs and the two major Church Based Hospital NGOs. These Centres cater to more than 90% of the total Health Service load in the State.

Rationale : Most of the activities carried out in the National AIDS Control Program has now become more of the State mandate e.g Blood Safety, STI/RTI Control, School Health/Adolescent Education Program/ARSH, Prevention of Mother to Child Transmission and Maternal Child Health, Universal Work Precaution, Condom Promotion etc hence integration of AIDS Control Program in the existing health care system and administration has become an utmost necessity for ensuring continuity, ownership and mainstreaming.

CONVERGENCE ACTIVITY PLAN

The following tables showed the plan for convergence which will be met from NRHM PIP.

| s/n | Focussed area | Proposed activity/strategy | Budget implication (INR) | Remarks |
| --- | --- | --- | --- | --- |
| 1 | STI/RTI Control Program through facility and IEC Strengthening Justification: STI/RTI performance of NRHM facilities has always been very poor due to many factors. Among these are absence of audio-visual privacy & equipments for examination, poor awareness regarding STI/RTI among key health staff and general public. | Enhance quality of service by provision of basic equipments to all 57 PHCs, 9 CHCs and 3 Sub-District hospitals (total= 69 centres) : A speculum and a proctoscope for all clinics | 1,10,400.00 | 2 Vaginal Speculum each per centre and 2 proctoscope per centre estimated @ Rs.200/speculum and Rs.600/proctoscope, and 2 for each centres |
|  |  | Procurement of RPR/VDRL test kits for 26,000 ANC and 12,618 estimated STI cases | 2,31,708.00 | 38,618 test @ Rs.6/test |
|  |  | Minor refurbishment for 3 Sub-District Hospitals, 9 CHCs and 57 PHCs to ensure audio-visual privacy | 20,70,000.00 | 69 Health Institutions require minor civil works/refurbishment @ Rs.30,000/centre |
|  |  | IEC materials development on STI/RTI | 5,00,000.00 | Hoardings for all delivery points and reading materials e.g leaflet/pamphlet |
|  |  | IPC Campaign with 745 Local Council/Village Council | 7,45,000.00 | @ Rs.1,000 /Council |
|  | Capacity building of ANM and Nurses on STI/HIV screening through single finger prick test | 300 ANM and 25 Nurses to be trained on Whole Blood Testing and RPR/VDRL test | 9,75,000.00 | @ Rs.1000/person/day for 3 days |
| 2 | Ensuring Safe and quality blood | Provision of RPR/VDRL test kits to all blood banks | 1,37,850.00 | VDRL/RPR test kits required for 22,930 blood units |
| 3 | Integrating MCH services with PPTCT | Refresher training for ICTC Counselors and district ICTC Supervisors on MCH | 1,54,800.00 | 1200/day x 43 Counselors + 3 District Supervisors x 3 days |
| 4 | Increase institutional delivery and PPTCT services | Safe delivery kits for all institutional deliveries | 78,00,000.00 | 26,000 deliveries x 300 |
| 5 | Monitoring and Supervision | Joint field visit of NACP, NRHM common sites by both SACS and NRHM Officials | N.A | This will focus on STI/RTI, HIV-TB, RCH/PPTCT performance indicators |
| 6 | Site sensitization on NACP-NRHM Convergence | @ Rs. 5,000/centre for 8 District Hospitals, 3 Sub-District Hospitals, 9 CHCs, 57 PHCs and 1 DHS level (Total=78) | 3,90,000.00 | Justification: It is observed that ignorance regarding NACP activities and the areas for NACP-NRHM convergence prevail among all categories of staff in health institutions of Mizoram. To bridge this gap, on-site sensitization is proposed. The benefits of this has already time tested in the instances of establishing new NACP service centres and Full Site Sensitization Conducted in the concerned centre. Mizoram SACS will conduct this activity in consultation with NRHM. |
|  |  | State Level review meeting of implementation progress once in a quarter and review of District level review meeting report | N.A |  |
|  |  | District level review meeting of NACP and NRHM led by the District Health Society | N.A |  |
|  | TOTAL BUDGET | 1,31,14,758.00 |  |  |