Background Information Required for Approval of State PIPs for 2013-14

F.M.R. Code- B 1 : ASHA

ASHA- Annexure-I

| Number of ASHA Required as per Rural population | Number of ASHA engaged (Atleast trained in 1st Module) | Shortfall | Target for 2013-14 |
| --- | --- | --- | --- |
| 1090 ( as per 2011 census) | 987 | 103 | NIL |

***** State will go ahead with existing ASHAs (987)

ASHA- Annexure-II

Status of ASHA Training

| Sl. No | Cumulative Achievement (Since inception -till date) | Proposed numbers to be trained in 13-14 |
| --- | --- | --- |
| Module 1 | 987 |  |
| Module 2 | 987 |  |
| Module 3 | 987 |  |
| Module 4 | 987 |  |
| Module 5 | 987 | Proposed Refresher training for 1 state ASHA Coordinator, 9 District ASHA Coordinators and 80 ASHA Mobilisers |
| Module 6 & 7 Round One | 987 | Proposed 1st round training for 1 state ASHA Coordinator, 9 District ASHA Coordinators and 80 ASHA Mobilisers |
| Module 6 & 7 Round Two | 987 ASHAs completed during 2012-13 | Proposed 2nd round training for 1 state ASHA Coordinator, 9 District ASHA Coordinators and 80 ASHA Mobilisers |
| Module 6 & 7 Round Three | 0 | 3rd Round ToT at the State level and 3rd round training for 1 state ASHA Coordinator, 9 District ASHA Coordinators and 80 ASHA Mobilisers |
| Module 6 & 7 Round Four | 0 | 4th Round ASHA training for all 987 ASHAs |

ASHA- Annexure-III

ASHA Drug Kits

| Number of ASHA Engaged (Trained in Module-I) | 987 |
| --- | --- |
| Number of ASHA with Drug Kits | 987 |
| Number of ASHA with HBNC Kits | 987 (Digital thermometer and weighing scale) |
| No. of New Drug Kits Required | 0 |
| No. of Drug kits to be Replenished | 987 |
| No. of New HBNC Kits required | (1)mucus extractor : 3000 (2) Home visit booklet : 19000 (3) Baby blanket : 19000 |
| No. of HBNC Kits to be Replenished | Nil |

| Sr. No. | Name of Drug in Drug Kit | Quantity |
| --- | --- | --- |
| 1 | Cotrimoxazole (Trimethoprim – 80 mg+, sulphamethoxazole – 400 mg) | 50 Tab |
| 2 | Tetracycline 250 | 50 caps |
| 3 | Tab Paracetamol 500mg | 100 Tab |
| 4 | Provident Ointment tube 5gm tube | 1 Tube |
| 5 | Band Aid | 20 nos |
| 6 | Cotton absorbent roll of 100 gm | 1 Roll |
| 7 | Bandage, 4cmx4meters ( Paper wrapped) | 10 Rolls |

| Sr. No. | Name of Instrument/ drug/ communication material in HBNC Kit | Quantity |
| --- | --- | --- |
| 1 | Mucous Extractor | 1000 x 3 = 3000 nos |
| 2 | Home visit booklet (for every live births) | 19,000 books |
| 3 | Baby blanket (size : 1mx1m) | 19,000 |

ASHA- Annexure-IV

Incentives for ASHAs

| Sl. No | Incentive | Amount proposed per ASHA | Target Population | Total Amount Proposed |
| --- | --- | --- | --- | --- |
| 1 | Incentive under JSY / Incentive under Maternal Health | @ Rs. 350 | 14800 | Budgeted under part-A (Maternal Health) |
| 2 |  |  |  |  |
| 3 | B1.1.3.2.1 Incentive under Child Health (HBNC/ home visit) | @ Rs. 250 | 19,000 (no. of live births in a year ) | Rs. 47,50,000 |
| 4 | Incentive under immunization programme | @ Rs. 150 | 24666 | Budgeted under Part C (Immunisation) |
| 5 | Incentive under Family Planning |  |  |  |
| a. | Ensuring spacing of 2 years after marriage | @ Rs. 500 | 200 | Budgeted under part-A (Family Planning) |
| b. | Ensuring spacing of 3 years after the birth of 1st child | @ Rs. 500 | 1000 | Budgeted under part-A (Family Planning) |
| c. | Opts for a permanent limiting method upto 2 children | @ Rs. 1000 | 2000 | Budgeted under part-A (Family Planning) |
| 6 | Incentive under DOTS Programme (ASHA as DOTS provider) | @Rs.250 | 500 | Budgeted under NDCP (RNTCP) |
| 7 | Incentive under leprosy Programme | 0 | 0 | Budgeted under NDCP (NLEP) |
| 8 | Incentive under Disease control Programmes (SVBDCP) |  |  |  |
|  | - Blood slide | @ Rs.290 | 1057 | Budgeted under NDCP (NVBDCP) |
|  | - LLIN | @ Rs. 10 | 1,00,000 | Budgeted under NDCP (NVBDCP) |
| 9 | Any other (please specify) |  |  |  |

ASHA- Annexure-V

| Human Resource | Required as per norms | Approved 2012-13 |  |  | Proposed 2013-14 |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | No. In position | Monthly Remuneration | Total Amount Approved | No. | Monthly Remuneration | Total Amount |
| State ASHA Coordinator at State Level | 1 | 0 | 0 | 0 | 1 | 20,000 | 2.4 |
| ASHA Coordinator at District Level | 9 | 9 | 8000 per month | 6.48 | 9 | 8000 per Month | 8.64 |
| ASHA Coordinator at Block Level/ Block Community Mobilizer for ASHA |  |  |  |  |  |  |  |
| ASHA Facilitator / ASHA Mobilisers at PHC/CHC/SDH/main centres | 80 ASHA Mobilisers at each CHC, PHC, 1SDH and all main centres | 66 ASHA Mobilisers at 9 CHC and 57 PHC | 4000 per Month | 23.76 | 66 +13+1 = 80 (13 main centres and 1 SDH | 4000 Per Month | 38.4 |
| Any other please specify |  |  |  |  |  |  |  |

Remarks : 1. There is no block system under H&FW Dept, Govt of Mizoram

2. Budget on the above annexure – V has been calculated under detailed work plan annexure :  B1.1.51/ B1.1.51/ B1.1.51

Detailed ASHA work plan - annexures

Accredited Social Health Activists (ASHA)

F.M.R. Code – B 1 : ASHA

District wise strength of ASHA :

| Name of District | No. of ASHA engaged |  |  | Selected / In place ASHA | Status of ASHA trained |  |  |  |  |  |  |  |  | Drug kits distributed to ASHA |  | 2nd round Mod 6&7 ASHA training |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | Mod-1 | Mod-2 | Mod-3 | Mod-4 |  | Mod5 |  | Mod 6&7 (1st round and refresher training) |  |  |  |  |
| Aizawl E | 124 |  |  | 124 | 124 | 124 | 124 | 124 |  | 124 |  |  | 124 | 124 |  | completed |
| Aizawl W | 119 |  |  | 119 | 119 | 119 | 119 | 119 |  | 119 |  |  | 119 | 119 |  | completed |
| Kolasib | 75 |  |  | 75 | 75 | 75 | 75 | 75 |  | 75 |  |  | 75 | 75 |  | completed |
| Mamit | 62 |  |  | 62 | 62 | 62 | 62 | 62 |  | 62 |  |  | 62 | 62 |  | completed |
| Serchhip | 54 |  |  | 54 | 54 | 54 | 54 | 54 |  | 54 |  |  | 54 | 54 |  | completed |
| Champhai | 122 |  |  | 122 | 122 | 122 | 122 | 122 |  | 122 |  |  | 122 | 122 |  | completed |
| Lunglei | 186 |  |  | 186 | 186 | 186 | 186 | 186 |  | 186 |  |  | 186 | 186 |  | completed |
| Lawngtlai | 174 |  |  | 174 | 174 | 174 | 174 | 174 |  | 174 |  |  | 174 | 174 |  | completed |
| Saiha | 71 |  |  | 71 | 71 | 71 | 71 | 71 |  | 71 |  |  | 71 | 71 |  | completed |
| TOTAL | 987 |  |  | 987 | 987 | 987 | 987 | 987 |  | 987 |  |  | 987 | 987 |  |  |
| B1.1.5.1/ B1.1.5.2/ B1.1.5.3 HONORARIUM FOR EXISTING DISTRICT ASHA COORDINATORS AND ASHA MOBILISERS, NEW SELECTION OF STATE ASHA COORDINATOR AND ASHA MOBILISERS AT 13 MAIN CENTRES AND 1 SDH : No of post : 1 State ASHA Coordinator and 14 ASHA Mobilisers Place of Posting : State ASHA Coordinator @ NRHM, SPMSU Section, Directorate of Health Services and 13 main centres + 1 main centres (SDH) List of main centres proposed to select ASHA Mobilisers: - Aizawl East main centre - Aizawl North main centre - Aizawl West main centre - Aizawl South main centre - Lunglei North main centre - Lunglei South main centre - Zobawk main centre - Champhai main centre - Kolasib main centre - Serchhip main centre - Mamit main centre - Lawngtlai main centre - Saiha main centre and - Tlabung SDH/main centre These are the centres which are located at the district capital/town area attached to DH/CMO office. The offices are functioning with health Supervisors (male & female), Health workers (male & female). All the achievements reports are collected from various sub centres and compilation is done at the main centre office. Likewise Main centres office is functioning at Tlabung SDH as well. Sl.No; Particulars; No. of manpower; Honorarium per month; Unit Cost. B1.1.5.1; Selection of State ASHA Coordinator; 1; 20,000; 20,000x12 = 2,40,000. B1.1.5.2; Honorarium for District ASHA Coordinator; 9; 8000; 8000 x 9 x 12 = 8,64,000. B1.1.5.3; Honorarium for Existing ASHA Mobilisers at 57 PHC, 9 CHC; 66; 1000 + incentives @200x15 visits = 4000; 66x4000x12 = 31,68,000. Selection of new ASHA Mobilisers at 13 main centres and 1 SDH; 14; 1000 + incentives @200x15 visits = 4000; 14x4000x12 = 6,72,000. Total; Rs.49,44,000. Total budget : Rs. 49,44,000/- (Rupees forty nine lakhs and forty four thousand) only. B1.1.3.6.2 REPRINTING/TRANSLATION OF ASHA 6&7 MODULE As it has been decided that modules in local language will be given to ASHAs, so it is decided to print Module 6 & 7 in local language. Thus, it is proposed in PIP 2013-14. 6th Module book : 987 Copies for ASHA, 90 Copies for ASHA Facilitators, 9 copies for DPM and 4 copies for Trainers and 10 copies for SPMSU = 1100 copies 7th Module book : 987 Copies for ASHA, 90 Copies for ASHA Facilitators, 9 copies for DPM and 4 copies for Trainers and 10 copies for SPMSU = 1100 copies Work Plan for Reprinting/translation of ASHA module 6&7 : Description of items; Quantity; Rate/unit cost; Total amount. Module 6; 1100; @ Rs 200; 2,20,000. Module 7; 1100; @ Rs 200; 2,20,000. Total; Rs. 4,40,000. Total Budget : Rs.4,40,000/- (Rupees four lakhs and forty thousand) only B1.1.1.4.2 WORK PLAN FOR INDUCTION TRAINING OF NEWLY SELECTED STATE ASHA COORDINATOR AND NEW ASHA MOBILISERS Proposed no. of participants : 1 + 14 + 4 + 5 + 3 = 27. Head; No. of Participants/Particulars; Unit cost/ Rate (in Rupees); No. of persons; No. of days; Total budget. TA for (to and fro); ASHA Mobilisers at 13 main centres and 1 SDH = 14; @ Rs. 650; 14; 2; 18,200. DA; 14 ASHA Mobilisers + 1 State ASHA Coordinator + 5 supporting staff; @ Rs.200; 20; 2; 8000. 2 state Officials + 1 Observer; @ Rs. 500; 3; 2; 3000. Honorarium; Resource persons/Trainers; @ Rs.700; 4; 2; 5600. TA/DA Total; 31,200. Training materials; Notepad, pen, folder, marker, chart paper, white board etc.; 100/- per head; 15+4+5+3 = 27; 2700. Banner; Banner to put up at the training Hall; 1000/-; 1000. Refreshments; Lunch packages, Mineral water, Tea/coffee etc.; 100/- per head; 15+4+5+3 = 27; 2; 5400. Hall Rent; Hall rent at the state training site; 500/-; 2; 1000. TOTAL; 44,900. Grand Total: Rs. 44,900/- (Rupees forty four thousand nine hundred ) only.. B1.1.1.4.3 WORK PLAN FOR 5th MODULE TRAINING FOR STATE/DISTRICT ASHA COORDINATORS AND ASHA MOBILISERS AT STATE Proposed no. of Participants : 80 + 4 + 5 +1 = 90 |
| Head |  |  | Particulars/Requirements |  |  |  |  |  | Rate (in Rupees) |  | No. of persons |  |  |  | No. of days | Total budget |
| TA for trainees – actual sumo fare (to and fro) |  |  | 9 District ASHA Coordinators and 72 ASHA Mobilisers |  |  |  |  |  | 650 |  | 80 |  |  |  |  | 1,04,000 |
| DA |  |  | No. of trainees : 80 + 1 State ASHA Coordinator |  |  |  |  |  | 200 per day |  | 81 |  |  |  | 5 days | 81,000 |
|  |  |  | Supporting staff |  |  |  |  |  | 200 |  | 5 |  |  |  | 5 days | 5000 |
| Honorarium |  |  | Resource persons / Trainers /Observer |  |  |  |  |  | 700 |  | 4 |  |  |  | 5 days | 14,000 |
| TA/DA Total |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 2,02,400 |
| Material |  | Training material : notepad, pen, folder, Chart paper, marker pen etc. |  |  |  |  |  |  | 100 per head |  | 80+5+4+1=90 |  |  |  |  | 45,000 |
| Banner |  | Banner to put up at the training Hall |  |  |  |  |  |  | 1000 |  |  |  |  |  |  | 1000 |
| Refreshments |  | Lunch packages, Mineral water, Tea/coffee etc. |  |  |  |  |  |  | 100 per head |  | 80+5+4+1=90 |  |  |  | 5 days | 45,000 |
| Hall Rent |  | Hall rent at the state training site |  |  |  |  |  |  | 500 |  |  |  |  |  | 5 days | 2500 |
| TOTAL |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 2,93,500 |
| Grand Total : Rs. 2,93,500/- (Rupees three lakhs ninety three thousand and five hundred) only. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| B1.1.1.4.4 WORK PLAN FOR 1st round 6 &7 MODULE TRAINING FOR STATE/DISTRICT ASHA COORDINATORS AND ASHA MOBILISERS AT STATE Proposed no. of Participants : 80 + 4 + 5 +1 = 90 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Head |  |  | Particulars/No. of participants |  |  |  |  |  | Rate (in Rupees) |  | No. of persons |  |  |  | No. of days | Total budget |
| TA for trainees – actual sumo fare (to and fro) |  |  | 9 District ASHA Coordinators and 72 ASHA Mobilisers |  |  |  |  |  | 650.00 |  | 80 |  |  |  |  | 1,04,000 |
| DA |  |  | No. of trainees : 80 + 1 state ASHA Coordinator |  |  |  |  |  | 200/- per day |  | 81 |  |  |  | 5 days | 81,000 |
|  |  |  | DA for Mothers and Driver on Field practice |  |  |  |  |  | 200/- per head |  | 10 mothers + 1 driver + 1 helper |  |  |  | 1 day | 2400 |
|  |  |  | Supporting staff |  |  |  |  |  | 200/- |  | 5 |  |  |  | 5 days | 5000 |
| Honorarium |  |  | Resource persons / Trainers /Observer |  |  |  |  |  | 500/- |  | 4 |  |  |  | 5 days | 10,000 |
| TA/DA Total |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 2,02,400 |
| Material |  | Training material : notepad, pen, folder, Chart paper, marker pen etc. |  |  |  |  |  |  | 100/- per head |  | 80+5+4+1=90 |  |  |  |  | 45,000 |
| Banner |  | Banner to put up at the training Hall |  |  |  |  |  |  | 1000/- |  |  |  |  |  |  | 1000 |
| Refreshments |  | Lunch packages, Mineral water, Tea/coffee etc. |  |  |  |  |  |  | 100/- per head |  | 80+5+4+1=90 |  |  |  | 5 days | 45,000 |
| Hall Rent |  | Hall rent at the state training site |  |  |  |  |  |  | 500/- |  |  |  |  |  | 5 days | 2500 |
| Mobility |  | Transportation for field practice (Hirer of Bus) |  |  |  |  |  |  | 10,000/- (to and fro) |  |  |  |  |  | 1 day | 10,000 |
| TOTAL |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 3,05,900 |
| Grand Total : Rs. 3,05,900/- (Rupees three lakhs five thousand nine hundred) only. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

| B1.1.1.4.4.1 WORK PLAN FOR 2nd round 6 &7 MODULE TRAINING FOR STATE/DISTRICT ASHA COORDINATORS AND ASHA MOBILISERS AT STATE Proposed no. of Participants : 80 + 4 + 5 +1 = 90 |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Head |  |  | Particulars/No. of participants | Rate (in Rupees) | No. of persons | No. of days | Total budget |  |
| TA for trainees – actual sumo fare (to and fro) |  |  | 9 District ASHA Coordinators and 72 ASHA Mobilisers | 650.00 | 80 |  | 1,04,000 |  |
| DA |  |  | No. of trainees : 80 + 1 state ASHA Coordinator | 200/- per day | 81 | 5 days | 81,000 |  |
|  |  |  | DA for Mothers and Driver on Field practice | 200/- per head | 10 mothers + 1 driver + 1 helper | 1 day | 2400 |  |
|  |  |  | Supporting staff | 200/- | 5 | 5 days | 5000 |  |
| Honorarium |  |  | Resource persons / Trainers /Observer | 500/- |  | 5 days | 10,000 |  |
| TA/DA Total |  |  |  |  |  |  | 2,02,400 |  |
| Material |  | Training material : notepad, pen, folder, Chart paper, marker pen etc. |  | 100/- per head | 80+5+4+1=90 |  | 45,000 |  |
| Banner |  | Banner to put up at the training Hall |  | 1000/- |  |  | 1000 |  |
| Refreshments |  | Lunch packages, Mineral water, Tea/coffee etc. |  | 100/- per head | 80+5+4+1=90 | 5 days | 45,000 |  |
| Hall Rent |  | Hall rent at the state training site |  | 500/- |  | 5 days | 2500 |  |
| Mobility |  | Transportation for field practice (Hirer of Bus) |  | 10,000/- (to and fro) |  | 1 day | 10,000 |  |
| TOTAL |  |  |  |  |  |  | 3,05,900 |  |
| Grand Total : Rs. 3,05,900/- (Rupees three lakhs five thousand nine hundred) only. |  |  |  |  |  |  |  |  |

| B1.1.1.4.4.2 WORK PLAN FOR 3rd round 6 &7 MODULE TRAINING FOR STATE/DISTRICT ASHA COORDINATORS AND ASHA MOBILISERS AT STATE Proposed no. of Participants : 80 + 4 + 5 +1 = 90 |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Head |  |  | Particulars/No. of participants | Rate (in Rupees) | No. of persons | No. of days | Total budget |  |
| TA for trainees – actual sumo fare (to and fro) |  |  | 9 District ASHA Coordinators and 72 ASHA Mobilisers | 650.00 | 80 |  | 1,04,000 |  |
| DA |  |  | No. of trainees : 80 + 1 state ASHA Coordinator | 200/- per day | 81 | 5 days | 81,000 |  |
|  |  |  | DA for Mothers and Driver on Field practice | 200/- per head | 10 mothers + 1 driver + 1 helper | 1 day | 2400 |  |
|  |  |  | Supporting staff | 200/- | 5 | 5 days | 5000 |  |
| Honorarium |  |  | Resource persons / Trainers /Observer | 500/- |  | 5 days | 10,000 |  |
| TA/DA Total |  |  |  |  |  |  | 2,02,400 |  |
| Material |  | Training material : notepad, pen, folder, Chart paper, marker pen etc. |  | 100/- per head | 80+5+4+1=90 |  | 45,000 |  |
| Banner |  | Banner to put up at the training Hall |  | 1000/- |  |  | 1000 |  |
| Refreshments |  | Lunch packages, Mineral water, Tea/coffee etc. |  | 100/- per head | 80+5+4+1=90 | 5 days | 45,000 |  |
| Hall Rent |  | Hall rent at the state training site |  | 500/- |  | 5 days | 2500 |  |
| Mobility |  | Transportation for field practice (Hirer of Bus) |  | 10,000/- (to and fro) |  | 1 day | 10,000 |  |
| TOTAL |  |  |  |  |  |  | 3,05,900 |  |
| Grand Total : Rs. 3,05,900/- (Rupees three lakhs five thousand nine hundred) only. |  |  |  |  |  |  |  |  |

| B1.1.1.4.5 BUDGET PLAN FOR 3rd ROUND STATE LEVEL ASHA ToT ON MOD 6&7 List of proposed participants from Districts : DPM and District ASHA Coordinator (9 Districts) |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Head | Particulars/Requirements | Rate (in Rupees) | No. of persons | No. of days | Total budget |
| TA for trainees – actual sumo fare (to and fro) | Saiha District | 650/ | 2 |  | 1300 |
|  | Lawngtlai | 600/ | 2 |  | 1200 |
|  | Lunglei | 400/ | 2 |  | 800 |
|  | Serchhip | 250/ | 2 |  | 500 |
|  | Champhai | 400/ | 2 |  | 800 |
|  | Mamit | 250/ | 2 |  | 500 |
|  | Kolasib | 200/ | 2 |  | 400 |
| DA | Trainees (18 from Districts + 2 District Trainers) | 200/- per day | 20 | 5 days | 20,000 |
|  | DA for Mothers and Driver on Field practice | 100/- per head | 8 mothers + 1 driver + 3 helper (12) | 1 day | 1200 |
|  | Supporting staff | 200/- | 5 | 5 days | 5000 |
| Honorarium | Resource persons/State Trainers/Observer | 700/- | 4 | 5 days | 14,000 |
| Material | Training material : notepad, pen, folder, Chart paper, marker pen etc. | 100/- per head | 22+4=26 |  | 2600 |
| Banner | Banner to put up at the training Hall | 1000/- |  |  | 1000 |
| Refreshments | Lunch packages, Mineral water, Tea/coffee etc. | 100/- per head | 35 | 5 days | 17,500 |
| Hall Rent | Hall rent at the state training site | 500/- |  | 5 days | 2500 |
| Mobility | Transportation for field practice (Hirer of Bus) | 10,000/- (to and fro) |  | 1 day | 10,000 |
| TOTAL |  |  |  |  | 79,300 |
| Grand Total : Rs. 79,300/- (Rupees seventy nine thousand and three hundred) only. |  |  |  |  |  |

| B1.1.1.4.6 BUDGET PLAN FOR 4th ROUND ASHA TRAINING ON MOD 6&7 AT DISTRICT LEVEL List of proposed participants at each Districts : ASHA, District ASHA Coordinator, ASHA Mobilisers and other supporting staff (9 Districts) |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Head | Particulars/Requirements | Rate (in Rupees) | No. of participants | No. of days |  | Total budget |
| TA for trainees – actual sumo fare (to and fro) | Saiha District | 200 | 71 + 4=75 |  |  | 15,000 |
|  | Lawngtlai |  | 174+5=180 |  |  | 36,000 |
|  | Lunglei |  | 186+11 = 197 |  |  | 39,400 |
|  | Serchhip |  | 54+6= 60 |  |  | 12,000 |
|  | Champhai |  | 122+13= 135 |  |  | 27,000 |
|  | Mamit |  | 62+8=70 |  |  | 14,000 |
|  | Kolasib |  | 75+6=81 |  |  | 16,200 |
| DA | Trainees (987 + 80 ASHA Mobilisers + 9 District ASHA Coordinators) | 200/- per day | 1076 | 5 days |  | 10,76,000 |
|  | DA for Mothers and Driver on Field practice | 100/- per head | 8 mothers + 1 driver + 3 helper (12) | 1 day |  | 1200 |
|  | Supporting staff | 200/- | 3 | 5 days |  | 3000 |
| Honorarium | Resource persons/District trainers/Observer | 700/- | 4 | 5 days |  | 14,000 |
| Material | Training material : notepad, pen, folder, Chart paper, marker pen etc. | 100/- per head | 987+80+9+4=1080 |  |  | 1,08,000 |
| Banner | Banner to put up at the training Hall | 1000/- |  |  |  | 1000 |
| Refreshments | Lunch packages, Mineral water, Tea/coffee etc. | 100/- per head | 987+80+9+4+3=1083 | 5 days |  | 5,41,500 |
| Hall Rent | Hall rent at the state training site | 500/- |  | 5 days |  | 2500 |
| Mobility | Transportation for field practice (Hirer of Bus) | 10,000/- (to and fro) |  | 1 day |  | 10,000 |
| TOTAL |  |  |  |  |  | 19,16,800 |
| Grand Total : Rs. 19,16,800/- (Rupees nineteen lakhs sixteen thousand and eight hundred) only. |  |  |  |  |  |  |

B1.1.2.2 REPLENISHMENT OF ASHA DRUG KITS :

| Sr. No. | Name of Drug in Drug Kit | Quantity |
| --- | --- | --- |
| 1 | Cotrimoxazole (Trimethoprim – 80 mg+, sulphamethoxazole – 400 mg) | 50 Tab |
| 2 | Tetracycline 250 | 50 caps |
| 3 | Tab Paracetamol 500mg | 100 Tab |
| 4 | Provident Ointment tube 5gm tube | 1 Tube |
| 5 | Band Aid | 20 nos |
| 6 | Cotton absorbent roll of 100 gm | 1 Roll |
| 7 | Bandage, 4cmx4meters ( Paper wrapped) | 10 Rolls |

| Sr. No. | Quantity | Frequency of refilling | Unit cost/rate | Total amount in Rs. |
| --- | --- | --- | --- | --- |
| 1 | 1000 kits | Twice in a year | @ Rs. 350 | 7,00,000 |
| Total Budget : Rs. 7,00,000/- (Rupees seven lakhs) only. |  |  |  |  |

B1.1.2.4 PROCUREMENT OF  HOME BASED NEWBORN CARE KIT

| Sl.no | Name of kits | Quantity | Rate/unit cost | Total amount |
| --- | --- | --- | --- | --- |
| 1 | Mucous extractor | 1000 x 3 pcs = 3000 | @ Rs. 40 | 1,20,000 |
| 2 | Home visit booklet | 19,000 (total estimated live births in a year) | @ Rs. 20 | 3,80,000 |
| 3 | Baby blanket (size : 1mx1m) | 19,000 (total estimated live births in a year) | @ Rs 300 | 57,00,000 |
| Total |  |  |  | Rs.62,00,000 |

Total Budget :Rs. 62,00,000/- (Rupees sixty two lakhs) only.

.

| B1.1.3.6.1 REVIEW MEETING FOR ASHA AND ASHA FACILITATORS AT DISTRICT LEVEL No. of meeting / frequency proposed to be held : Quarterly Proposed nominees to attend the meeting : ASHA, ASHA Mobilisers, District ASHA Coordinators and DPMs. |  |
| --- | --- |
| Head; Total no. of participants from PHC/CHC/SDH; Unit cost (in Rupees); No. of days; Rate in Rs; Amount. TA (to and fro) for ASHA and ASHA Mobilisers; 987 + 80 = 1067; 200/- per head to and fro; 2; 200 x 1067x4; 8,53,600. DA; 987+80+9+9+ (3 supporting staff) = 1088; 200/-; 1; 1088x200x4; 8,70,400. Refreshments; Lunch packages, Mineral water, Tea etc.; 100/- per head; 1; 100x1088x4; 4,35,200. TOTAL; 21,59,200. Total Budget : Rs. 21,59,200/- (Rupees twenty one lakhs fifty nine thousand two hundred) only.. B1.1.5.4 REVIEW MEETING FOR ASHA MENTORING GROUP AT STATE LEVEL. Head; Particulars/Requirements; Rate (in Rupees); No. of persons; Frequency; Amount. TA/DA for AMG members; Quarterly review meeting; 300/- per members; 15; 4 Quarters; 18,000. Banner; Banner to put up at the meeting Hall; 1000; 4 Quarters; 4000. Refreshments; Lunch packages, Mineral water, Tea/coffee etc.; 100 per head; 15; 4 Quarters; 6000. Field exposure for AMG members; Hirer of vehicle for field visit; @ 4000 per headx 15 = 60,000; 4 quarters; 2,40,000. Total; 2,68,000. Total budget : Rs.2,68,000/- (Rupees two lakhs sixty eight thousand) only. |  |

B1.1.3.6.2 		Action plan  for ASHA Conference:

There are 987 Accredited Social Health Activist (ASHA) in Mizoram. ASHAs are the grass root and voluntary public workers who played one of the most essential role in achieving the aims and goals of NRHM. Due to their hard work and the success that they have achieved, ASHA Conference will be organize and observe for one day at each District on the day when NRHM was launched, i.e 12th April (from 13th April, 2012 onwards). On this day, different ASHAs from all the Villages will be sharing their success stories so that everyone could gain something from someone’s experience. This can motivate and challenge them to perform better.

On this day, the ASHAs would portray through short play/drama an awareness relating to mothers and pregnant women, the advantages of delivering in hospitals or delivery under the guidance of trained personnel and the importance of regular check-up and treatment after delivery. The ASHAs may share their best practices story on this day. The best ASHAs will be awarded at each Districts based on her performance throughout the rear. The criteria for the award may be work out by the concerned CMO, CHO/HS and VHSNC members. The grading system format may be prepared at each District. The programme will be covered through Media local channels to create awareness within the community on the ASHA programmes.

The budget approved for the FY 2012-13 was 4.6 lakhs only. The conference could not be observed due to insufficient approval of fund. Thus, the additional requirements of fund for ASHA Conference is proposed again as follows :

Proposed list of participants : ASHA, ASHA Mobilisers, District ASHA Coordinators and other supporting staff at each District.

WORK PLAN FOR OBSERVATION OF ASHA CONFERENCE AT DISTRICT LEVEL :

| Head | Particulars/Requirements | Rate (in Rupees) | No. of persons per District | Total Amount |
| --- | --- | --- | --- | --- |
| TA/DA for ASHAs and ASHA Mobilisers (to and fro) | Transportation cost and DA | 400 per head | 987+80= 1067 | 4,26,800 |
| DA for Supporting staff |  | 200/- per head | 5x9 | 9000 |
| Offering Award to best performing ASHAs throughout the year |  | @Rs 2000/ per ASHA | 1x9 | 18,000 |
| Banner | Banner to put up at the conference Hall | 1000/- |  | 1000 |
| Refreshments | Lunch packages, Mineral water, Tea/coffee etc. For ASHA and other supporting staff | @200/- per head | 1067+33=1100 | 2,20,000 |
| Stage arrangement | Sound system/Banquet | @10,000 | 10,000 x 9 | 90,000 |
| Hall Rent | Hall rent at the District HQ | 1000x9 |  | 9000 |
|  |  |  | Total | 7,73,800 |
| Amount available with the state as per approval of 12-13 |  |  |  | 4,60,000 |
| Amount required in 2013-14 for conducting the event |  |  |  | Rs. 3,13,800 |

Total Budget for ASHA Conference : Rs.3,13,800 /- (Rupees three lakhs thirteen thousand eight hundred only).

Justification on comments : An amount of Rs.0.18 lakhs of award to ASHA has been budgeted under state budget sheet of B1.1.4 whereas lump sum budgeted is shown on this work Plan annexure.

Consolidated Budget of ASHA Programme for 2013-14:

| Sl. No. | FMR Code | Activity | Proposed Budget |
| --- | --- | --- | --- |
| 1 | B1.1.5.1/ B1.1.5.2/ B1.1.5.3 | New Selection of State ASHA Coordinator and Honorarium of existing District ASHA Coordinator and ASHA Mobilisers at PHC/CHC and new ASHA Mobilisers at 13 main Centres and 1 SDH | 49,44,000 |
| 2 | B1.1.3.6.2 | Reprinting and translation of ASHA Module 6&7 | 4,40,000 |
| 3 | B1.1.1.4.2 | Induction Training of newly selected State ASHA Coordinator and new ASHA Mobilisers | 44,900 |
| 4 | B1.1.1.4.3 | 5th Mod training for State ASHA Coordinator, District ASHA Coordinators and ASHA Mobilisers | 2,93,500 |
| 5 | B1.1.1.4.4/ B1.1.1.4.4.1/ B1.1.1.4.4.2 | 6&7 Mod training for State ASHA Coordinator, District ASHA Coordinators and ASHA Mobilisers | 9,17,700 |
| 6 | B1.1.1.4.5 | 3rd round State level ASHA ToT on Mod 6&7 | 79,300 |
| 7 | B1.1.1.4.6 | 4th round ASHA training on Mod 6&7 at District level | 19,16,800 |
| 8 | B1.1.2.2 | Replenishment of ASHA Drug Kits | 7,00,000 |
| 9 | B1.1.2.4 | Procurement of ASHA HBNC Kit | 62,00,000 |
| 10 | B1.1.3.6.1 | Review Meeting for ASHA and ASHA Facilitators at District level | 21,59,200 |
| 11 | B1.1.5.4 | Review meeting for ASHA Mentoring Group at State level | 2,68,000 |
| 12 | B1.1.3.6.2 | Observation of ASHA Conference at District level | 3,13,800 |
| 13 | B1.1.3.2.1 | Incentive to ASHA under Child Health on Home Visit | 47,50,000 |
| TOTAL |  |  | 230,27,200 |

Grand Total of FMR Code-B 1 ASHA :     Rs. 230,27,200/- (2.3 crores)

(Rupees Two hundred and thirty lakhs twenty seven thousand two hundred) only.

Remarks : Budget under ASHA Annexure – V  is calculated under the detailed ASHA work Plan annexure - B1.1.51/ B1.1.51/ B1.1.51.

8.6