Background Information Required for Approval of State PIPs for 2013-14

F.M.R. Code: A.3- Family Planning

FP: Annexure -1

| SN. | Indicator | Target / ELA 2012-13 | Achievements (as on date) | Remarks |
| --- | --- | --- | --- | --- |
| 1 | Goal (target): |  |  |  |
| 1.1 | Reduction in TFR – 2013 | Maintain TFR level | Na | Current status 2.9 (NFHS-3) |
| 2 | Service delivery (ELA): |  |  |  |
| 2.1 | IUCD: |  |  | - |
| 2.1.1 | Post-partum IUCD | 300 | 1608 | - |
| 2.1.2 | Interval IUCD | 4700 |  | - |
| 2.2 | Sterilisation: |  |  | - |
| 2.2.1 | Tubectomy | 1500 | 547 | - |
| 2.2.2 | Post-partum sterilisation (subset of tubectomy) | 1500 | 614 | - |
| 2.2.3 | Vasectomy | 10 | 1 | - |
| 3 | Training of personnel (target): |  |  |  |
| 3.1 | Post-partum IUCD |  |  |  |
| 3.1.1 | MO | - | - | - |
| 3.1.2 | SN/ ANM | - | - | - |
| 3.2 | Interval IUCD |  | - | - |
| 3.2.1 | MO | - | - | - |
| 3.2.2 | SN | - | - | - |
| 3.2.3 | ANM/ LHV | 50 | 47 | - |
| 3.3 | Minilap | 10 | 4 | - |
| 3.4 | NSV | - | - | - |
| 3.5 | Laparoscopic | 1 team | 0 | - |
| 4 | Others (target): |  |  |  |
| 4.1 | Appointment of FP Counsellors | 100% (DH) | 2 | - |
| 4.3 | Regular reporting of the scheme of “home delivery of contraceptives by ASHAs” | Regular reporting | - | - |
| 4.4 | Fixed Day Services for IUCD | Twice a week CHC-9, SDH-2, PHC-40 | 0 | - |
| 4.5 | Fixed Day Services for Sterilisation | Once Monthly, CHC-9, PHC-41 | 0 | - |

FP: Annexure -II

FORMAT FOR FAMILY PLANNING FOR ACTIVITIES FOR 2013-14 PIP

| SN. | STRATEGY / ACTIVITY | Cumulative achievement (as on 31st March 2012) | PLANNED | ACHIEVED | WORK PLAN | SCHEDULED/ Trg. LOAD | BUDGET (In lakhs) | REMARKS |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | 2012-13 |  | 2013-14 |  |  |  |
| 1 | FAMILY PLANNING MANAGEMENT |  |  |  |  |  |  |  |
| 1.1 | Review meetings on Family Planning performance and initiatives at the state and district level (periodic; including QAC meetings)) | NR | Quarterly at State and District |  |  | 40 meetings | 4.00 | Quarterly review meeting at State and all Districts. ( FP performance has been reviewed during NRHM State and District quarterly review meeting, expenditure has been incurred from the budget allotted under M&E. However, it has been planned to organize separate review meeting on FP during 4th quarter. Therefore no physical and financial achievements has been mentioned for 2012-13 under this head. It may also be noted that all the approved activities could not be taken up due to shortage of fund |
| 1.2 | Monitoring and supervisory visits to districts/ facilities | NR | 150 |  |  |  |  | - |
| 1.3 | Orientation workshops on technical manuals of FP viz. standards, QA, FDS approach, SOP for camps, Insurance etc. ( Orientation for Service Providers, State & District FP Programme Officers, DPM etc) | NR | 2 batches | 0 |  | 3 batches | 1.50 | Budgeted @ Rs.50,000/- per batch. Planned to be organized at State Hqrs. It is expected that 30 participants per batch. This activity has not been taken up due to shortage of fund. |
| 2 | SPACING METHOD (Providing of IUCD services by districts) |  |  |  |  |  |  |  |
| 2.1 | Plan for providing FDS (Fixed Day Static) IUCD services at health facilities in districts (at least 2 days in a week at SHC and PHC level) – number of facilities to be provided |  | SDH-2, CHC-9, PHC-40, atleast 2 days per week | SDH-2, CHC-9, PHC-40, 2 days per week | - | SDH-2, CHC-9, PHC-40, atleast 2 days per week |  | No separate budget is required |
| 2.2 | No. of IUCD camps in districts | NR | - | - | - | - | - | - |
| 2.3 | Compensation for IUCD | NR | 5000 | 1608 |  | 5000 | 1.00 | - |
| 2.4 | Plan for strengthening PPIUCD services | NR | Not approved |  |  |  |  |  |

| 3 | TERMINAL/LIMITING METHODS ( Providing sterilization services in districts) |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 3.1 | Plan for facilities providing FEMALE sterilization services on fixed days at health facilities in districts (number of facilities) | NA | 9 CHC, 41 PHC once a month | 0 | 8 DH, 9 CHC, 41PHC-1day per week, | - |  | Compensation to beneficiaries will be given from relevant budget head. Hence no separate budget is required |
| 3.2 | Plan for facilities providing NSV services on fixed days at health facilities in districts (number of facilities) | - | - | - | - | - | - | - |
| 3.3 | Number of FEMALE Sterilisation camps in districts. | NR | 15 | 4 | - | 20 | 3.00 @ RS.15,000/- per camp | @ Rs 12,000/- per camp. District no of camps planned: - Aizawl E -3 - Aizawl W – 2 - Champhai – 2 - Kolasib - 2 - Lawngtlai - 2 - Lunglei -2 - Mamit - 2 - Saiha - 2 - Serchhip - 2 |
| 3.4 | Number of NSV camps in districts. | NR | - | - | - | - | - | - |
| 3.5 | Compensation for sterilisation (female) | NR | 4500 | 1161 |  | 4750 | 47.5 | - |
| 3.6 | Compensation for sterilisation NSV (male) | NR | 10 | 1 | - | 15 | 0.23 | - |
| 3.7 | Additional mobility support to surgeon’s team (if required) | NR | 10 teams | - | - | 10 trips | 3.00 | @ Rs 30,000/- per trip ( It has been budgeted as per local logistic travel arrangement). These will be taken up in 4th qtr. |
| 3.8 | Accreditation of private centres/ NGOs for sterilization services (number accredited) | 3 | 1 | 3 | 3 | - | - | 1 Private Centre i.e B.N.Hospital in Aizawl was accredited in 2012-13. But no expenditure was incurred. |
| 3.9 | Plan for post partum sterilisation | NR |  |  |  |  |  | - |
| 4 | Placement of counsellors at high case load facilities | 2 | 8 | 0 | - | 21 | 26.46 @ Rs 10,000/- per month ( including incentive for 3 counsellors working in difficult area @Rs.1,500/- and 2 counsellors working in very difficult area @ Rs.3,000/- per month) | Budget under Human Resources. |
| 5 | Social marketing of contraceptives | NR | - | - | - | - | - | - |
| 6 | FAMILY PLANNING TRAINING |  |  |  |  |  |  |  |
| 6.1 | IUCD 380 A Insertion training |  |  |  |  |  |  |  |
| 6.1.1 | TOT for IUCD 380 A insertion | State TOT-3 District TOT-24 | - | - | - | 18 (1 batch) | 1.67 @ Rs.1,67,300/- per batch | Many District trainers have been transferred and posted somewhere other than their respective districts at the time of their TOT. Hence fresh TOTs are required. |
| 6.1.2 | Training of Medical officers in IUCD 380 A insertion | 83 | - | - | - | 90 ( 9 batches @ 10 per batch ) | 2.75 @ Rs.30,600 per batch | - |
| 6.1.3 | Training of staff nurses in IUCD 380 A insertion | 37 | - | - | - | 140 (14 batches @ 10 per batch) | 5.25 @ 37,500 per batch |  |
| 6.1.4 | Training of ANMs / LHVs in IUCD 380 A insertion | 607 | 50 | 47 | - | 30 (3 batches @ 10 per batch)) | 1.13 @ 37,500 per batch |  |
| 6.1.5 | Refresher training in IUCD 380 A | - | - | - | - | 600 (60 batches @ 10 per batch) | 15.54 @ 25,900 per batch | Refresher training in IUCD 380-A is for 2 days to be followed by 1 day of training in Cu 375 |
| 6.2 | PPIUCD training |  |  |  |  |  |  |  |
| 6.2.1 | TOT for PPIUCD insertion | - | - | - | - | 2 (1 batch) | 1.50 @ Rs.1,5,000/- per batch | - |
| 6.2.2 | Training of Medical officers in PPIUCD insertion | - | - | - | - | 90 (18 batches @ 5 per batch) | 5.18@ 28,800 per batch | Duration of training is 3 days |
| 6.2.3 | Training of staff nurses in PPIUCD insertion | - | - | - | - | 50 (10 batches @ 5 per batch) | 1.71@ 17,100 per batch | Duration of training is 3 days |
| 6.3 | Cu IUCD 375 Insertion training |  |  |  |  |  |  |  |
| 6.3.1 | TOT for Cu IUCD 375 insertion | - | - | - | - | 3 | 2.00 | Cu 380 training + Cu 375 training |
| 6.3.2 | Training of Medical officers in Cu IUCD 375 insertion | - | - | - | - | 90 ( 9 batches @ 10 per batch ) | 1.38@ 15,300 per batch | Training of Cu IUCD 375 is for 1 day to be clubbed with Cu 380 A Training (fresh as well as refresher training) |
| 6.3.3 | Training of staff nurses in Cu IUCD 375 insertion | - | - | - | - | 140 (14 batches @ 10 per batch) | 1.74@ 12,400 per batch |  |
| 6.3.4 | Training of ANMs / LHVs in Cu IUCD 375 insertion | - | - | - | - | 630(63 batches @ 10 per batch) | 7.81@ 12,400 per batch |  |
| 6.4 | Laparoscopic Sterilisation Training |  |  |  |  |  |  |  |
| 6.4.1 | TOT on laparoscopic sterilisation | - | - | - | - | - | - | - |
| 6.4.2 | Laparoscopic sterilisation training for service providers (gynaecologists /surgeons) | 4 | 1 team | 0 | - | 1 team | 0.44 | - |
| 6.4.3 | Refresher training (if required) | - | - |  | - | - | - | - |
| 6.5 | Minilap Training for MOs/ MBBS |  |  |  |  |  |  |  |
| 6.5.1 | TOT on Minilap | - | - | - | - | - | - | - |
| 6.5.2 | Minilap training for service providers (medical officers) | 83 | 10 | 4 | - | 4 (2 batches) | 0.92 | - |
| 6.5.3 | Refresher training (if required) | - | - | - | - | 16 (8 batches) | 3.68 | - |
| 6.6 | Non-Scalpel Vasectomy (NSV) Training |  |  |  |  |  |  |  |
| 6.6.1 | TOT on NSV | - | - | - | - | - | - | - |
| 6.6.2 | NSV training for medical officers | - | - | - | - | - | - | - |
| 6.6.3 | Refresher training (if required) | - | - | - | - | - | - | - |
| 6.7 | No. of Contraceptive Update trainings for health providers in the districts | - | - | - |  | HW -1200, SN- 105 | 16.85 1.40 | @70,200 per batch for SN and ANM |
| 6.8 | Other family planning trainings RMNCH Counsellor Training | - | - | - | - | 19 (1 batch) | 1.00 | - |
| 7 | ‘World Population Day’ celebration (such as mobility, IEC activities etc.): funds earmarked for district and block level activities. | NR | State, Districts & PHC/CHC | Observed at State and all districts | - | To be observed at State and District levels | 10.00 | - |
| 8 | BCC/ IEC activities – Campaigns/ melas / print/ audio/ video materials for family planning | NR | - | - | - | - | 23.00 | Please refer IEC Annexure |
| 9 | PROCUREMENT of DRUGS/MATERIALS |  |  |  |  |  |  |  |
| 9.1 | NSV Kits | - | - | - | - | 8 | 0.32(@Rs.4000/- per Kit) | For 8 DH |
| 9.2 | IUCD insertion Kits | - | - | - | - | 64 | 3.20 ( @ Rs 5000/-) | For delivery points SDH, CHC, PHC & SC |
| 9.3 | PPIUCD (Kelly’s) forceps | - | - | - | - | 30 | 0.21 (@ Rs.700/-) | For all DHs |
| 9.4 | Minilap Set | - | 41 | - | - | 33 | 0.83 (@ Rs 2,500/- per set) | For all delivery points except Sub Centre |
| 9.5 | Procurement/ repair of laparoscopes | - | 8 | 0 | - | 2 | 14.00 @ Rs.7,00,000/- | As per last year approval, procurement of 8 laparoscopes is under process and expected to during February, 2012-13. All these laparoscopes will be placed in all district Hospitals. In addition to these 2 more are required for Civil Hospital Aizawl for use while conducting Sterilization Camps. |
| 9.6 | Laparotomy set | - | - | - | - |  |  |  |
| 9.7 | Condoms |  |  |  |  | 2,50,000 pcs |  | 2% is calculated as condom users out of eligible couples .( Expected from GOI in kind) |
| 9.8 | Copper T (375) |  |  |  |  | 2500 pcs |  | Based on target |
|  | Copper T (380) |  |  |  |  | 2500 pcs |  |  |
| 9.9 | Oral contraceptive Pills |  |  |  |  | 55000 cycles |  | 4% is calculated as OCP users out of eligible couples. .( GOI will going to supply) |
| 10 | Strengthening of programme management structures | NR | - | - | - | - | - | - |
| 11 | Performance based rewards to institutions and providers for FP performance at state and district level | NR | Planned for service providers, institutions, districts |  |  |  | 8.00 | Please refer explanation below this table. |
| 12 | PROMOTIONAL SCHEMES |  |  |  |  |  |  |  |
| 12.1 | Delivery of contraceptives by ASHA at door step | NR | - | - | - | 1 batch | 2.00 | One day orientation for programme Officials such as CMO, SMO, DPM etc ( No of estimated participants – 70 persons). ASHA may be oriented during Module training under the budget head of ASHA) |
| 12.2 | Scheme of “utilising services of ASHAs for delaying first child birth after marriage and have 3 year’s spacing between 1st and 2nd child” | NR | - | - | 1. ensuring spacing of 2 yrs after marriage | 200 Cases | 1.00 @Rs 500/ case | - |
|  |  |  |  |  | 2. Ensuring spacing of 3 yrs after birth of 1st child | 1000 Cases | 5.00 @ Rs 500/- per case | - |
|  |  |  |  |  | 3. opts for permanent limiting method after 2 children | 200 Cases | 2.00 @ Rs 1000/- per case | - |
| 13 | Other activities | NR |  |  |  |  |  |  |
|  | Awareness campaign on IUCD | - | - | - | - | - | - | - |
|  | Monitoring on IUCD | - | - | - | - | - | - | - |

PERFORMANCE BASE REWARD

Performance Based Reward has been implemented in the State since 2011-12. It is proposed to continue this team to service providers, Institution wise and District wise. Performance based criteria will be made available for all Family Planning Services such as Spacing and limiting method, Utilization of train providers etc. Achievable target will be made and the reward will be disbursed as follows:-

- Reward to Services providers to be disbursed at District Level:

1st Prize		-	Rs. 8,000/-

2nd Prize	-	Rs. 6,000/-

3rd Prize	-	Rs. 5,000/-

Total	-	Rs. 19,000/-

Total for 9 Districts	-	Rs. 19000/- X 9 = Rs. 1, 71,000/-

- Reward to Institution i.e SDH/CHC/PHC to be disbursed at District Level:

1st Prize		-	Rs. 12,000/-

2nd Prize	-	Rs. 9,000/-

3rd Prize	-	Rs. 6,000/-

Total	-	Rs. 27,000/-

Total for 9 Districts	-	Rs. 27,000/- X 9 = Rs. 2, 43,000/-

- Reward to SC Level to be disbursed at District Level:

1st Prize		-	Rs. 8,000/-

2nd Prize	-	Rs. 7,000/-

3rd Prize	-	Rs. 6,000/-

Total	-	Rs. 21,000/-

Total for 9 Districts	-	Rs. 21,000/- X 9 = Rs. 1, 89,000/-

- Reward to District Level:

1st Prize		-	Rs. 87,000/-

2nd Prize	-	Rs. 60,000/-

3rd Prize	-	Rs. 50,000/-

Total	-	Rs. 1,97,000/-

Grand Total	-	Rs. 8, 00,000/-

FAMILY PLANNING INDEMNITY SCHEME:

Family planning Insurance Scheme has been implemented in the State with ICICI Lombard General Insurance Company Limited since 29th November, 2005. As per instruction issued by GoI vide No. N-23011/68/2011 (Policy)(Pt) Date: 13th February, 2013, the implementation of this Scheme w.e.f 01.04.2013 is to be done through State PIP under National Rural Health Mission and the scheme may be renamed ‘Family Planning Indemnity Scheme’. Budget has to be calculated as per tentative allocation made by GoI /as per prescribed parameters for Budget calculation. As per GoI letter, an amount to the extent of Rs. 5, 00,000/- may be proposed for the State of Mizoram

However, It may be noted in this connection that as per state record during the last 3 years, 81 Claims had been submitted to ICICI Lombard General Insurance Company Limited. Out of which 69 Claims were settled and the amount settled was Rs. 20, 70,000/- that means the average amount of Rs. 6, 90,000/- was settled per year. Therefore, ir has considered that Rs. 7, 00,000/- is appropriate budget for Mizoram in 2013-14.