Background Information Required for Approval of State PIPs for 2013-14

Infrastructure- Annexure –I

OVERALLINFRASTRUCTURE

| Name of the district | Population (Census 2011) | DH |  |  |  |  | FRU / CHC |  |  |  |  | PHC |  |  |  |  | SC |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Required | Existing | Under construction | Short fall | No. proposed in PIP 2013-14 | Required | Existing | Under construction | Short fall | No. proposed in PIP 2013-14 | Required | Existing | Under construction | Short fall | No. proposed in PIP 2013-14 | Required | Existing | Under construction | Short fall | No. proposed in PIP 2013-14 |
| Aizawl East | 233978 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 6 | 1 PHC type –II qrt | 0 | Re-construction of 1 PHC bldg.(Darlawn PHC) | Re-construction of 1 SC + 3 SC Qrt. | 54 | Re-construction of 1 SC bldg + 3 SC qrt | 0 | Re-construction of 1 SC bldg. + 3 SC Qrt. |
| Aizawl West | 170076 | 0 | 1 | Bldg. Upgradation. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | Re-construction of 5 SC | 40 | Re-construction of 1 SC + 3 SC qrt | 0 | Re-construction of 5 SC |
| Kolasib | 83054 | Re-construction of Dist. Adm.Bld DPMSU, Kolasib | 1 | 0 | 0 | Re-construction of Dist. Adm.Bld DPMSU, Kolasib | 0 | 1 | 0 | 0 | 0 | Re-construction of 2 PHC bldg. | 5 | 0 | 0 | Re-construction of 2 PHC bldg | Re-construction of 5 SC bldg | 29 | Re-construction of 8 SC+ 2 SC qrt | 0 | Re-construction of 5 SC bldg |
| Champhai | 125370 | Re-construction of Dist. Adm.Bld DPMSU, Champhai | 1 | 1 DH Main bldg. |  | Dist. Adm.Bld DPMSU, Champhai | Upgradation of CHC to SDH ( Khawzawl) | 2 | 0 | 0 | Upgradation of CHC to SDH ( Khawzawl) | Re-construction of 1 PHC(Rabung PHC) | 11 | 0 | 0 | Re-construction of 1 PHC(Rabung PHC) | Re-construction 3 SC + 1 SC qrt | 59 | Re-construction of 19 SC+ 3 SC qrt | 0 | Re-construction 3 SC + 1 SC qrt |
| Serchhip | 64875 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Re-construction of 2 PHC qrt | 5 | Re-construction of 1 PHC + 1 PHC qrt |  | Re-construction of 2 PHC qrt | 0 | 26 | Re-construction of 8 SC Bldg | 0 | 0 |
| Lunglei | 154094 | 0 | 1 | 0 | 0 | 0 | Upgradation of CHC to SDH ( Hnahthial) | 1 | 0 | 0 | Upgradation of CHC to SDH ( Hnahthial) | Re-construction of 1 PHC + New2 RCC tank + 5 Type Qtr | 9 | Re-construction of 2 PHC qrt | 0 | Re-construction of 1 PHC + New2 RCC tank + 5 Type Qtr | 0 | 71 | 0 | 0 | 0 |
| Mamit | 85737 | Re-construction of I type IIQrt | 1 | 0 | 0 | Re-construction of I type IIQrt | Re-construction of 1 Type III Qrt + reno. Of Qrt | 1 | 0 | 0 | Re-construction of 1 Type III Qrt + reno. Of Qrt | Re-construction of 8 PHC qrt+ 2 Kitchen + Renovation of 2 PHC | 7 | 0 | 0 | Re-construction of 8 PHC qrt+ 2 Kitchen + Renovation of 2 PHC | Re-construction of 1 SC + 6 SC qrt | 30 | Re-construction of 5 SC | 0 | Re-construction of 1 SC + 6 SC qrt |
| Lawngtlai | 117444 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Reconstruction of 3 PHC Type II qrt | 5 | 0 | 0 | Reconstruction of 3 PHC qrt | Reconstruction of 3 SC + 3 SC qrt | 37 | 0 | 0 | Reconstruction of 3 SC + 3 SC qrt |
| Saiha | 56368 | Reconstruction of 1each of Type II & III Qrt | 1 | 0 | 0 | Reconstruction of 1Type II & III Qrt | 0 | 0 | 0 | 0 | 0 | Reconstruction of 1 PHC ( Tuipang) | 4 | 0 | 0 | Reconstruction 1 PHC (Tuipang) | Reconstruction of 4 SC | 24 | Reconstruction of 2SC | 0 | Reconstruction of 4 SC |
| State total | 1091014 | Reconstruction of 2 Adm.Bld + 2 Type II Qtr & 1 Type III Qtr | 8 | 2 DH ( Aizawl ‘W’ & Champhai) | 0 | Reconstruction of 2 Adm.Bld + 2 Type II Qtr & 1 Type III Qtr | 2 Bldg const for upgradation of CHC to SDH + Type III Qtr + Renovation 1 | 9 | 0 | 0 | 2 Bldg const for upgradation of CHC to SDH + Type III Qtr + Renovation 1 | Reconstruction of 6 PHC + 2 Kitchen+ 18 PHC qrt+ Renovation of 2 PHC +2 RCC Tank | 57 | Reconstruction of 1 PHC + 4 PHC qrt | 0 | Reconstruction of 6 PHC + 2 Kitchen+ 18 PHC qrt+ Renovation of 2 PHC +2 RCC Tank | Reconstruction of 23 SC+ 13 SC qrt + renovation of 2 SC qrt | 370 | Reconstruction of 44 SC + 11 SC qrt | 0 | Reconstruction of 23 SC+ 13 SC qrt + renovation of 2 SC qrt |
| HF total | 259456 | Reconstruction of 2Type II & 1Type III Qrt | 3 | 0 | 0 | Reconstruction of 2Type II & 1Type III Qrt | Re-construction of 1 Type III Qrt + reno. Of Qrt | 2 | 0 | 0 | Re-construction of 1 Type III Qrt + reno. Of Qrt | Reconstruction of 1 PHC Bldg+ 2 Kitchen+ 11 PHC qrt+ Renovation of 2 PHC | 16 | 0 | 0 | Reconstruction of 1 PHC Bldg+ 2 Kitchen+ 11 PHC qrt+ Renovation of 2 PHC | Reconstruction of 8 SC + 9 SC qrt | 91 | Reconstruction of 7 SC | 0 | Reconstruction of 8 SC + 9 SC qrt |

F.M.R. Code- B 4 & 5: infrastructure

Infrastructure- Annexure –II

New Constructions – I - (To include Absolutely New Constructions only)

| Name of the District | Type and Name of the Facility | No. of Beds Proposed | Population to be covered by the facility | Timeline for completion | Total Project cost (Rs. In lakhs) | Total funds proposed for 2013-14 (Rs. In lakhs) | Justification for Facility |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Common Justification: Mizoram is hilly terrain characterized by spare, small and hamlet villages. Transport and communication facilities are also very poor. The target groups living in remote areas where there is no health facility are not getting proper health care services. Proverty and ignorance of the villagers is also another problems in service delivery. A number of villagers do not afford to access health facility on time. Hence it can be said that population criteria for the establishment of Health Centre is not suitale in Mizoram. Therefore establishment of new 10 Sub Centre has been proposed as tabulated below. |  |  |  |  |  |  |  |
| Lunglei | Khojoisuri | Nil | 863 | 2013-14 | 6.78 | 6.78 | The distance of the nearest SC from this village is 25km. There is no proper road connection |
|  | Malsuri | Nil | 886 | 2013-14 | 6.78 | 6.78 | Motorable road connects this village during dry seassion. But not during monsoon season due to frequent landslide. The nearest health Centre from this village is 30km. |
| Lawngtlai | Parva | Nil | 704 | 2013-14 | 7.31 | 7.31 | This village is covered by Parva SHC. Under Parva SHC there are five villages. It is difficult for ANM to cover during Immunization Session. |
|  | Mandirasora | Nil | 506 | Nil | 7.31 | 7.31 | Some of this illage dwellers are still following their traditional health care system. There is Health Centre 30 km away from this place. |
| Saiha | Longmasu |  | 389 | 2013-2014 | 7.46 | 7.46 | Longmasu village is connected only by foothpath road. |
|  | Chheihlu |  | 432 | 2013-2014 | 7.46 | 7.46 | Chheihlu is one of the most backward villages in Saiha District. Most of the target group do not afford to access even the nearest health facility situated 20 km away. |
| Mamit | Marpara North |  | 1552 | 2013-2014 | 6.38 | 6.38 | In order to get health care service, the villagers will have to go 19km on footpath road |
|  | Sihthiang |  | 191 | 2013 | 6.38 | 6.38 | In order to reach the nearest Health Centre, the pregnant women have to go the hill steep of 17 km. |
|  | Serhmun |  | 611 | 2013 | 6.38 | 6.38 | Kawrthethawveng PHC is the nearest Health Centre from this village which is situated at around 30km away. |
|  | Phulpui |  | 984 | 2013 | 6.38 | 6.38 | The distance between Phulpui and the nearest SC is 19 km. |

PROPOSED NEW CONSTRUCTION FOR 10 SUBCENTRE IN HIGH FOCUS DISTRICTS

| Sl.No | District | Name of Village | Estimated Amount ( Rs.In lakhs) |
| --- | --- | --- | --- |
| 1. | Lunglei | 1) Khojoisury | 6.78 |
|  |  | 2) Malusury | 6.78 |
| 2. | Lawngtlai | 3) Parva II | 7.31 |
|  |  | 4) Mandirasora | 7.31 |
| 3. | Saiha | 5) Langmasu | 7.46 |
|  |  | 6) Chheihlu | 7.46 |
| 4. | Mamit | 7) Marpara South | 6.38 |
|  |  | 8) Sihthiang | 6.38 |
|  |  | 9) Serhmun | 6.38 |
|  |  | 10) Phulpui | 6.38 |
|  | Total |  | 68.62 |

LUNGLEI DISTRICT

| Sl.No. |  | TYPE OF WORKS | NO. | AMOUNT(Rs) | TOTAL AMOUNT(Rs) |
| --- | --- | --- | --- | --- | --- |
| A |  | CONSTRUCTION OF SUB CENTRE |  |  |  |
|  | 1 | Khojoisuri | 1 |  |  |
|  | 2 | Malsuri | 1 |  |  |
|  |  | a) Civil Works including Cost Index 2011 @ 39.88% of MPWD SOR 2007 for Lunglei Division |  | Rs. 572,936.00 |  |
|  |  | b) Water Supply & Sanitary Installation @ 7.5% |  | Rs. 42,970.20 |  |
|  |  | c) Electrification @ 8.5% |  | Rs. 48,699.56 |  |
|  |  | Sub Total |  | Rs. 664,605.76 |  |
|  |  | d) Quality control & Monitoring @ 1% |  | Rs. 6,646.06 |  |
|  |  | e) Contingency & Administrative Charges @ 1% |  | Rs. 6,646.06 |  |
|  |  | G.Total |  | Rs. 677,897.88 |  |
|  |  | Say |  | Rs. 678,000.00 |  |
|  |  | No.of Sub Centre Building | 2 | Rs.1,356,000.00 | Rs 1,356,000.00 |

LAWNGTLAI DISTRICT

| Sl.No. |  | TYPE OF WORKS | NO. | AMOUNT(Rs) | TOTAL AMOUNT(Rs) |
| --- | --- | --- | --- | --- | --- |
| B |  | CONSTRUCTION OF SUB CENTRE |  |  |  |
|  | 1 | Parva | 1 |  |  |
|  | 2 | Mandirasora | 1 |  |  |
|  |  | a) Civil Works including Cost Index 2011 @ 50.78% of MPWD SOR 2007 for Lawngtlai Division |  | Rs. 617,581.00 |  |
|  |  | b) Water Supply & Sanitary Installation @ 7.5% |  | Rs. 46,318.58 |  |
|  |  | c) Electrification @ 8.5% |  | Rs. 52,494.39 |  |
|  |  | Sub Total |  | Rs. 716,393.96 |  |
|  |  | d) Quality control & Monitoring @ 1% |  | Rs. 7,163.94 |  |
|  |  | e) Contingency & Administrative Charges @ 1% |  | Rs. 7,163.94 |  |
|  |  | G.Total |  | Rs. 730,721.84 |  |
|  |  | Say |  | Rs. 731,000.00 |  |
|  |  | No.of Sub Centre Building | 2 | Rs.1,462,000.00 | Rs 1,462,000.00 |

SAIHA

| Sl.No. |  | TYPE OF WORKS | NO. | AMOUNT(Rs) | TOTAL AMOUNT(Rs) |
| --- | --- | --- | --- | --- | --- |
| C |  | CONSTRUCTION OF SUB CENTRE |  |  |  |
|  | 1 | Longmasu | 1 |  |  |
|  | 2 | Chheihlu | 1 |  |  |
|  |  | a) Civil Works including Cost Index 2011 @ 50.78% of MPWD SOR 2007 for Lawngtlai Division |  | Rs. 630,565.00 |  |
|  |  | b) Water Supply & Sanitary Installation @ 7.5% |  | Rs. 47,292.38 |  |
|  |  | c) Electrification @ 8.5% |  | Rs. 53,598.03 |  |
|  |  | Sub Total |  | Rs. 731,455.40 |  |
|  |  | d) Quality control & Monitoring @ 1% |  | Rs. 7,314.55 |  |
|  |  | e) Contingency & Administrative Charges @ 1% |  | Rs. 7,314.55 |  |
|  |  | G.Total |  | Rs. 746,084.51 |  |
|  |  | Say |  | Rs. 746,000.00 |  |
|  |  | No.of Sub Centre Building | 2 | Rs.1,492,000.00 | Rs 1,492,000.00 |

MAMIT DISTRICT

|  | Sub-Centre | no. | Amount | Total Amount |
| --- | --- | --- | --- | --- |
| 1 | Marpara North | 1 |  |  |
| 2 | Sihthiang | 1 |  |  |
| 3 | Serhmun | 1 |  |  |
| 4 | Phulpui | 1 |  |  |
|  | a) Civil Works including Cost Index 2011 @ 24.29% of MPWD SOR 2007 for Mamit Division |  | Rs.523,989.56 |  |
|  | b) Water Supply & Sanitary Installation @ 7.5% |  | Rs. 39,299.22 |  |
|  | c) Electrification @ 8.5% |  | Rs. 44,539.12 |  |
|  | d) Quality control & Monitoring @ 2% |  | Rs. 12,156.56 |  |
|  | e) Contingency & Administrative Charges @ 3% |  | Rs. 18,234.84 |  |
|  | Total | 4 | Rs.638,219.28 |  |
|  | Say |  | Rs.638,000.00 | Rs 2,552,000.00 |

CONSOLIDATED ESTIMATED BUDGET FOR STRENGTHENING/ UPGRADATION OF SUB CENTRE DELIVERY POINTS IN HIGH FOCUS DISTRICTS

| Sl.No | District | Name of Villages | Estimated Amount (Rs) |
| --- | --- | --- | --- |
| 1 | Mamit | Tuipuibari | 6,18,000/- |
|  |  | Hriphaw | 6,18,000/- |
| 2 | Lunglei | Zawlpui | 10,41,000/- |
|  |  | Changpui | 10,41,000/- |
|  |  | Thenhlum | 10,41,000/- |
| 3 | Lawngtlai | Vathuampui | 11,22,000/- |
|  |  | Lungtian | 11,22,000/- |
|  |  | Paithar | 11,22,000/- |
| 4 | Saiha | Chakhang | 7,64,000/- |
|  |  | Zawngling | 7,64,000/- |
|  |  |  | 92,53,000/- |

|  |  | MAMIT DISTRICT |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Sl.No. |  | TYPE OF WORKS | NO. | AMOUNT(Rs) | TOTAL AMOUNT(Rs) |
| A |  | UPGRADATION OF SUB HEALTH CENTRE |  |  |  |
|  | 1 | Tuipuibari | 1 |  |  |
|  | 2 | Hriphaw | 1 |  |  |
|  |  | a) Civil Works including Cost Index 2011 @ 39.88% of MPWD SOR 2007 for Lunglei Division |  | Rs.260,815.00 |  |
|  |  | b) Water Supply & Sanitary Installation @ 7.5% |  | Rs.19,561.13 |  |
|  |  | c) Electrification @ 8.5% |  | Rs.22,169.28 |  |
|  |  | Sub Total |  | Rs.302,545.40 |  |
|  |  | d) Quality control & Monitoring @ 1% |  | Rs. 3,025.45 |  |
|  |  | e) Contingency & Administrative Charges @ 1% |  | Rs. 3,025.45 |  |
|  |  | G.Total |  | Rs. 308,596.31 |  |
|  |  | Say |  | Rs. 309,000.00 |  |
|  |  | No.of Sub Health Centre Building | 2 | Rs. 618,000.00 | 618,000.00 |

|  |  | LUNGLEI DISTRICT |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Sl.No. |  | TYPE OF WORKS | NO. | AMOUNT(Rs) | TOTAL AMOUNT(Rs) |
| B |  | UPGRADATION OF SUB HEALTH CENTRE |  |  |  |
|  | 1 | Zawlpui | 1 |  |  |
|  | 2 | Changpui | 1 |  |  |
|  | 3 | Thenhlum | 1 |  |  |
|  |  | a) Civil Works including Cost Index 2011 @ 39.88% of MPWD SOR 2007 for Lunglei Division |  | Rs. 293,530.00 |  |
|  |  | b) Water Supply & Sanitary Installation @ 7.5% |  | Rs. 22,014.75 |  |
|  |  | c) Electrification @ 8.5% |  | Rs. 24,950.05 |  |
|  |  | Sub Total |  | Rs. 340,494.80 |  |
|  |  | d) Quality control & Monitoring @ 1% |  | Rs. 3,404.95 |  |
|  |  | e) Contingency & Administrative Charges @ 1% |  | Rs. 3,404.95 |  |
|  |  | G.Total |  | Rs. 347,304.70 |  |
|  |  | Say |  | Rs. 347,000.00 |  |
|  |  | No.of Sub Health Centre Building | 3 | Rs.1,041,000.00 | Rs 1,041,000.00 |
|  |  | LAWNGTLAI DISTRICT |  |  |  |
| Sl.No. |  | TYPE OF WORKS | NO. | AMOUNT(Rs) | TOTAL AMOUNT(Rs) |
| C |  | UPGRADATION OF SUB HEALTH CENTRE |  |  |  |
|  | 1 | Vathuampui | 1 |  |  |
|  | 2 | Lungtian | 1 |  |  |
|  | 3 | Paithar | 1 |  |  |
|  |  | a) Civil Works including Cost Index 2011 @ 50.78% of MPWD SOR 2007 for Lawngtlai Division |  | Rs. 316,403.00 |  |
|  |  | b) Water Supply & Sanitary Installation @ 7.5% |  | Rs. 23,730.23 |  |
|  |  | c) Electrification @ 8.5% |  | Rs. 26,894.26 |  |
|  |  | Sub Total |  | Rs. 367,027.48 |  |
|  |  | d) Quality control & Monitoring @ 1% |  | Rs. 3,670.27 |  |
|  |  | e) Contingency & Administrative Charges @ 1% |  | Rs. 3,670.27 |  |
|  |  | G.Total |  | Rs. 374,368.03 |  |
|  |  | Say |  | Rs. 374,000.00 |  |
|  |  | No.of Sub Health Centre Building | 3 | Rs.1,122,000.00 | Rs 1,122,000.00 |
|  |  | SAIHA DISTRICT |  |  |  |
| Sl.No. |  | TYPE OF WORKS | NO. | AMOUNT(Rs) | TOTAL AMOUNT(Rs) |
| D |  | UPGRADATION OF SUB HEALTH CENTRE |  |  |  |
|  | 1 | Chakhang | 1 |  |  |
|  | 2 | Zawngling | 1 |  |  |
|  |  | a) Civil Works including Cost Index 2011 @ 50.78% of MPWD SOR 2007 for Lawngtlai Division |  | Rs. 323,055.00 |  |
|  |  | b) Water Supply & Sanitary Installation @ 7.5% |  | Rs. 24,229.13 |  |
|  |  | c) Electrification @ 8.5% |  | Rs. 27,459.68 |  |
|  |  | Sub Total |  | Rs. 374,743.80 |  |
|  |  | d) Quality control & Monitoring @ 1% |  | Rs. 3,747.44 |  |
|  |  | e) Contingency & Administrative Charges @ 1% |  | Rs. 3,747.44 |  |
|  |  | G.Total |  | Rs. 382,238.68 |  |
|  |  | Say |  | Rs. 382,000.00 |  |
|  |  | No.of Sub Health Centre Building | 2 | Rs. 764,000.00 | Rs 764,000.00 |

Infrastructure- Annexure -III

New Constructions II – (Rented to own Building/ Additional Building/ Major upgradation/ MCH Wings)

Note: Kindly note that proposed Reconstructions / Constructions are indicated in the column ‘ Any additional infrastructure’

Calculation of Bed Occupancy Rate = Total in patient Service days for a period / Total no of days in authorized bed * 100

| Name of the District | Type and Name of the Facility | Population covered by the facility | No. of existing bed | No. of additional bed proposed | Any additional infrastructure proposed | OPD/month (average since April 2012) | IPD/month (average since April 2012) | Normal Deliveries per month (average since April 2012) | C-section per month (average since April 2012) | Bed occupancy per month (average since April 2012) | Timeline for completion | Total Project cost (Rs. In lakhs) | Total funds proposed for 2013-14 (Rs. In lakhs) | Justific ation |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| MAMIT | Mamit DH | 85737 | 50 | 0 | Type II | 1388 | 190 | 30 | 6 | 76 | 2014 | 8.69 | 8.69 | The existing quarters are very old & in bad condition and need to be re-construction/major upgradation |
| MAMIT | Kawrthah CHC | 5058 | 30 |  | Type III Qrt | 506 | 75 | 10 | 0 | 33 | 2014 | 14.76 | 14.76 |  |
| LUNGLEI | Hnahthial CHC | 15640 | 30 |  | Upgradation of CHC | 1554 | 80 | 16 | 0 | 44 | 2014 | 195.86 | 195.86 | CHC to be upgraded to Sub-District Hospital |
| MAMIT | W.Phaileng PHC | 17570 | 10 | 2 | Type III | 583 | 65 | 10 | 0 | 65 | 2014 | 14.76 | 14.76 | The existing quarter are very old and need to be re-construction/major upgradation |
| MAMIT | Zawlnuam PHC | 7261 | 10 |  | Type III | 515 | 41 | 7 | 0 | 54 | 2014 | 14.76 | 14.76 |  |
| SERCHHIP | North Vanlaiphai PHC | 6438 | 14 |  | Type III | 501 | 50 | 6 | 0 | 66 | 2014 | 14.75 | 14.75 |  |
| MAMIT | Phuldungsei PHC | 4417 | 10 |  | Type II | 108 | 20 | 4 | 0 | 26 | 2014 | 8.69 | 8.69 |  |
| MAMIT | Kawrtethawveng PHC | 3980 | 10 |  | Type II | 364 | 40 | 11 | 0 | 53 | 2014 | 8.69 | 8.69 |  |
| MAMIT | Kanhmun PHC | 4805 | 10 |  | Type II | NA | NA | 0 | 0 | NA | 2014 | 8.69 | 8.69 |  |
| MAMIT | Rawpuichhip PHC | 3648 | 8 |  | Type II | 477 | 30 | 4 | 0 | 40 | 2014 | 8.69 | 8.69 |  |
| SERCHHIP | Chhingchhip PHC | 7481 | 10 |  | Type II | 287 | 43 | 5 | 0 | 57 | 2014 | 8.68 | 8.68 |  |
| LAWNGTLAI | Sangau PHC | 5012 | 10 |  | Type II | 362 | NA | 7 | 0 | NA | 2014 | 10.54 | 10.54 |  |
| LAWNGTLAI | Bualpui PHC | 2226 | 10 |  | type II | 60 | NA | 2 | 0 | NA | 2014 | 10.54 | 10.54 |  |
| LAWNGTLAI | Lungpher PHC | 4815 | 10 |  | Type II | 201 | 16 | 4 | 0 | 21 | 2014 | 10.54 | 10.54 |  |
| LUNGLEI | Bunghmun PHC | 4116 | 10 |  | PHC Type II | 102 | NA | 2 | 0 | NA | 2014 | 9.78 | 9.78 |  |
| LUNGLEI | Buarpui PHC | 5022 | 10 |  | Type II Qrt | 345 | 23 | 6 | 0 | 31 | 2014 | 9.78 | 9.78 |  |
| LUNGLEI | Pangzawl PHC | 3644 | 10 |  | Type II Qrt | 320 | NA | 4 | 0 | NA | 2014 | 9.78 | 9.78 |  |
| LUNGLEI | Cherhlun PHC | 3152 | 10 |  | Type II Qrt | 329 | NA | 5 | 0 | NA | 2014 | 9.78 | 9.78 |  |
| LUNGLEI | South Vanlaiphai PHC | 5025 | 10 |  | Type II Qrt | 232 | 10 | 4 | 0 | 13 | 2014 | 9.78 | 9.78 |  |
| MAMIT | Marpara PHC | 8221 | 10 |  | Type I | 335 | 52 | 6 | 0 | 69 | 2014 | 6.39 | 6.39 |  |
| MAMIT | Rawpuichhip PHC | 3648 | 8 |  | Type I | 477 | 30 | 5 | 0 | 40 | 2014 | 6.39 | 6.39 |  |
| MAMIT | Kanhmun PHC | 4805 | 10 |  | Kitchen | 0 | 0 | 0 | 0 |  | 2014 | 4.28 | 4.28 | There are no separate room for kitchen in these two PHCs..so, separate kitchen need to be constructed |
| MAMIT | Rawpuichhip PHC | 3648 | 8 |  | Kitchen | 477 | 30 | 3 | 0 | 40 | 2014 | 4.28 | 4.28 |  |
| MAMIT | Zawlnuam SC | 7261 |  |  | Bldg | 180 | 0 | 0 | 0 |  | 2014 | 6.38 | 6.38 | The existing SC bldg are very old and in bad condition and need to be reconstructed. |
| SAIHA | Phura SC | 3501 |  |  | Bldg | 209 | 0 | 3 | 0 |  | 2014 | 7.88 | 7.88 |  |
| SAIHA | Lawngban SC | 1205 |  |  | Bldg | 259 | 0 | 3 | 0 |  | 2014 | 7.88 | 7.88 |  |
| SAIHA | Latawh SC | 926 |  |  | Bldg | 153 | 0 | 2 | 0 |  | 2014 | 7.88 | 7.88 |  |
| SAIHA | Mohre SC | 820 |  |  | Bldg | 23 |  | 0 |  |  |  | 7.88 | 7.88 |  |
| SAIHA | Saiha DH | 56368 |  |  | Type II qrt |  |  |  |  |  |  | 10.04 | 10.04 | The existing quarter are very old and need to be re-construction/major upgradation |
| SAIHA | Saiha DH | 56368 |  |  | Type III |  |  |  |  |  |  | 15.62 | 15.62 |  |
| CHAMPHAI | Mimbung SC | 2158 |  |  | Bldg | 38 | 0 | 0 | 0 |  | 2014 | 6.43 | 6.43 | The existing SC bldg are very old and in bad condition and need to be reconstructed |
| CHAMPHAI | NE Khawdungsei SC | 2318 |  |  | Bldg | 0 | 0 | 0 | 0 |  | 2014 | 6.43 | 6.43 |  |
| CHAMPHAI | Khuangphah SC | 714 |  |  | Bldg | 126 | 0 | 2 | 0 |  | 2014 | 6.43 | 6.43 |  |
| CHAMPHAI | Bungzung SC | 1986 |  |  | Bldg | 195 |  | 0 |  |  |  | 6.43 | 6.43 |  |
| CHAMPHAI | Khuangphah SC qrt | 714 |  |  | SC qrt | 126 | 0 | 2 | 0 |  | 2014 | 6.93 | 6.93 |  |
| CHAMPHAI | DPMSU, Champhai. Amisnitrative Builing |  |  |  | DPMSU, Champhai. Amisnitrative Builing |  |  |  |  |  | 2014 | 50.96 | 50.96 | Newly proposed |
| CHAMPHAI | Khawzawl CHC | 15278 | 25 |  | Upgradation of CHC to SDH | 930 | 110 | 32 | 4 | 73 | 2014 | 188.68 | 188.68 | CHC upgraded to Sub-District Hospital |
| KOLASIB | Hmar Veng SC | 967 |  |  | Bldg | 327 | 0 | 0 | 0 |  | 2014 | 5.84 | 5.84 | The existing Bldgs are very old and in bad condition and need to be reconstructed |
| KOLASIB | Park kawn SC | 832 |  |  | Bldg | 309 | 0 | 0 | 0 |  | 2014 | 5.84 | 5.84 |  |
| KOLASIB | Vairengte SC | 9741 |  |  | Bldg | 309 | 0 | 0 | 0 |  | 2014 | 5.84 | 5.84 |  |
| KOLASIB | Kawnpui SC | 8124 |  |  | Bldg | 183 | 0 | 0 | 0 |  | 2014 | 5.84 | 5.84 |  |
| KOLASIB | Bilkhawthlir SC | 2348 |  |  | Bldg | 102 | 0 | 0 | 0 |  | 2014 | 5.84 | 5.84 |  |
| KOLASIB | Lungdai PHC | 4621 | 10 |  | Bldg | 298 | 27 | 6 | 0 | 36 |  | 82.14 | 82.14 |  |
| KOLASIB | DPMSU Kolasib, Administrative Building. |  |  |  | DPMSU Kolasib, Administrative Building. |  |  |  |  |  |  | 44.43 | 44.43 |  |
| AIZAWL EAST | Tuithiang SC | 1890 |  |  | Bldg | 166 | 0 | 0 | 0 |  | 2014 | 6.26 | 6.26 |  |
| AIZAWL WEST | Vaivakawn SC | 3900 |  |  | Bldg | 329 | 0 | 0 | 0 |  | 2014 | 6.26 | 6.26 |  |
| AIZAWL WEST | Dinthar SC | 3923 |  |  | Bldg | 304 | 0 | 0 | 0 |  | 2014 | 6.26 | 6.26 |  |
| AIZAWL WEST | Hlimen SC | 1235 |  |  | Bldg | 217 | 0 | 2 | 0 |  | 2014 | 6.26 | 6.26 |  |
| AIZAWL WEST | Thiak SC | 785 |  |  | Bldg | 94 | 0 | 0 | 0 |  | 2014 | 6.26 | 6.26 |  |
| AIZAWL WEST | Hreichhuk SC | 864 |  |  | Bldg | 161 | 0 | 0 | 0 |  | 2014 | 6.26 | 6.26 |  |
| MAMIT | Rawpuichhip SC Qrt | 3648 |  |  | SC Qtr | 262 | 0 | 0 | 0 |  | 2014 | 6.85 | 6.85 |  |
| MAMIT | Parvatui SC Qrt | 723 |  |  | SC Qtr | 138 | 0 | 0 | 0 |  | 2014 | 6.85 | 6.85 |  |
| MAMIT | Tuipuibari SC Qrt | 7121 |  |  | SC Qtr | 260 | 0 | 0 | 0 |  | 2014 | 6.85 | 6.85 | The existing are very old and in bad condition and need to be reconstructed |
| MAMIT | Phuldungsei SC Qrt | 4417 |  |  | SC Qtr | 78 | 0 | 0 | 0 |  | 2014 | 6.85 | 6.85 |  |
| MAMIT | W Phaileng SC qrt | 4842 |  |  | SC Qtr | 97 | 0 | 0 | 0 |  | 2014 | 6.85 | 6.85 |  |
| MAMIT | Zawlnuam SC qrt | 4261 |  |  | SC Qtr | 195 |  |  |  |  | 2014 | 6.85 | 6.85 |  |
| CHAMPHAI | Hmunlai SC | 898 |  |  | Bldg | 31 | 0 | 0 | 0 |  | 2014 | 6.85 | 6.85 |  |
| CHAMPHAI | Khuangphah SC | 714 |  |  | Bldg | 21 | 0 | 3 | 0 |  | 2014 | 6.85 | 6.85 |  |
| AIZAWL EAST | Tualbung SC | 1010 |  |  | Bldg | 40 | 0 | 2 | 0 |  | 2014 | 6.75 | 6.75 |  |
| AIZAWL EAST | Sihfa SC | 689 |  |  | Bldg | 65 | 0 | 0 | 0 |  | 2014 | 6.75 | 6.75 |  |
| AIZAWL EAST | Sesawng SC | 3643 |  |  | Bldg | 95 | 0 | 0 | 0 |  | 2014 | 6.75 | 6.75 |  |
| LAWNGTLAI | Vathuampui SC | 2562 |  |  | Bldg | 87 |  |  |  |  |  | 7.71 | 7.71 |  |
| LAWNGTLAI | Hmunlai SC | 898 |  |  | Bldg | 31 |  |  |  |  |  | 7.71 | 7.71 |  |
| LAWNGTLAI | Lawngtlai-I SC | 6919 |  |  | Bldg | 282 |  |  |  |  |  | 7.71 | 7.71 |  |
| LAWNGTLAI | Vathuampui SC Qrt | 2562 |  |  | Qtr | 221 |  |  |  |  |  | 8.31 | 8.31 |  |
| LAWNGTLAI | Hmunlai SC Qrt | 898 |  |  | Qtr | 187 |  |  |  |  |  | 8.31 | 8.31 |  |
| LAWNGTLAI | Lawngtlai-I SC Qrt | 6919 |  |  | Qtr | 282 |  |  |  |  |  | 8.31 | 8.31 |  |
| SAIHA | Tuipang PHC | 4354 | 10 |  | Bldg | 248 | 20 | 5 | 0 | 27 | 2014 | 114.64 | 114.64 | Proposed for reconstruction to meet demand of increasing population |
| LUNGLEI | Haulawng PHC | 2156 | 10 |  | Bldg | 199 | 21 | 4 | 0 | 28 | 2014 | 104.16 | 104.16 |  |
| CHAMPHAI | Rabung PHC | 15500 | 10 |  | Bldg | 273 | 25 | 5 | 0 | 33 | 2014 | 90.37 | 90.37 |  |
| KOLASIB | Bukpui PHC | 5780 | 10 |  | Bldg | 377 | 25 | 9 | 0 | 33 | 2014 | 82.14 | 82.14 |  |
| AIZAWL EAST | Darlawn PHC | 10526 | 10 |  | Bldg | 778 | 44 | 15 | 0 | 58 | 2014 | 88.03 | 88.03 |  |
| LUNGLEI | Cherhlun PHC | 3152 | 10 |  | RCC tanky | 379 | 32 | 5 | 0 | 43 | 2014 | 6.59 | 6.59 | RCC water tank are old and need to be reconstructed. |
| LUNGLEI | Lungsen PHC | 2681 | 10 |  | RCC tanky | 591 | 14 | 6 | 0 | 19 | 2014 | 6.59 | 6.59 |  |

Infrastructure- Annexure –IV

Repair & Renovation of existing structure:

| Name of the District | Type and Name of the Facility | Population covered by the facility | No. of existing bed | No. of additional bed proposed | Any additional infrastructure proposed | OPD/month (average since April 2012) | IPD/month (average since April 2012) | Normal Deliveries per month (average since April 2012) | C-section per month (average since April 2012) | Bed occupancy per month (average since April 2012) | Timeline for completion | Total Project cost (Rs. In lakhs) | Total funds proposed for 2013-14 (Rs. In lakhs) | Justification |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| MAMIT | W. Phaileng PHC | 17570 | 10 | 2 |  | 583 | 65 | 10 | 0 | 65 | 2014 | 7.00 | 7.00 | Renovation/ Repaire is required for providing quality services |
| MAMIT | Rawpuichhip PHC | 3648 | 8 |  |  | 477 | 30 | 3 | 0 | 40 | 2014 | 7.00 | 7.00 |  |
| MAMIT | Kawrthah CHC | 5058 | 30 |  |  | 506 | 75 | 10 | 0 | 33 | 2014 | 2.00 | 2.00 |  |
| MAMIT | Ngaizawl SC qrt | 786 |  |  |  | 14 | 0 | 0 | 0 |  | 2014 | 2.00 | 2.00 |  |
| MAMIT | Dam diai SC | 1036 |  |  |  | 35 | 0 | 0 | 0 |  | 2014 | 2.00 | 2.00 |  |

Infrastructure- Annexure -V

Ongoing / Spill Over Works

| Name of the District | Type and Name of the Facility | Year of Approval of Project | Total Project Cost | Amount Approved in 2011-12 (if any) | Amount Approved in 2012-13 | Amount Proposed for 2013-14 (if any) | Remaining Amount (if any) | Physical Progress till date | Time Line for Completion | Justification |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Aizawl District | Sub-centre(2 no.). Sub-centre quarters(6no.). Type-II quarters(1no.). | 2012-2013. 2012-2013. 2012-2013. | 12.58 lakhs. 43.62 lakhs. 8.92 lakhs. |  | 12.58 lakhs. 43.62 lakhs. 8.92 lakhs. |  |  | 80% 80% 80% | 2013 2013 2013 | Works in progress and expected to complete before March 2013. |
| Kolasib District | Sub-centre(8 no.). Sub-centre quarters(2 no.). | 2012-2013. 2012-2013. 2012-2013. | 46.96 lakhs. 13.58 lakhs. |  | 46.96 lakhs. 13.58 lakhs. |  |  | 80% 85% | 2013 2013 2013 |  |
| Mamit District | Sub-centre(5no.) | 2012-2013 | 31 lakhs |  | 31 lakhs |  |  | 80% | 2013 |  |
| Serchhip District | Sub-centre(8no.). PHC(1no). Type-II quarters(1no.). | 2012-2013. 2012-2013. 2012-2013. | 49.6 lakhs. 91.46 lakhs. 7.17lakhs. |  | 49.6 lakhs. 91.46 lakhs. 7.17lakhs. |  |  | 80% 80% 85% | 2013 |  |
| Lunglei District | Type-II quarters(2no.). Type-IV quarters(1 no.). | 2012-2013 | 19.8 lakhs. 18.31 lakhs. |  | 19.8 lakhs. 18.31 lakhs. |  |  | 80% 90% | 2013 |  |
| Lawngtlai District | Type-III quarters(1 no.) | 2012-2013 | 15.82 lakhs |  | 15.82 lakhs |  |  | 85% | 2013 |  |
| Saiha District | Sub-centre(2 no.) | 2012-2013 | 15.36 lakhs |  | 15.36 lakhs |  |  | 90% | 2013 |  |
| Champhai District | Sub-centre(19 no.). Sub-centre quarters(3no.). | 2012-2013 | 122.55 lakhs. 22.38lakhs. |  | 122.55 lakhs. 22.38lakhs. |  |  | 85%. 80%. | V |  |

Infrastructure- Annexure -VI

Achievements in Infrastructure Development -

| Health Facility | Year | No. Sanctioned |  | Progress of New Constructions |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | No. Completed |  | No. Under Construction |  | No. Sanctioned but Yet to start |  |
|  |  | High Focus Districts | Non High Focus Districts | High Focus Districts | Non High Focus Districts | High Focus Districts | Non High Focus Districts | High Focus Districts | Non High Focus Districts |
| DH | Start of NRHM till 2012-13 | 3 | 2 | 3 | 2 |  |  |  |  |
|  | In 2012-13 |  |  |  |  |  |  |  |  |
| SDH and other hospitals above CHC | Start of NRHM till 2012-13 |  |  |  |  |  |  |  |  |
|  | In 2012-13 |  |  |  |  |  |  |  |  |
| CHCs | Start of NRHM till 2012-13 | 2 | 6 | 2 | 6 |  |  |  |  |
|  | In 2012-13 |  |  |  |  |  |  |  |  |
| PHCs | Start of NRHM till 2012-13 | 4 | 8 | 4 | 8 |  |  |  |  |
|  | In 2012-13 |  |  |  |  |  |  |  |  |
| APHC/ Others | Start of NRHM till 2012-13 | 27 | 95 | 27 | 95 |  |  |  |  |
|  | In 2012-13 | 1 | 5 |  |  |  | 2 | 1 | 3 |
| Sub-Centers | Start of NRHM till 2012-13 | 67 | 127 | 67 | 127 |  |  |  |  |
|  | In 2012-13 | 7 | 43 |  |  | 2 | 19 | 5 | 24 |

| SUMMARY OF PROPOSED CIVIL CONSTRUCTION 2013-2014 |  |  |  |
| --- | --- | --- | --- |
| SL.NO | Name of works | Nos | Budget(Rs.) |
| 1 | Re-Construction of Sub-Centre | 23 | 15,351,000.00 |
| 2 | Re-Construction of Sub-Centre Quarter | 13 | 9,321,000.00 |
| 3 | Renovation of Sub-Centre Quarter | 2 | 400,000.00 |
| 4 | Re-construction of PHC | 6 | 56,148,000.00 |
| 5 | Construction PHC Type III quarter | 3 | 4,427,000.00 |
| 6 | Construction PHC Type II quarter | 13 | 12,396,000.00 |
| 7 | Construction PHC Type I quarter | 2 | 1,278,000.00 |
| 8 | Construction PHC Kitchen | 2 | 856,000.00 |
| 9 | Extension / renovation of PHC | 2 | 1,400,000.00 |
| 10 | Construction RCC Water tank at PHC | 2 | 1,318,000.00 |
| 11 | Construction CHC Type III quarter | 1 | 1,476,000.00 |
| 12 | Renovation of CHC | 1 | 200,000.00 |
| 13 | Construction Type II District Hospital quarter | 2 | 1,873,000.00 |
| 14 | Construction Administrative Building | 2 | 9,539,000.00 |
| 15 | Construction Type III District Hospital quarter | 1 | 1,562,000.00 |
| 16 | Upgradation of CHC to SDH | 2 | 38,454,000.00 |
| TOTAL |  | 77 | 155,999,000.00 |
| TOTAL (in Lakhs) |  |  | 1,559.99 |

DISTRICT WISE ABSTRACT COST OF PROPOSED CIVIL CONSTRUCTION

| KOLASIB DISTRICT |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Sl.No. |  |  |  | TYPE OF WORKS | NO. |  | AMOUNT(Rs) |  | TOTAL AMOUNT(Rs) |  |
| I | RE-CONSTRUCTION OF SUB CENTRE |  |  |  |  |  |  |  | Rs 2,920,000.00 |  |
|  | 1 |  | Hmar Veng SC Clinic |  | 1 |  |  |  |  |  |
|  | 2 |  | Parkkawn SC Clinic |  | 1 |  |  |  |  |  |
|  | 3 |  | Vairengte SC Clinic |  | 1 |  |  |  |  |  |
|  | 4 |  | Kawnpui SC Clinic |  | 1 |  |  |  |  |  |
|  | 5 |  | Bilkhawthlir SC Clinic |  | 1 |  |  |  |  |  |
|  |  |  | a) Civil Works including Cost Index 2011 @ 17.62% of MPWD SOR 2007 for Kolasib Division |  |  |  | Rs. 493,705.00 |  |  |  |
|  |  |  | b) Water Supply & Sanitary Installation @ 7.5% |  |  |  | Rs. 37,027.88 |  |  |  |
|  |  |  | c) Electrification @ 8.5% |  |  |  | Rs. 41,964.93 |  |  |  |
|  |  |  | Sub Total |  |  |  | Rs. 572,697.80 |  |  |  |
|  |  |  | d) Quality control & Monitoring @ 1% |  |  |  | Rs. 5,726.98 |  |  |  |
|  |  |  | e) Contingency & Administrative Charges @ 1% |  |  |  | Rs. 5,726.98 |  |  |  |
|  |  |  | Total |  |  |  | Rs. 584,151.76 |  |  |  |
|  |  |  | Say |  |  |  | Rs. 584,000.00 |  |  |  |
|  |  |  | No.of Sub Centre |  | 5 |  | Rs. 2,920,000.00 |  |  |  |
| III | RE CONSTRUCTION OF PHC |  |  |  |  |  |  |  | Rs 16,428,000.00 |  |
|  | 1 |  |  | Lungdai |  | 1 |  |  |  |  |
|  | 2 |  |  | Bukpui |  | 1 |  |  |  |  |
|  |  |  |  | a) Civil Works including Cost Index 2011 @ 17.62% of MPWD SOR 2007 for Kolasib Division |  |  |  | Rs. 6,801,555.00 |  |  |
|  |  |  |  | b) Water Supply & Sanitary Installation |  |  |  | Rs. 332,826.00 |  |  |
|  |  |  |  | c) Electrification |  |  |  | Rs. 918,210.00 |  |  |
|  |  |  |  | Sub Total |  |  |  | Rs. 8,052,591.00 |  |  |
|  |  |  |  | d) Quality control & Monitoring @ 1% |  |  |  | Rs. 80,525.91 |  |  |
|  |  |  |  | e) Contingency & Administrative Charges @ 1% |  |  |  | Rs. 80,525.91 |  |  |
|  |  |  |  | Total |  |  |  | Rs. 8,213,642.82 |  |  |
|  |  |  |  | Say |  |  |  | Rs. 8,214,000.00 |  |  |
|  |  |  |  | No.of PHC |  | 2 |  | Rs. 16,428,000.00 |  |  |
| IV | CONSTRUCTION OF STAFF BUILDING |  |  |  |  |  |  |  | Rs 4,443,000.00 |  |
|  | 1 |  |  | DPMSU Office |  | 1 |  |  |  |  |
|  |  |  |  | a) Civil Works including Cost Index 2011 @ 17.62% of MPWD SOR 2007 for Kolasib Division |  |  |  | Rs. 3,755,040.00 |  |  |
|  |  |  |  | b) Water Supply & Sanitary Installation @ 7.5% |  |  |  | Rs. 281,628.00 |  |  |
|  |  |  |  | c) Electrification @ 8.5% |  |  |  | Rs. 319,178.40 |  |  |
|  |  |  |  | Sub Total |  |  |  | Rs. 4,355,846.40 |  |  |
|  |  |  |  | d) Quality control & Monitoring @ 1% |  |  |  | Rs. 43,558.46 |  |  |
|  |  |  |  | e) Contingency & Administrative Charges @ 1% |  |  |  | Rs. 43,558.46 |  |  |
|  |  |  |  | Total |  |  |  | Rs. 4,442,963.33 |  |  |
|  |  |  |  | Say |  |  |  | Rs. 4,443,000.00 |  |  |
|  |  |  |  | No.of building |  | 1 |  | Rs. 4,443,000.00 |  |  |
| Grand Total of Kolasib District |  |  |  |  |  |  |  |  | Rs 23,791,000.00 |  |
| CHAMPHAI DISTRICT |  |  |  |  |  |  |  |  |  |  |
| Sl.No. |  |  |  | TYPE OF WORKS |  | NO. |  | AMOUNT(Rs) |  | TOTAL AMOUNT(Rs) |
| I |  | RE CONSTRUCTION OF SUB CENTRE |  |  |  |  |  |  |  | Rs 2,572,000.00 |
|  |  | 1 |  | Mimbung SC |  | 1 |  |  |  |  |
|  |  | 2 |  | NE Khawdungsei SC |  | 1 |  |  |  |  |
|  |  | 3 |  | Khuangphah SC |  | 1 |  |  |  |  |
|  |  | 4 |  | Bungzung SC |  | 1 |  |  |  |  |
|  |  |  |  | a) Civil Works including Cost Index 2011 @ 29.34% of MPWD SOR 2007 for Champhai Division |  |  |  | Rs. 543,468.00 |  |  |
|  |  |  |  | b) Water Supply & Sanitary Installation @ 7.5% |  |  |  | Rs. 40,760.10 |  |  |
|  |  |  |  | c) Electrification @ 8.5% |  |  |  | Rs. 46,194.78 |  |  |
|  |  |  |  | Sub Total |  |  |  | Rs. 630,422.88 |  |  |
|  |  |  |  | d) Quality control & Monitoring @ 1% |  |  |  | Rs. 6,304.23 |  |  |
|  |  |  |  | e) Contingency & Administrative Charges @ 1% |  |  |  | Rs. 6,304.23 |  |  |
|  |  |  |  | Total |  |  |  | Rs. 643,031.34 |  |  |
|  |  |  |  | Say |  |  |  | Rs. 643,000.00 |  |  |
|  |  |  |  | No.of Sub Centre |  | 4 |  | Rs. 2,572,000.00 |  |  |
| II |  | RE CONSTRUCTION OF SUB CENTRE QUARTER |  |  |  |  |  |  |  | Rs 693,000.00 |
|  |  | 1 |  | Khuangphah |  | 1 |  |  |  |  |
|  |  |  |  | a) Civil Works including Cost Index 2011 @ 29.34% of MPWD SOR 2007 for Champhai Division |  |  |  | Rs. 585,736.00 |  |  |
|  |  |  |  | b) Water Supply & Sanitary Installation @ 7.5% |  |  |  | Rs. 43,930.20 |  |  |
|  |  |  |  | c) Electrification @ 8.5% |  |  |  | Rs. 49,787.56 |  |  |
|  |  |  |  | Sub Total |  |  |  | Rs. 679,453.76 |  |  |
|  |  |  |  | d) Quality control & Monitoring @ 1% |  |  |  | Rs. 6,794.54 |  |  |
|  |  |  |  | e) Contingency & Administrative Charges @ 1% |  |  |  | Rs. 6,794.54 |  |  |
|  |  |  |  | Total |  |  |  | Rs. 693,042.84 |  |  |
|  |  |  |  | Say |  |  |  | Rs. 693,000.00 |  |  |
|  |  |  |  | No.of Sub Centre Qtr |  | 1 |  | Rs. 693,000.00 |  |  |
| III |  | RE CONSTRUCTION OF PHC |  |  |  |  |  |  |  | Rs 9,037,000.00 |
|  |  | 1 |  | Rabung |  | 1 |  |  |  |  |
|  |  |  |  | a) Civil Works including Cost Index 2011 @ 29.34% of MPWD SOR 2007 for Champhai Division |  |  |  | Rs. 7,483,541.00 |  |  |
|  |  |  |  | b) Water Supply & Sanitary Installation |  |  |  | Rs. 365,989.00 |  |  |
|  |  |  |  | c) Electrification |  |  |  | Rs. 1,010,278.00 |  |  |
|  |  |  |  | Sub Total |  |  |  | Rs. 8,859,808.00 |  |  |
|  |  |  |  | d) Quality control & Monitoring @ 1% |  |  |  | Rs. 88,598.08 |  |  |
|  |  |  |  | e) Contingency & Administrative Charges @ 1% |  |  |  | Rs. 88,598.08 |  |  |
|  |  |  |  | Total |  |  |  | Rs. 9,037,004.16 |  |  |
|  |  |  |  | Say |  |  |  | Rs. 9,037,000.00 |  |  |
|  |  |  |  | No.of PHC |  | 1 |  | Rs. 9,037,000.00 |  |  |
| IV |  | CONSTRUCTION OF ADMINISTRATIVE BUILDING |  |  |  |  |  |  |  | Rs 5,096,000.00 |
|  |  | 1 |  | Champhai |  | 1 |  |  |  |  |
|  |  |  |  | a) Civil Works including Cost Index 2011 @ 29.34% of MPWD SOR 2007 for Champhai Division |  |  |  | Rs. 4,129,204.00 |  |  |
|  |  |  |  | b) Water Supply & Sanitary Installation @ 7.5% |  |  |  | Rs. 309,690.30 |  |  |
|  |  |  |  | c) Electrification @ 13.5% |  |  |  | Rs. 557,442.54 |  |  |
|  |  |  |  | Sub Total |  |  |  | Rs. 4,996,336.84 |  |  |
|  |  |  |  | d) Quality control & Monitoring @ 1% |  |  |  | Rs. 49,963.37 |  |  |
|  |  |  |  | e) Contingency & Administrative Charges @ 1% |  |  |  | Rs. 49,963.37 |  |  |
|  |  |  |  | Total |  |  |  | Rs. 5,096,263.58 |  |  |
|  |  |  |  | Say |  |  |  | Rs. 5,096,000.00 |  |  |
|  |  |  |  | No.of building |  | 1 |  | Rs. 5,096,000.00 |  |  |
| V |  | UPGADATION OF KHAWZAWL CHC TO SUB-DISTRICT HOSPITAL |  |  |  |  |  |  |  | Rs 18,868,000.00 |
|  |  | 1 |  | Khawzawl |  | 1 |  |  |  |  |
|  |  |  |  | a) Civil Works including Cost Index 2011 @ 22.35% of MPWD SOR 2007 for Khawzawl Division |  |  |  | Rs. 15,287,737.00 |  |  |
|  |  |  |  | b) Water Supply & Sanitary Installation @ 7.5% |  |  |  | Rs. 1,146,580.28 |  |  |
|  |  |  |  | c) Electrification @ 13.5% |  |  |  | Rs. 2,063,844.50 |  |  |
|  |  |  |  | Sub Total |  |  |  | Rs. 18,498,161.77 |  |  |
|  |  |  |  | d) Quality control & Monitoring @ 1% |  |  |  | Rs. 184,981.62 |  |  |
|  |  |  |  | e) Contingency & Administrative Charges @ 1% |  |  |  | Rs. 184,981.62 |  |  |
|  |  |  |  | Total |  |  |  | Rs. 18,868,125.01 |  |  |
|  |  |  |  | Say |  |  |  | Rs. 18,868,000.00 |  |  |
|  |  |  |  | No.of building |  | 1 |  | Rs. 18,868,000.00 |  |  |
| Grand Total of Champhai District |  |  |  |  |  |  |  |  |  | Rs 36,266,000.00 |
| AIZAWL EAST DISTRICT |  |  |  |  |  |  |  |  |  |  |
| Sl.No. |  |  |  | TYPE OF WORKS |  | NO. |  | AMOUNT(Rs) |  | TOTAL AMOUNT(Rs) |
| I |  | RE CONSTRUCTION OF SUB CENTRE |  |  |  |  |  |  |  | Rs 626,000.00 |
|  |  | 1 |  | Tuithiang |  | 1 |  |  |  |  |
|  |  |  |  | a) Civil Works including Cost Index 2011 @ 26.06% of MPWD SOR 2007 for Aizawl Division |  |  |  | Rs. 529,132.00 |  |  |
|  |  |  |  | b) Water Supply & Sanitary Installation @ 7.5% |  |  |  | Rs. 39,684.90 |  |  |
|  |  |  |  | c) Electrification @ 8.5% |  |  |  | Rs. 44,976.22 |  |  |
|  |  |  |  | Sub Total |  |  |  | Rs. 613,793.12 |  |  |
|  |  |  |  | d) Quality control & Monitoring @ 1% |  |  |  | Rs. 6,137.93 |  |  |
|  |  |  |  | e) Contingency & Administrative Charges @ 1% |  |  |  | Rs. 6,137.93 |  |  |
|  |  |  |  | Total |  |  |  | Rs. 626,068.98 |  |  |
|  |  |  |  | Say |  |  |  | Rs. 626,000.00 |  |  |
|  |  |  |  | No.of Sub Centre |  | 1 |  | Rs. 626,000.00 |  |  |
| II |  | RE CONSTRUCTION OF SUB CENTRE QUARTER |  |  |  |  |  |  |  | Rs 2,025,000.00 |
|  |  | 1 |  | Tualbung |  | 1 |  |  |  |  |
|  |  | 2 |  | Sihfa |  | 1 |  |  |  |  |
|  |  | 3 |  | Sesawng |  | 1 |  |  |  |  |
|  |  |  |  | a) Civil Works including Cost Index 2011 @ 26.06.62% of MPWD SOR 2007 for Aizawl Division |  |  |  | Rs. 570,552.00 |  |  |
|  |  |  |  | b) Water Supply & Sanitary Installation @ 7.5% |  |  |  | Rs. 42,791.40 |  |  |
|  |  |  |  | c) Electrification @ 8.5% |  |  |  | Rs. 48,496.92 |  |  |
|  |  |  |  | Sub Total |  |  |  | Rs. 661,840.32 |  |  |
|  |  |  |  | d) Quality control & Monitoring @ 1% |  |  |  | Rs. 6,618.40 |  |  |
|  |  |  |  | e) Contingency & Administrative Charges @ 1% |  |  |  | Rs. 6,618.40 |  |  |
|  |  |  |  | Total |  |  |  | Rs. 675,077.13 |  |  |
|  |  |  |  | Say |  |  |  | Rs. 675,000.00 |  |  |
|  |  |  |  | No.of Sub Centre Qtr |  | 3 |  | Rs. 2,025,000.00 |  |  |
| III |  | RE CONSTRUCTION OF PHC |  |  |  |  |  |  |  | Rs 8,803,000.00 |
|  |  | 1 |  | Darlawn |  | 1 |  |  |  |  |
|  |  |  |  | a) Civil Works including Cost Index 2011 @ 26.06% of MPWD SOR 2007 for Aizawl Division |  |  |  | Rs. 7,289,611.00 |  |  |
|  |  |  |  | b) Water Supply & Sanitary Installation |  |  |  | Rs. 356,708.00 |  |  |
|  |  |  |  | c) Electrification |  |  |  | Rs. 984,097.00 |  |  |
|  |  |  |  | Sub Total |  |  |  | Rs. 8,630,416.00 |  |  |
|  |  |  |  | d) Quality control & Monitoring @ 1% |  |  |  | Rs. 86,304.16 |  |  |
|  |  |  |  | e) Contingency & Administrative Charges @ 1% |  |  |  | Rs. 86,304.16 |  |  |
|  |  |  |  | Total |  |  |  | Rs. 8,803,024.32 |  |  |
|  |  |  |  | Say |  |  |  | Rs. 8,803,000.00 |  |  |
|  |  |  |  | No.of PHC |  | 1 |  | Rs. 8,803,000.00 |  |  |
| Grand Total of Aizawl East District |  |  |  |  |  |  |  |  |  | Rs 11,454,000.00 |
| AIZAWL WEST DISTRICT |  |  |  |  |  |  |  |  |  |  |
| Sl.No. |  |  |  | TYPE OF WORKS |  | NO. |  | AMOUNT(Rs) |  | TOTAL AMOUNT(Rs) |
| I |  | RE CONSTRUCTION OF SUB CENTRE |  |  |  |  |  |  |  | Rs 3,130,000.00 |
|  |  | 1 |  | Vaivakawn |  | 1 |  |  |  |  |
|  |  | 2 |  | Dinthar |  | 1 |  |  |  |  |
|  |  | 3 |  | Hlimen |  | 1 |  |  |  |  |
|  |  | 4 |  | Thiak |  | 1 |  |  |  |  |
|  |  | 5 |  | Hreichhuk |  | 1 |  |  |  |  |
|  |  |  |  | a) Civil Works including Cost Index 2011 @ 26.06% of MPWD SOR 2007 for Aizawl Division |  |  |  | Rs. 529,132.00 |  |  |
|  |  |  |  | b) Water Supply & Sanitary Installation @ 7.5% |  |  |  | Rs. 39,684.90 |  |  |
|  |  |  |  | c) Electrification @ 8.5% |  |  |  | Rs. 44,976.22 |  |  |
|  |  |  |  | Sub Total |  |  |  | Rs. 613,793.12 |  |  |
|  |  |  |  | d) Quality control & Monitoring @ 1% |  |  |  | Rs. 6,137.93 |  |  |
|  |  |  |  | e) Contingency & Administrative Charges @ 1% |  |  |  | Rs. 6,137.93 |  |  |
|  |  |  |  | Total |  |  |  | Rs. 626,068.98 |  |  |
|  |  |  |  | Say |  |  |  | Rs. 626,000.00 |  |  |
|  |  |  |  | No.of Sub Centre |  | 5 |  | Rs. 3,130,000.00 |  |  |
| Grand Total of Aizawl west District |  |  |  |  |  |  |  |  |  | Rs 3,130,000.00 |
|  |  |  |  | LUNGLEI DISTRICT (Reconstruction) |  |  |  |  |  |  |
| Sl.No. |  |  |  | TYPE OF WORKS |  | NO. |  | AMOUNT(Rs) |  | TOTAL AMOUNT(Rs) |
| A |  |  |  | CONSTRUCTION OF PHC BUILDING |  |  |  |  |  |  |
|  |  | 1 |  | Haulawng |  | 1 |  |  |  |  |
|  |  |  |  | a) Civil Works including Cost Index 2011 @ 39.88% of MPWD SOR 2007 for Lunglei Division |  |  |  | Rs. 8,739,978.00 |  |  |
|  |  |  |  | a) Electrification @ 13.5% |  |  |  | Rs. 1,179,897.03 |  |  |
|  |  |  |  | Sub Total |  |  |  | Rs. 9,919,875.03 |  |  |
|  |  |  |  | b) Quality control & Monitoring @ 2% |  |  |  | Rs. 198,397.50 |  |  |
|  |  |  |  | c) Contingency & Administrative Charges @ 3% |  |  |  | Rs. 297,596.25 |  |  |
|  |  |  |  | G.Total |  |  |  | Rs. 10,415,868.78 |  |  |
|  |  |  |  | Say |  |  |  | Rs. 10,416,000.00 |  | Rs 10,416,000.00 |
| Sl.No. |  |  |  | TYPE OF WORKS |  | NO. |  | AMOUNT(Rs) |  | TOTAL AMOUNT(Rs) |
| B |  |  |  | RE CONSTRUCTION OF TYPE-II QUARTER |  |  |  |  |  |  |
|  |  | 1 |  | Bunghmun |  | 1 |  |  |  |  |
|  |  | 2 |  | Buarpui |  | 1 |  |  |  |  |
|  |  | 3 |  | Pangzawl |  | 1 |  |  |  |  |
|  |  | 4 |  | Cherhlun |  | 1 |  |  |  |  |
|  |  | 5 |  | S.Vanlaiphai |  | 1 |  |  |  |  |
|  |  |  |  | a) Civil Works including Cost Index 2011 @ 39.88% of MPWD SOR 2007 for LungleiDivision |  |  |  | Rs. 803,116.00 |  |  |
|  |  |  |  | b) Water Supply & Sanitary Installation @ 7.5% |  |  |  | Rs. 60,233.70 |  |  |
|  |  |  |  | c) Electrification @ 8.5% |  |  |  | Rs. 68,264.86 |  |  |
|  |  |  |  | Sub Total |  |  |  | Rs. 931,614.56 |  |  |
|  |  |  |  | d) Quality control & Monitoring @ 2% |  |  |  | Rs. 18,632.29 |  |  |
|  |  |  |  | e) Contingency & Administrative Charges @ 3% |  |  |  | Rs. 27,948.44 |  |  |
|  |  |  |  | G.Total |  |  |  | Rs. 978,195.29 |  |  |
|  |  |  |  | Say |  |  |  | Rs. 978,000.00 |  |  |
|  |  |  |  | No.of Type-II Qtr Building |  | 5 |  | Rs. 4,890,000.00 |  | Rs 4,890,000.00 |
| Sl.No. |  |  |  | TYPE OF WORKS |  | NO. |  | AMOUNT(Rs) |  | TOTAL AMOUNT(Rs) |
| C |  |  |  | CONSTRUCTION OF RCC WATER TANK |  |  |  |  |  |  |
|  |  | 1 |  | Cherhlun |  | 1 |  |  |  |  |
|  |  | 2 |  | Lungsen |  | 1 |  |  |  |  |
|  |  |  |  | a) Civil Works including Cost Index 2011 @ 39.88% of MPWD SOR 2007 for Lunglei Division |  |  |  | Rs.627,215.00 |  |  |
|  |  |  |  | d) Quality control & Monitoring @ 2% |  |  |  | Rs. 12,544.30 |  |  |
|  |  |  |  | e) Contingency & Administrative Charges @ 3% |  |  |  | Rs. 18,816.45 |  |  |
|  |  |  |  | G.Total |  |  |  | Rs. 658,575.75 |  |  |
|  |  |  |  | Say |  |  |  | Rs. 659,000.00 |  |  |
|  |  |  |  | No.of RCC Water Tank |  | 2 |  | Rs. 1,318,000.00 |  | Rs 1,318,000.00 |
| Sl.No. |  |  |  | TYPE OF WORKS |  | NO. |  | AMOUNT(Rs) |  | TOTAL AMOUNT(Rs) |
| A |  | A |  | UPGRADATION OF HNAHTHIAL CHC TO SUB-DISTRICT HOSPITAL |  |  |  |  |  |  |
|  |  | 1 |  |  |  | 1 |  |  |  |  |
|  |  |  |  | a) Civil Works including Cost Index 2011 @ 39.88% of MPWD SOR 2007 for Lunglei Division |  |  |  | Rs15,416,315.00 |  |  |
|  |  |  |  | a) Electrification @ 13.5% |  |  |  | Rs. 2,081,202.53 |  |  |
|  |  |  |  | b) Water Supply &sanitary7.5% |  |  |  | Rs. 1,156,223.63 |  |  |
|  |  |  |  | Sub Total |  |  |  | Rs. 18,653,741.15 |  |  |
|  |  |  |  | b) Quality control & Monitoring @ 2% |  |  |  | Rs. 373,074.82 |  |  |
|  |  |  |  | c) Contingency & Administrative Charges @ 3% |  |  |  | Rs. 559,612.23 |  |  |
|  |  |  |  | Total |  |  |  | Rs. 19,586,428.21 |  |  |
|  |  |  |  | Say |  |  |  | Rs. 19,586,000.00 |  | Rs 19,586,000.00 |
| Grand Total for Lunglei District |  |  |  |  |  |  |  |  |  | 36,210,000.00 |
|  |  |  |  | LAWNGTLAI DISTRICT (Reconstruction) |  |  |  |  |  |  |
| Sl.No. |  |  |  | TYPE OF WORKS |  | NO. |  | AMOUNT(Rs) |  | TOTAL AMOUNT(Rs) |
| A |  |  |  | RE CONSTRUCTION OF SUB CENTRE |  |  |  |  |  |  |
|  |  | 1 |  | Vathuampui |  | 1 |  |  |  |  |
|  |  | 2 |  | Hmunlai |  | 1 |  |  |  |  |
|  |  | 3 |  | Lawngtlai -I |  | 1 |  |  |  |  |
|  |  |  |  | a) Civil Works including Cost Index 2011 @ 50.78% of MPWD SOR 2007 for Lawngtlai Division |  |  |  | Rs. 632,893.00 |  |  |
|  |  |  |  | b) Water Supply & Sanitary Installation @ 7.5% |  |  |  | Rs. 47,466.98 |  |  |
|  |  |  |  | c) Electrification @ 8.5% |  |  |  | Rs. 53,795.91 |  |  |
|  |  |  |  | Sub Total |  |  |  | Rs. 734,155.88 |  |  |
|  |  |  |  | d) Quality control & Monitoring @ 2% |  |  |  | Rs. 14,683.12 |  |  |
|  |  |  |  | e) Contingency & Administrative Charges @ 3% |  |  |  | Rs. 22,024.68 |  |  |
|  |  |  |  | G.Total |  |  |  | Rs. 770,863.67 |  |  |
|  |  |  |  | Say |  |  |  | Rs. 771,000.00 |  |  |
|  |  |  |  | No.of Sub Centre Building |  | 3 |  | Rs. 2,313,000.00 |  | Rs 2,313,000.00 |
| Sl.No. |  |  |  | TYPE OF WORKS |  | NO. |  | AMOUNT(Rs) |  | TOTAL AMOUNT(Rs) |
| B |  |  |  | CONSTRUCTION OF SUB CENTRE QUARTER |  |  |  |  |  |  |
|  |  | 1 |  | Vathuampui |  | 1 |  |  |  |  |
|  |  | 2 |  | Hmunlai |  | 1 |  |  |  |  |
|  |  | 3 |  | Lawngtlai -I |  | 1 |  |  |  |  |
|  |  |  |  | a) Civil Works including Cost Index 2011 @ 50.78% of MPWD SOR 2007 for Lawngtlai Division |  |  |  | Rs. 682,435.00 |  |  |
|  |  |  |  | b) Water Supply & Sanitary Installation @ 7.5% |  |  |  | Rs. 51,182.63 |  |  |
|  |  |  |  | c) Electrification @ 8.5% |  |  |  | Rs. 58,006.98 |  |  |
|  |  |  |  | Sub Total |  |  |  | Rs. 791,624.60 |  |  |
|  |  |  |  | d) Quality control & Monitoring @ 2% |  |  |  | Rs. 15,832.49 |  |  |
|  |  |  |  | e) Contingency & Administrative Charges @ 3% |  |  |  | Rs. 23,748.74 |  |  |
|  |  |  |  | G.Total |  |  |  | Rs. 831,205.83 |  |  |
|  |  |  |  | Say |  |  |  | Rs. 831,000.00 |  |  |
|  |  |  |  | No.of Sub Centre Quarter Building |  | 3 |  | Rs. 2,493,000.00 |  | Rs 2,493,000.00 |
| Sl.No. |  |  |  | TYPE OF WORKS |  | NO. |  | AMOUNT(Rs) |  | TOTAL AMOUNT(Rs) |
| C |  |  |  | CONSTRUCTION OF PHC QUARTER TYPE-II |  |  |  |  |  |  |
|  |  | 1 |  | Sangau |  | 1 |  |  |  |  |
|  |  | 2 |  | Bualpui |  | 1 |  |  |  |  |
|  |  | 3 |  | Lungpher |  | 1 |  |  |  |  |
|  |  |  |  | a) Civil Works including Cost Index 2011 @ 50.78% of MPWD SOR 2007 for Lawngtlai Division |  |  |  | Rs. 865,698.00 |  |  |
|  |  |  |  | b) Water Supply & Sanitary Installation @ 7.5% |  |  |  | Rs. 64,927.35 |  |  |
|  |  |  |  | c) Electrification @ 8.5% |  |  |  | Rs. 73,584.33 |  |  |
|  |  |  |  | Sub Total |  |  |  | Rs. 1,004,209.68 |  |  |
|  |  |  |  | d) Quality control & Monitoring @ 2% |  |  |  | Rs. 20,084.19 |  |  |
|  |  |  |  | e) Contingency & Administrative Charges @ 3% |  |  |  | Rs. 30,126.29 |  |  |
|  |  |  |  | G.Total |  |  |  | Rs. 1,054,420.16 |  |  |
|  |  |  |  | Say |  |  |  | Rs. 1,054,000.00 |  |  |
|  |  |  |  | No.ofType-II Quarter Building |  | 3 |  | Rs. 3,162,000.00 |  | Rs 3,162,000.00 |
| TOTAL OF LAWNGTLAI |  |  |  |  |  |  |  |  |  | Rs 7,968,000.00 |
|  |  |  |  | SAIHA DISTRICT (Reconstruction) |  |  |  |  |  |  |
| Sl.No. |  |  |  | TYPE OF WORKS |  | NO. |  | AMOUNT(Rs) |  | TOTAL AMOUNT(Rs) |
| A |  | A |  | RE CONSTRUCTION OF PHC BUILDING |  |  |  |  |  |  |
|  |  | 1 |  | Tuipang |  | 1 |  |  |  |  |
|  |  |  |  | a) Civil Works including Cost Index 2011 @ 53.95% of MPWD SOR 2007 for Saiha Division |  |  |  | Rs. 9,619,100.00 |  |  |
|  |  |  |  | a) Electrification @ 13.5% |  |  |  | Rs. 1,298,578.50 |  |  |
|  |  |  |  | Sub Total |  |  |  | Rs. 10,917,678.50 |  |  |
|  |  |  |  | b) Quality control & Monitoring @ 2% |  |  |  | Rs. 218,353.57 |  |  |
|  |  |  |  | c) Contingency & Administrative Charges @ 3% |  |  |  | Rs. 327,530.36 |  |  |
|  |  |  |  | Total |  |  |  | Rs. 11,463,562.43 |  |  |
|  |  |  |  | Say |  |  |  | Rs. 11,464,000.00 |  | Rs 11,464,000.00 |
| Sl.No. |  |  |  | TYPE OF WORKS |  | NO. |  | AMOUNT(Rs) |  | TOTAL AMOUNT(Rs) |
| B |  | B |  | RE CONSTRUCTION OF SUB CENTRE |  |  |  |  |  |  |
|  |  | 1 |  | Phura |  | 1 |  |  |  |  |
|  |  | 2 |  | Longban |  | 1 |  |  |  |  |
|  |  | 3 |  | Mohre |  | 1 |  |  |  |  |
|  |  | 4 |  | Latawh |  | 1 |  |  |  |  |
|  |  |  |  | a) Civil Works including Cost Index 2011 @ 53.95% of MPWD SOR 2007 for Saiha Division |  |  |  | Rs. 646,876.00 |  |  |
|  |  |  |  | b) Water Supply & Sanitary Installation @ 7.5% |  |  |  | Rs. 48,515.70 |  |  |
|  |  |  |  | c) Electrification @ 8.5% |  |  |  | Rs. 54,984.46 |  |  |
|  |  |  |  | Sub Total |  |  |  | Rs. 750,376.16 |  |  |
|  |  |  |  | d) Quality control & Monitoring @ 2% |  |  |  | Rs. 15,007.52 |  |  |
|  |  |  |  | e) Contingency & Administrative Charges @ 3% |  |  |  | Rs. 22,511.28 |  |  |
|  |  |  |  | Total |  |  |  | Rs. 787,894.97 |  |  |
|  |  |  |  | Say |  |  |  | Rs. 788,000.00 |  |  |
|  |  |  |  | No.of Sub Centre |  | 4 |  | Rs. 3,152,000.00 |  | Rs 3,152,000.00 |
| Sl.No. |  |  |  | TYPE OF WORKS |  | NO. |  | AMOUNT(Rs) |  | TOTAL AMOUNT(Rs) |
| C |  | B |  | CONSTRUCTION OF QUARTER TYPE-II |  |  |  |  |  |  |
|  |  | 1 |  | District Hospital, Saiha |  | 1 |  |  |  |  |
|  |  |  |  | a) Civil Works including Cost Index 2011 @ 53.95% of MPWD SOR 2007 for Saiha Division |  |  |  | Rs. 883,899.00 |  |  |
|  |  |  |  | b) Water Supply & Sanitary Installation @ 7.5% |  |  |  | Rs. 66,292.43 |  |  |
|  |  |  |  | c) Electrification @ 8.5% |  |  |  | Rs. 5,634.86 |  |  |
|  |  |  |  | Sub Total |  |  |  | Rs. 955,826.28 |  |  |
|  |  |  |  | d) Quality control & Monitoring @ 2% |  |  |  | Rs. 19,116.53 |  |  |
|  |  |  |  | e) Contingency & Administrative Charges @ 3% |  |  |  | Rs. 28,674.79 |  |  |
|  |  |  |  | Total |  |  |  | Rs. 1,003,617.60 |  |  |
|  |  |  |  | Say |  |  |  | Rs. 1,004,000.00 |  |  |
|  |  |  |  | No.of Type-II Qtr. |  | 1 |  | Rs. 1,004,000.00 |  | Rs 1,004,000.00 |
| Sl.No. |  |  |  | TYPE OF WORKS |  | NO. |  | AMOUNT(Rs) |  | TOTAL AMOUNT(Rs) |
| D |  | B |  | CONSTRUCTION OF QUARTER TYPE-III |  |  |  |  |  |  |
|  |  | 1 |  | District Hospital, Saiha |  | 1 |  |  |  |  |
|  |  |  |  | a) Civil Works including Cost Index 2011 @ 53.95% of MPWD SOR 2007 for Saiha Division |  |  |  | Rs. 1,282,809.00 |  |  |
|  |  |  |  | b) Water Supply & Sanitary Installation @ 7.5% |  |  |  | Rs. 96,210.68 |  |  |
|  |  |  |  | c) Electrification @ 8.5% |  |  |  | Rs. 109,038.77 |  |  |
|  |  |  |  | Sub Total |  |  |  | Rs. 1,488,058.44 |  |  |
|  |  |  |  | d) Quality control & Monitoring @ 2% |  |  |  | Rs. 29,761.17 |  |  |
|  |  |  |  | e) Contingency & Administrative Charges @ 3% |  |  |  | Rs. 44,641.75 |  |  |
|  |  |  |  | Total |  |  |  | Rs. 1,562,461.36 |  |  |
|  |  |  |  | Say |  |  |  | Rs. 1,562,000.00 |  |  |
|  |  |  |  | No.of Type-II Qtr. |  | 1 |  | Rs. 1,562,000.00 |  | Rs 1,562,000.00 |
| Grand TOTAL OF SAIHA |  |  |  |  |  |  |  |  |  | Rs 17,182,000.00 |
|  |  |  |  | MAMIT DISTRICT(Reconstruction) |  |  |  |  |  |  |
| Sl.No. |  |  |  | TYPE OF WORKS |  | NO. |  | AMOUNT(Rs) |  | TOTAL AMOUNT(Rs) |
| A |  |  |  | CONSTRUCTION OF QUARTERS |  |  |  |  |  |  |
|  |  |  |  | Type-III quarters |  |  |  |  |  |  |
|  |  | 1 |  | Kawrthah CHC |  | 1 |  |  |  |  |
|  |  | 2 |  | W.Phaileng PHC |  | 1 |  |  |  |  |
|  |  | 3 |  | Zawlnuam PHC |  | 1 |  |  |  |  |
|  |  |  |  | a) Civil Works including Cost Index 2011 @ 24.29% of MPWD SOR 2007 for Mamit Division |  |  |  | Rs. 1,247,390.57 |  |  |
|  |  |  |  | b) Water Supply & Sanitary Installation @ 7.5% |  |  |  | Rs. 93,554.29 |  |  |
|  |  |  |  | c) Electrification @ 8.5% |  |  |  | Rs. 106,028.20 |  |  |
|  |  |  |  | d) Quality control & Monitoring @ 1% |  |  |  | Rs. 14,469.73 |  |  |
|  |  |  |  | e) Contingency & Administrative Charges @ 1% |  |  |  | Rs. 14,469.73 |  |  |
|  |  |  |  | Total |  | 1 |  | Rs. 1,475,912.52 |  |  |
|  |  |  |  | Say |  |  |  | Rs. 1,476,000.00 |  | Rs 4,428,000.00 |
| B |  |  |  | (Type-II quarters) |  |  |  |  |  |  |
|  |  | 1 |  | Mamit DH |  | 1 |  |  |  |  |
|  |  | 2 |  | Phuldungsei PHC |  | 1 |  |  |  |  |
|  |  | 3 |  | Kawrtethawveng PHC |  | 1 |  |  |  |  |
|  |  | 4 |  | KanhmunPHC |  | 1 |  |  |  |  |
|  |  | 5 |  | Rawpuichhip PHC |  | 1 |  |  |  |  |
|  |  |  |  | a) Civil Works including Cost Index 2011 @ 24.29% of MPWD SOR 2007 for Mamit Division |  |  |  | Rs. 713,606.78 |  |  |
|  |  |  |  | b) Water Supply & Sanitary Installation @ 7.5% |  |  |  | Rs. 53,520.51 |  |  |
|  |  |  |  | c) Electrification @ 8.5% |  |  |  | Rs. 60,656.58 |  |  |
|  |  |  |  | d) Quality control & Monitoring @ 2% |  |  |  | Rs. 16,555.68 |  |  |
|  |  |  |  | e) Contingency & Administrative Charges @ 3% |  |  |  | Rs. 24,833.52 |  |  |
|  |  |  |  | Total |  | 1 |  | Rs. 869,173.06 |  |  |
|  |  |  |  | Say |  |  |  | Rs. 869,000.00 |  | Rs 4,345,000.00 |
| C |  |  |  | (Type-Iquarters) |  |  |  |  |  |  |
|  |  | 1 |  | Marpara PHC |  | 1 |  |  |  |  |
|  |  | 2 |  | Rawpuichhip PHC |  | 1 |  |  |  |  |
|  |  |  |  | a) Civil Works including Cost Index 2011 @ 24.29% of MPWD SOR 2007 for Mamit Division |  |  |  | Rs. 524,935.76 |  |  |
|  |  |  |  | b) Water Supply & Sanitary Installation @ 7.5% |  |  |  | Rs. 39,370.18 |  |  |
|  |  |  |  | c) Electrification @ 8.5% |  |  |  | Rs. 44,619.54 |  |  |
|  |  |  |  | d) Quality control & Monitoring @ 2% |  |  |  | Rs. 12,178.51 |  |  |
|  |  |  |  | e) Contingency & Administrative Charges @ 3% |  |  |  | Rs. 18,267.76 |  |  |
|  |  |  |  | Total |  | 1 |  | Rs. 639,371.75 |  |  |
|  |  |  |  | Say |  |  |  | Rs. 639,000.00 |  | Rs 1,278,000.00 |
| D |  |  |  | Hospital Kitchen |  |  |  |  |  |  |
|  |  | 1 |  | Kanhmun PHC |  | 1 |  |  |  |  |
|  |  | 2 |  | Rawpuichhip PHC |  | 1 |  |  |  |  |
|  |  |  |  | a) Civil Works including Cost Index 2011 @ 24.29% of MPWD SOR 2007 for Mamit Division |  |  |  | Rs. 351,335.93 |  |  |
|  |  |  |  | b) Water Supply & Sanitary Installation @ 7.5% |  |  |  | Rs. 26,350.19 |  |  |
|  |  |  |  | c) Electrification @ 8.5% |  |  |  | Rs. 29,863.55 |  |  |
|  |  |  |  | d) Quality control & Monitoring @ 2% |  |  |  | Rs. 8,150.99 |  |  |
|  |  |  |  | e) Contingency & Administrative Charges @ 3% |  |  |  | Rs. 12,226.49 |  |  |
|  |  |  |  | Total |  | 1 |  | Rs. 427,927.16 |  |  |
|  |  |  |  | Say |  |  |  | Rs. 428,000.00 |  | Rs 856,000.00 |
| E |  |  |  | Sub-Centre |  |  |  |  |  |  |
|  |  | 1 |  | Zawlnuam |  | 1 |  |  |  |  |
|  |  |  |  | a) Civil Works including Cost Index 2011 @ 24.29% of MPWD SOR 2007 for Mamit Division |  |  |  | Rs. 523,989.56 |  |  |
|  |  |  |  | b) Water Supply & Sanitary Installation @ 7.5% |  |  |  | Rs. 39,299.22 |  |  |
|  |  |  |  | c) Electrification @ 8.5% |  |  |  | Rs. 44,539.12 |  |  |
|  |  |  |  | d) Quality control & Monitoring @ 2% |  |  |  | Rs. 12,156.56 |  |  |
|  |  |  |  | e) Contingency & Administrative Charges @ 3% |  |  |  | Rs. 18,234.84 |  |  |
|  |  |  |  | Total |  | 1 |  | Rs. 638,219.28 |  |  |
|  |  |  |  | Say |  |  |  | Rs. 638,000.00 |  | Rs 638,000.00 |
| F |  |  |  | (Sub-centre quarters) |  |  |  |  |  |  |
|  |  | 1 |  | Zawlnuam |  | 1 |  |  |  |  |
|  |  | 2 |  | Rawpuichhip |  | 1 |  |  |  |  |
|  |  | 3 |  | Parvatui |  | 1 |  |  |  |  |
|  |  | 4 |  | Tuipuibari |  | 1 |  |  |  |  |
|  |  | 5 |  | Phuldungsei |  | 1 |  |  |  |  |
|  |  | 6 |  | W.Phaileng |  | 1 |  |  |  |  |
|  |  |  |  | a) Civil Works including Cost Index 2011 @ 24.29% of MPWD SOR 2007 for Mamit Division |  |  |  | Rs. 562,037.10 |  |  |
|  |  |  |  | b) Water Supply & Sanitary Installation @ 7.5% |  |  |  | Rs. 42,152.78 |  |  |
|  |  |  |  | c) Electrification @ 8.5% |  |  |  | Rs. 47,773.15 |  |  |
|  |  |  |  | d) Quality control & Monitoring @ 2% |  |  |  | Rs. 13,039.26 |  |  |
|  |  |  |  | e) Contingency & Administrative Charges @ 3% |  |  |  | Rs. 19,558.89 |  |  |
|  |  |  |  | Total |  | 1 |  | Rs. 684,561.19 |  |  |
|  |  |  |  | Say |  |  |  | Rs. 685,000.00 |  | Rs 4,110,000.00 |
| G |  |  |  | Extension/Renovation of ward |  |  |  |  |  |  |
|  |  | 1 |  | W.Phaileng PHC |  | 1 |  |  |  |  |
|  |  | 2 |  | Rawpuichhip PHC |  | 1 |  |  |  |  |
|  |  |  |  | a) Civil Works including Cost Index 2011 @ 24.29% of MPWD SOR 2007 for Mamit Division |  |  |  | Rs. 700,000.00 |  |  |
|  |  |  |  | Total |  | 1 |  | Rs. 700,000.00 |  |  |
|  |  |  |  | Say |  |  |  | Rs. 700,000.00 |  | Rs 1,400,000.00 |
| H |  |  |  | Renovation of quarters |  |  |  |  |  |  |
|  |  | 1 |  | Kawrthah CHC quarters |  | 1 |  |  |  |  |
|  |  | 2 |  | Ngalzawl Sub-centre quarters |  | 1 |  |  |  |  |
|  |  | 3 |  | Damdiai Sub-Centre quarters |  | 1 |  |  |  |  |
|  |  |  |  | a) Civil Works including Cost Index 2011 @ 24.29% of MPWD SOR 2007 for Mamit Division |  |  |  | Rs. 200,000.00 |  |  |
|  |  |  |  | Total |  | 1 |  | Rs. 200,000.00 |  |  |
|  |  |  |  | Say |  |  |  | Rs. 200,000.00 |  | Rs 600,000.00 |
| Grand total of Mamit District |  |  |  |  |  |  |  |  |  | 17,655,000.00 |
|  |  |  |  | SERCHHIP DISTRICT (Reconstruction) |  |  |  |  |  |  |
| A |  | 1 |  | N.Vanlaiphai PHC Type-III quarters |  | 1 |  |  |  |  |
|  |  |  |  | a) Civil Works including Cost Index 2011 @ 24.18% of MPWD SOR 2007 for Serchhip Division |  |  |  | Rs. 1,246,286.59 |  |  |
|  |  |  |  | b) Water Supply & Sanitary Installation @ 7.5% |  |  |  | Rs. 93,471.49 |  |  |
|  |  |  |  | c) Electrification @ 8.5% |  |  |  | Rs. 105,934.36 |  |  |
|  |  |  |  | d) Quality control & Monitoring @1% |  |  |  | Rs. 14,456.92 |  |  |
|  |  |  |  | e) Contingency & Administrative Charges @ 1% |  |  |  | Rs. 14,456.92 |  |  |
|  |  |  |  | Total |  | 1 |  | Rs. 1,474,606.30 |  |  |
|  |  |  |  | Say |  |  |  | Rs. 1,475,000.00 |  | Rs 1,475,000.00 |
| B |  | 1 |  | Chhingchhip PHC Type-II quarters |  | 1 |  |  |  |  |
|  |  |  |  | a) Civil Works including Cost Index 2011 @ 24.18% of MPWD SOR 2007 for Serchhip Division |  |  |  | Rs. 712,975.22 |  |  |
|  |  |  |  | b) Water Supply & Sanitary Installation @ 7.5% |  |  |  | Rs. 53,473.14 |  |  |
|  |  |  |  | c) Electrification @ 8.5% |  |  |  | Rs. 60,602.89 |  |  |
|  |  |  |  | d) Quality control & Monitoring @2% |  |  |  | Rs. 16,541.03 |  |  |
|  |  |  |  | e) Contingency & Administrative Charges @ 3% |  |  |  | Rs. 24,811.54 |  |  |
|  |  |  |  | Total |  | 1 |  | Rs. 868,403.82 |  |  |
|  |  |  |  | Say |  |  |  | Rs. 868,000.00 |  | Rs 868,000.00 |
| Grand Total of Serchhip District |  |  |  |  |  |  |  |  |  | Rs 2,343,000.00 |
| Grand Total of All the Districts |  |  |  |  |  |  |  |  |  | 155,999,000.00 |